## Dammam school-1
|  | Report Date | 2026-02-23
Project |  | Schools Information | [12 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School No | School ID | School Name (Arabic) | School Name (English) | School Level | School Gender (Boys / Girls) | Region | City | School Coordinates |  | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Dammam-1 | 1 | SS-ZAM-DAM1001 | الثانوية الثالثة والثلاثون بالدمام بنات | 33rd Secondary School for Girls in Dammam | Secondary | Girls | Dammam | Dammam | 26.3722 | 50.0388 | 26.3722226,50.0387821 | KFM2120660290159 | 10006265229 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Primary | Boys | Not Started
| 2 | SS-ZAM-DAM1002 | الابتداائية الرابعة والأربعون | 44th Elementary School | Primary | Girls | Dammam | Dammam | 26.3732 | 50.0393 | 26.37320366,50.0393325 | KFM2120660275093 | 10006262245 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Intermediate | Girls | In Progress
| 3 | SS-ZAM-DAM1003 | المتوسطة الثامنة والثلاثون بالدمام | 38th Intermediate School in Dammam | Intermediate | Girls | Dammam | Dammam | 26.3959 | 50.0682 | 26.3959349,50.06823244 | KFM2020660216536 | 10006265210 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Secondary | NA | Completed
| 4 | SS-ZAM-DAM1004 | الثانوية الثلاثون بالدمام | 30th Secondary School in Dammam | Secondary | Girls | Dammam | Dammam | 26.363 | 50.0657 | 26.36303717,50.06569779 | KFM2020660114420 | 10006250880 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Early Childhood |  | NA
| 5 | SS-ZAM-DAM1005 | متوسطة نسيبة بنت كعب بالدمام بنات | Nusaybah Bint Ka'ab Intermediate School for Girls in Dammam | Intermediate | Girls | Dammam | Dammam | 26.374 | 50.0781 | 26.37401624,50.07807658 | KFM2020660214829 | 10006266852 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Kindergarten
| 6 | SS-ZAM-DAM1006 | ثانوية البنات الأولى بالدمام | 1st Secondary School for Girls in Dammam | Secondary | Girls | Dammam | Dammam | 26.3963 | 50.0684 | 26.3962827,50.06840249 | KFM2120660292966 | 10006272617 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 7 | SS-ZAM-DAM1007 | المتوسطة السابعة والعشرون بالدمام | 27th Intermediate School in Dammam | Intermediate | Girls | Dammam | Dammam | 26.3743 | 50.0775 | 26.37427544,50.07747573 | KFM2120660292967 | 10006237064 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 8 | SS-ZAM-DAM1008 | الابتدائية الخامسة والعشرون بالدمام بنات | 25th Elementary School for Girls in Dammam | Primary | Girls | Dammam | Dammam | 26.3964 | 50.0683 | 26.39639772,50.0683237 | KFM2120660282346 | 10006190791 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 9 | SS-ZAM-DAM1009 | ابتدائية الامام الشافعي بنين | Imam Al-Shafi'i Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.3787 | 50.0339 | 26.37873988,50.03391419 | KFM2120660282278 | 10006240847 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 10 | SS-ZAM-DAM1010 | الثانويه الثامنه عشر بالدمام | 18th Secondary School in Dammam | Secondary | Girls | Dammam | Dammam | 26.3677 | 50.0899 | 26.36771999,50.08985448 | KFM2020660216927 | 10006248934 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 11 | SS-ZAM-DAM1011 | المتوسطة الرابعة عشر بالدمام بنات | 14th Intermediate School for Girls in Dammam | Intermediate | Girls | Dammam | Dammam | 26.4 | 50.0389 | 26.3999949,50.03886 | KFM2120660288280 | 10006230591 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 12 | SS-ZAM-DAM1012 | ثانوية الشفا ء بنت عبدالله بالدمام | Al-Shifa Bint Abdullah Secondary School in Dammam | Secondary | Girls | Dammam | Dammam | 26.3818 | 50.04 | 26.38175013,50.03999064 | KFM2020660022040 | 10018852692 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 13 | SS-ZAM-DAM1013 | الابتدائية السادسة والثلاثون بنات | 36th Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.3782 | 50.0346 | 26.37822536,50.03464339 | KFM2120660275116 | 10006253442 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 14 | SS-ZAM-DAM1014 | الابتدائية السادسة والخمسون بالدمام بنات | The 56th Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.3908 | 50.0723 | 26.39075907,50.07230923 | KFM2020660090583 | 10006229714 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 15 | SS-ZAM-DAM1015 | المتوسطة التاسعة والعشرون بالدمام بنات | The 29th Intermediate School in Dammam (Girls) | Intermediate | Girls | Dammam | Dammam | 26.4026 | 50.0206 | 26.40256605,50.02061429 | KFM2120660293322 | 10006246930 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 16 | SS-ZAM-DAM1016 | الثانوية التاسعة بالدمام بنات | The 9th Secondary School in Dammam (Girls) | Secondary | Girls | Dammam | Dammam | 26.4146 | 50.0497 | 26.41459325,50.04967187 | KFM2120660289142 | 10006272232 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 17 | SS-ZAM-DAM1017 | الابتدائية الخمسون بالدمام بنات | The 50th Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4134 | 50.0367 | 26.41343615,50.03674149 | KFM2020660090590 | 10006229017 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 18 | SS-ZAM-DAM1018 | ابتدائية مسك - سابقا معهد الامل | Misk Elementary School - formerly Al-Amal Institute | Primary | Girls | Dammam | Dammam | 26.4189 | 50.0397 | 26.41893211,50.03965147 | KFM2120660289032 | 10006228548 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 19 | SS-ZAM-DAM1019 | المتوسطة التاسعة عشرة بالدمام | The 19th Intermediate School in Dammam | Intermediate | Girls | Dammam | Dammam | 26.4104 | 50.0537 | 26.41042681,50.05370748 | KFM2120660289033 | 10006272921 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 20 | SS-ZAM-DAM1020 | الابتدائية الحادية والسبعون بالدمام بنات | The 71st Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4151 | 50.0502 | 26.41505318,50.05024148 | KFM2020660178987 | 10006268454 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 21 | SS-ZAM-DAM1021 | المتوسطة الثالثة عشر بالدمام | The 13th Intermediate School in Dammam | Intermediate | Girls | Dammam | Dammam | 26.4226 | 50.0171 | 26.42262401,50.01712892 | KFM2120660289138 | 10006240702 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 22 | SS-ZAM-DAM1022 | الابتدائية السابعة والثلاثون بالدمام بنات | The 37th Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.409 | 50.0393 | 26.40895366,50.03927524 | KFM2120660252943 | 10006263421 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 23 | SS-ZAM-DAM1023 | الابتدائية الثانية لتحفيظ القرآن الكريم بالدمام | The 2nd Elementary School for Quran Memorization in Dammam | Primary | Girls | Dammam | Dammam | 26.405 | 50.0493 | 26.40504293,50.04934471 | KFM2120660289139 | 10006272260 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 24 | SS-ZAM-DAM1024 | الابتدائية السادسة عشر بالدمام | The 16th Elementary School in Dammam | Primary | Girls | Dammam | Dammam | 26.4231 | 50.0082 | 26.42311937,50.00815099 | KFM2120660289023 | 10006240631 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 25 | SS-ZAM-DAM1025 | المتوسطة الأربعون بالدمام بنات | The 40th Intermediate School in Dammam (Girls) | Intermediate | Girls | Dammam | Dammam | 26.4373 | 50.0406 | 26.43734533,50.04061388 | KFM2120660244191 | 10006245306 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 26 | SS-ZAM-DAM1026 | متوسطة فاطمة الزهراء بنات | Fatima Al-Zahra Intermediate School for Girls | Intermediate | Girls | Dammam | Dammam | 26.4232 | 50.0082 | 26.42318914,50.00815228 | KFM2120660293745 | 10019102679 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 27 | SS-ZAM-DAM1027 | متوسطة الثالثة والعشرون بالدمام | The 23rd Intermediate School in Dammam | Intermediate | Girls | Dammam | Dammam | 26.4116 | 50.0293 | 26.41161025,50.02933705 | KFM2120660244237 | 10006245244 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 28 | SS-ZAM-DAM1028 | الثانوية السادسة والعشرون بالدمام بنات | The 26th Secondary School in Dammam (Girls) | Secondary | Girls | Dammam | Dammam | 26.4158 | 50.0217 | 26.41582887,50.02174772 | KFM2120660244193 | 10006245262 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 29 | SS-ZAM-DAM1029 | المتوسطة السابعة والثلاثون بالدمام بنات | The 37th Intermediate School in Dammam (Girls) | Intermediate | Girls | Dammam | Dammam | 26.4001 | 50.0219 | 26.40007805,50.02193715 | KFM2020660216973 | 10006262209 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 30 | SS-ZAM-DAM1030 | الابتدائية الحادية عشر بالدمام | Eleventh Elementary School in Dammam | Primary | Girls | Dammam | Dammam | 26.4128 | 50.0293 | 26.41275606,50.02926352 | KFM2020660113233 | 10006250923 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 31 | SS-ZAM-DAM1031 | الابتدائية الرابعة والخمسون بالدمام بنات | Fifty-Fourth Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4103 | 50.0216 | 26.41026744,50.02164546 | KFM2020660219326 | 10006262227 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 32 | SS-ZAM-DAM1032 | الثانوية الثالثة عشر بالدمام | Thirteenth Secondary School in Dammam | Secondary | Girls | Dammam | Dammam | 26.3938 | 50.0254 | 26.39381218,50.02539377 | KFM2120660266193 | 10006245324 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 33 | SS-ZAM-DAM1033 | الابتدائية الثانية والخمسون بالدمام بنات | Fifty-Second Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.3998 | 50.039 | 26.39977371,50.0390183 | KFM2120660244236 | 10006245226 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 34 | SS-ZAM-DAM1034 | ابتدائية اسيا بنت مزاحم بنات | Asia Bint Muzahim Elementary School (Girls) | Primary | Girls | Dammam | Dammam | 26.4102 | 50.0156 | 26.4101631,50.01563509 | KFM2120660293753 | 10085798114 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 35 | SS-ZAM-DAM1035 | ثانويه ام سلمة بالدمام | Umm Salama Secondary School in Dammam | Secondary | Girls | Dammam | Dammam | 26.4101 | 50.0156 | 26.41013427,50.01555999 | KFM2120660293787 | 10019110035 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 36 | SS-ZAM-DAM1036 | الابتدائية الرابعة والثلاثون بالدمام | Thirty-Fourth Elementary School in Dammam | Primary | Girls | Dammam | Dammam | 26.4156 | 50.0341 | 26.41556688,50.03406569 | KFM2020660214289 | 10006266262 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 37 | SS-ZAM-DAM1037 | المتوسطة الرابعة والعشرون بالدمام بنات | Twenty-Fourth Intermediate School in Dammam (Girls) | Intermediate | Girls | Dammam | Dammam | 26.4029 | 50.0428 | 26.40292253,50.04278097 | KFM2020660113226 | 10006250905 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 38 | SS-ZAM-DAM1038 | الابتدائية الرابعة والستون بالدمام بنات | Sixty-Fourth Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4087 | 50.056 | 26.40874916,50.05602309 | KFM2120660289087 | 10006264910 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 39 | SS-ZAM-DAM1039 | الابتدائية الثانية والاربعون بالدمام بنات | Forty-Second Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4199 | 50.0471 | 26.4198931,50.04712081 | KFM2020660022033 | 10006225921 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 40 | SS-ZAM-DAM1040 | المتوسطة العشرون بالدمام | Twentieth Intermediate School in Dammam | Intermediate | Girls | Dammam | Dammam | 26.4046 | 50.0446 | 26.40456943,50.0446236 | KFM2120660293058 | 10006228584 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 41 | SS-ZAM-DAM1041 | الابتدائية السابعة عشر بالدمام بنات | Seventeenth Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4342 | 50.0438 | 26.43422463,50.04376709 | KFM2120660293062 | 10006240641 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 42 | SS-ZAM-DAM1042 | الابتدائية السادسة لتحفيظ القرآن الكريم بالدمام | Sixth Elementary School for Quran Memorization in Dammam | Primary | Girls | Dammam | Dammam | 26.4142 | 50.037 | 26.41424561,50.03696666 | KFM2020660089231 | 10006263725 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 43 | SS-ZAM-DAM1043 | الثانوية السابعة والعشرون بالدمام بنات | Twenty-Seventh Secondary School in Dammam (Girls) | Secondary | Girls | Dammam | Dammam | 26.4118 | 50.0272 | 26.41176658,50.0272275 | KFM2120660289106 | 10006250100 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 44 | SS-ZAM-DAM1044 | الابتدائية السابعة والاربعون بالدمام بنات | 47th Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.4057 | 50.0267 | 26.40573874,50.02668831 | KFM2120660293059 | 10006228332 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 45 | SS-ZAM-DAM1045 | ابتدائية السادسة والاربعون الدمام بنات | 46th Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.3964 | 50.028 | 26.39639621,50.02795631 | KFM2120660289088 | 10006228708 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 46 | SS-ZAM-DAM1046 | الابتدائية الثالثة والاربعون بالدمام بنات | 43rd Elementary School in Dammam (Girls) | Primary | Girls | Dammam | Dammam | 26.406 | 50.0273 | 26.40604478,50.02729289 | KFM2120660289098 | 10006240622 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 47 | SS-ZAM-DAM1047 | متوسطة زيد بن الخطاب بنين | Zaid bin Al-Khattab Intermediate School (Boys) | Intermediate | Boys | Dammam | Dammam | 26.432 | 50.0331 | 26.43197804,50.03306265 | KFM2120660275124 | 10006262076 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 48 | SS-ZAM-DAM1048 | ثانوية عكاظ بالدمام بنين | Okaz Secondary School in Dammam (Boys) | Secondary | Boys | Dammam | Dammam | 26.4116 | 50.0267 | 26.41157877,50.02672523 | KFM2020660216848 | 10006241227 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 49 | SS-ZAM-DAM1049 | ابتدائية عبيدة بن الحارث بنين | Ubaidah bin Al-Harith Elementary School (Boys) | Primary | Boys | Dammam | Dammam | 26.4005 | 50.0358 | 26.40046145,50.03582794 | KFM2120660289136 | 10006231445 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 50 | SS-ZAM-DAM1050 | ابتدائية مكة المكرمة | Makkah Al-Mukarramah Elementary School | Primary | Boys | Dammam | Dammam | 26.3952 | 50.0284 | 26.39524825,50.02843945 | KFM2120660293087 | 10006228931 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 51 | SS-ZAM-DAM1051 | متوسطة عبدالله بن عامر بالدمام بنين | Abdullah bin Amer Intermediate School in Dammam (Boys) | Intermediate | Boys | Dammam | Dammam | 26.4134 | 50.0152 | 26.41338252,50.01515041 | KFM2120660293027 | 10006242716 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 52 | SS-ZAM-DAM1052 | متوسطة عين جالوت | Ain Jalut Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.4039 | 50.045 | 26.40387992,50.04499163 | KFM2120660285937 | 10006216841 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 53 | SS-ZAM-DAM1053 | ابتدائية انس بن فضالة بنين | Anas bin Fadalah Elementary School (Boys) | Primary | Boys | Dammam | Dammam | 26.4 | 50.0384 | 26.40004128,50.03838803 | SMR2220661007940 | 10006241933 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 54 | SS-ZAM-DAM1054 | مدرسة عمرو بن معاذ الابتدائية | Amr bin Muadh Elementary School | Primary | Boys | Dammam | Dammam | 26.409 | 50.093 | 26.40904256,50.09304894 | KFM2120660289028 | 10006228501 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 55 | SS-ZAM-DAM1055 | ثانوية الشيخ عبدالعزيز بن باز بنين | Sheikh Abdulaziz bin Baz Secondary School (Boys) | Secondary | Boys | Dammam | Dammam | 26.3682 | 50.09 | 26.3682057,50.0900413 | KFM2120660293021 | 10006224941 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 56 | SS-ZAM-DAM1056 | ابتدائية المدينة المنورة بنين | Madinah Al-Munawwarah Elementary School (Boys) | Primary | Boys | Dammam | Dammam | 26.4152 | 50.0824 | 26.41519107,50.08243419 | KFM2120660289025 | 10006228379 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 57 | SS-ZAM-DAM1057 | ابتدائية اسامة بن زيد | Usamah bin Zaid Elementary School | Primary | Boys | Dammam | Dammam | 26.4152 | 50.0825 | 26.41515026,50.08246623 | KFM2020660220826 | 10006181451 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 58 | SS-ZAM-DAM1058 | متوسطة النعمان بن مقرن بنين | Al-Nu'man bin Muqrin Intermediate School (Boys) | Intermediate | Boys | Dammam | Dammam | 26.4044 | 50.08 | 26.4044197,50.07995742 | KFM2120660293089 | 10006224923 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 59 | SS-ZAM-DAM1059 | ابتدائية الوليد بن القاسم | Al-Walid bin Al-Qasim Elementary School | Primary | Boys | Dammam | Dammam | 26.4044 | 50.0807 | 26.4044426,50.0806909 | KFM2120660293750 | 10006274012 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 60 | SS-ZAM-DAM1060 | متوسطة عبدالرحمن الغافقي | Abdulrahman Al-Ghafiqi Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.4095 | 50.0787 | 26.40951427,50.07871968 | KFM2020660184075 | 10090868828 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 61 | SS-ZAM-DAM1061 | ابتدائية مجمع سليمان بن عبدالملك التعليمي بنين | Sulaiman Bin Abdulmalik Educational Complex Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4163 | 50.0863 | 26.41630568,50.08634574 | KFM2020660220902 | 10006244944 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 62 | SS-ZAM-DAM1062 | ابتدائية مجمع عقبة بن عامر التعليمي بنين | Uqba Bin Amer Educational Complex Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4099 | 50.0775 | 26.40985933,50.07749141 | KFM2120660286612 | 10006230457 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 63 | SS-ZAM-DAM1063 | متوسطة عمير بن الحمام الانصاري بنين | Umair Bin Al-Hamam Al-Ansari Intermediate School for Boys | Intermediate | Boys | Dammam | Dammam | 26.4108 | 50.0771 | 26.41076225,50.07714868 | KFM2120660289067 | 10006224905 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 64 | SS-ZAM-DAM1064 | ثانوية القاسم بن محمد بن ابي بكر بنين | Al-Qasim Bin Muhammad Bin Abi Bakr Secondary School for Boys | Secondary | Boys | Dammam | Dammam | 26.3704 | 50.0777 | 26.370384,50.07772 | KFM2120660289108 | 10006268973 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 65 | SS-ZAM-DAM1065 | مدرسة عمرو بن الجموح | Amr Bin Al-Jamuh School | Primary | Boys | Dammam | Dammam | 26.3892 | 50.0998 | 26.38921632,50.09984104 | KFM2120660293382 | 10006241236 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 66 | SS-ZAM-DAM1066 | ثانوية الجهاد بنين | Al-Jihad Secondary School for Boys | Secondary | Boys | Dammam | Dammam | 26.4215 | 50.0938 | 26.42153432,50.09381795 | KFM2120660289071 | 10006228056 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 67 | SS-ZAM-DAM1067 | ابتدائية النور بنين | Al-Nour Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4156 | 50.1184 | 26.41558745,50.11843415 | KFM2120660293068 | 10006272582 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 68 | SS-ZAM-DAM1068 | متوسطة مجمع عقبة بن عامر التعليمي | Uqba Bin Amer Educational Complex Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.4177 | 50.0989 | 26.41771755,50.09889419 | KFM2120660286614 | 10006230475 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 69 | SS-ZAM-DAM1069 | ابتدائية قتيبه بن مسلم بنين | Qutaiba Bin Muslim Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4052 | 50.0803 | 26.40517298,50.08027801 | KFM2120660289073 | 10006240829 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 70 | SS-ZAM-DAM1070 | متوسطة مجمع الامام الدوري لتحفيظ القران الكريم بنين | Imam Al-Duri Complex for Quran Memorization Intermediate School for Boys | Intermediate | Boys | Dammam | Dammam | 26.4043 | 50.08 | 26.4042625,50.07995115 | KFM2120660292799 | 10006273098 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 71 | SS-ZAM-DAM1071 | ابتدائية عثمان بن عفان | Uthman Bin Affan Elementary School | Primary | Boys | Dammam | Dammam | 26.3875 | 50.1088 | 26.387465,50.10877065 | KFM2120660289105 | 10006242752 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 72 | SS-ZAM-DAM1072 | ابتدائية ابوداوود | Abu Dawood Elementary School | Primary | Boys | Dammam | Dammam | 26.3702 | 50.1205 | 26.37017301,50.12054215 | KFM2120660276054 | 10006241540 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 73 | SS-ZAM-DAM1073 | الثانوية الرابعة والعشرون بنات | 24th Girls' Secondary School | Secondary | Girls | Dammam | Dammam | 26.3801 | 50.119 | 26.38012878,50.11903547 | KFM2020660221711 | 10006242734 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 74 | SS-ZAM-DAM1074 | ثانوية عبدالله بن الزبير بنين | Abdullah bin Al-Zubair Boys' Secondary School | Secondary | Boys | Dammam | Dammam | 26.4156 | 50.1194 | 26.41557157,50.11937502 | KFM2120660266108 | 10006266763 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 75 | SS-ZAM-DAM1075 | الابتدائية الأولى بالنابية | 1st Al-Nabiyah Elementary School | Primary | Boys | Dammam | Dammam | 26.3803 | 50.1199 | 26.38033168,50.11985637 | KFM2020660230497 | 10006292208 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 76 | SS-ZAM-DAM1076 | متوسطة الأولى بالنابية بنات | 1st Al-Nabiyah Girls' Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4246 | 50.1104 | 26.42456673,50.11041903 | KFM2020660218229 | 10006247786 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 77 | SS-ZAM-DAM1077 | الثانوية الاولى بالنابية بنات | 1st Al-Nabiyah Girls' Secondary School | Secondary | Girls | Dammam | Dammam | 26.4165 | 50.0707 | 26.41645132,50.07073961 | KFM2020660218208 | 10006248461 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 78 | SS-ZAM-DAM1078 | الابتدائية التاسعة والأربعون بالدمام بنات | 49th Dammam Girls' Elementary School | Primary | Girls | Dammam | Dammam | 26.4169 | 50.0728 | 26.41692491,50.07275524 | KFM2020660225023 | 10006248836 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 79 | SS-ZAM-DAM1079 | متوسطة مجمع ابن القيم التعليمي بنين | Ibn Al-Qayyim Educational Complex Boys' Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.4241 | 50.0688 | 26.42405365,50.06875079 | KFM2020660218390 | 10006247481 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 80 | SS-ZAM-DAM1080 | ثانوية الطفيل بن عمرو برنامج فكري متوسطة بنين | Al-Tufail bin Amr Boys' Fikri Program Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.3586 | 50.0474 | 26.3585817,50.0474278 | KFM2020660215281 | 10006274891 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 81 | SS-ZAM-DAM1081 | ثانوية المجيدية بنين | Al-Majidiyah Boys' Secondary School | Secondary | Boys | Dammam | Dammam | 26.4139 | 50.0367 | 26.4138841,50.036742 | KFM2120660295002 | 10006258752 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 82 | SS-ZAM-DAM1082 | متوسطة موسى بن نصير بسيهات بنين | Musa bin Nusair Boys' Intermediate School in Saihat | Intermediate | Boys | Dammam | Dammam | 26.4256 | 50.0911 | 26.42563886,50.09114217 | KFM2020660215287 | 10006277284 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 83 | SS-ZAM-DAM1083 | ثانوية سيهات | Saihat Secondary School | Secondary | Boys | Dammam | Dammam | 26.4239 | 50.0659 | 26.42388867,50.06591969 | KFM2020660219010 | 10006277767 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 84 | SS-ZAM-DAM1084 | متوسطة سعد بن الحارث | Saad bin Al-Harith Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.4186 | 50.0706 | 26.41861352,50.07062815 | KFM2020660218207 | 10006247740 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 85 | SS-ZAM-DAM1085 | ابتدائية اسامة بن عمير بنين | Usama bin Umair Boys' Elementary School | Primary | Boys | Dammam | Dammam | 26.4254 | 50.1218 | 26.42544426,50.12184984 | KFM2120660304226 | 10102374166 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 86 | SS-ZAM-DAM1086 | المتوسطة الرابعة بسيهات بنات | 4th Saihat Girls' Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4228 | 50.122 | 26.42280349,50.12203191 | KFM2020660234013 | 10006259123 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 87 | SS-ZAM-DAM1087 | الثانوية الخامسة بسيهات بنات | Fifth Secondary School in Saihat for Girls | Secondary | Girls | Dammam | Dammam | 26.4217 | 50.0773 | 26.4216532,50.07725048 | KFM2020660215016 | 10006248943 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 88 | SS-ZAM-DAM1088 | المتوسطة الخامسة بسيهات بنات | Fifth Intermediate School in Saihat for Girls | Intermediate | Girls | Dammam | Dammam | 26.4252 | 50.0923 | 26.42520695,50.09231652 | KFM2020660214308 | 10006248059 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 89 | SS-ZAM-DAM1089 | المدرسة الابتدائية التاسعة بسيهات بنات | Ninth Elementary School in Saihat for Girls | Primary | Girls | Dammam | Dammam | 26.434 | 50.1028 | 26.43403551,50.10283269 | KFM2020660206173 | 10006259141 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 90 | SS-ZAM-DAM1090 | الثانوية الرابعة بسيهات بنات | Fourth Secondary School in Saihat for Girls | Secondary | Girls | Dammam | Dammam | 26.434 | 50.0894 | 26.43399013,50.0893606 | KFM2020660218326 | 10006259464 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 91 | SS-ZAM-DAM1091 | المتوسطة الثالثة بسيهات | Third Intermediate School in Saihat | Intermediate | Girls | Dammam | Dammam | 26.4337 | 50.0903 | 26.43369069,50.09034958 | KFM2020660218321 | 10006248219 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 92 | SS-ZAM-DAM1092 | الابتدائيه الثامنة بسيهات بنات | Eighth Elementary School in Saihat for Girls | Primary | Girls | Dammam | Dammam | 26.4258 | 50.0786 | 26.42580464,50.07861901 | KFM2020660215014 | 10006248961 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 93 | SS-ZAM-DAM1093 | المتوسطة السابعة بسيهات بنات | Seventh Intermediate School in Saihat for Girls | Intermediate | Girls | Dammam | Dammam | 26.4276 | 50.0999 | 26.42757427,50.0999148 | KFM2020660215013 | 10006248925 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 94 | SS-ZAM-DAM1094 | الابتدائية الخامسه بسيهات بنات | Fifth Elementary School in Saihat for Girls | Primary | Girls | Dammam | Dammam | 26.4336 | 50.0915 | 26.4335871,50.09147497 | KFM2020660221652 | 10006277328 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 95 | SS-ZAM-DAM1095 | الثانوية الأولى بالملاحة بنات | First Secondary School in Al-Malaha for Girls | Secondary | Girls | Dammam | Dammam | 26.4315 | 50.0928 | 26.43149861,50.09278187 | KFM2020660221414 | 10006267027 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 96 | SS-ZAM-DAM1096 | ابتدائية الربيعية بنين | Al-Rabee'iyah Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4303 | 50.0985 | 26.43034694,50.09848423 | KFM2120660295591 | 10006287905 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 97 | SS-ZAM-DAM1097 | ابتدائية الاولى لتحفيظ القران الكريم بنات | First Elementary School for Quran Memorization for Girls | Primary | Girls | Dammam | Dammam | 26.4298 | 50.113 | 26.42978307,50.11300182 | KFM2020660214327 | 10006241254 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 98 | SS-ZAM-DAM1098 | ابتدائية السادسة بالدمام بنات | Sixth Elementary School in Dammam for Girls | Primary | Girls | Dammam | Dammam | 26.4222 | 50.0763 | 26.42224722,50.07634325 | KFM2020660222959 | 10006249600 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 99 | SS-ZAM-DAM1099 | ابتدائية خالد بن حزام للطفولة المبكرة | Khaled Bin Hazam Elementary School for Early Childhood | Primary | Boys | Dammam | Dammam | 26.4217 | 50.0775 | 26.42174403,50.07750927 | KFM2020660217353 | 10006228950 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 100 | SS-ZAM-DAM1100 | الابتدائية الأربعون بالدمام | Fortieth Elementary School in Dammam | Primary | Girls | Dammam | Dammam | 26.4348 | 50.1231 | 26.43483532,50.12308367 | KFM2120660261049 | 10006245422 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 101 | SS-ZAM-DAM1101 | الابتدائية التاسعة بنات بالدمام | Ninth Elementary School for Girls in Dammam | Primary | Girls | Dammam | Dammam | 26.4354 | 50.0906 | 26.43540278,50.09056443 | KFM2020660225836 | 10006180041 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 102 | SS-ZAM-DAM1102 | الابتدائية التاسعة والثلاثون بالدمام بنات | Thirty-Ninth Elementary School for Girls in Dammam | Primary | Girls | Dammam | Dammam | 26.4348 | 50.0646 | 26.43480206,50.06462627 | KFM2020660075621 | 10006251009 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 103 | SS-ZAM-DAM1103 | الابتدائية الثالثة بالدمام بنات | Third Elementary School for Girls in Dammam | Primary | Girls | Dammam | Dammam | 26.4401 | 50.0752 | 26.44014453,50.07523607 | KFM2120660290868 | 10006248916 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 104 | SS-ZAM-DAM1104 | الابتدائية الثالثة والعشرون بالدمام بنات | Twenty-Third Elementary School for Girls in Dammam | Primary | Girls | Dammam | Dammam | 26.4571 | 50.0904 | 26.457121,50.0904493 | KFM2020660215919 | 10006216153 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 105 | SS-ZAM-DAM1105 | الابتدائية الثانية بالدمام بنات | Second Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4467 | 50.0787 | 26.44666944,50.07872853 | KFM2020660220008 | 10006236281 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 106 | SS-ZAM-DAM1106 | الابتدائية الثانية عشر بالدمام بنات | Twelfth Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4446 | 50.1259 | 26.44459942,50.12590246 | KFM2020660225111 | 10006248630 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 107 | SS-ZAM-DAM1107 | الابتدائية الثلاثون بالدمام بنات | Thirtieth Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4083 | 50.1851 | 26.4083447,50.1851046 | KFM2020660226731 | 10006272180 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 108 | SS-ZAM-DAM1108 | الثانوية التاسعة عشر بالدمام بنات | Nineteenth Dammam Secondary School for Girls | Secondary | Girls | Dammam | Dammam | 26.4455 | 50.0726 | 26.4455154,50.07261568 | KFM2120660293049 | 10006226811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 109 | SS-ZAM-DAM1109 | الثانوية الخامسة والعشرون بالدمام بنات | Twenty-Fifth Dammam Secondary School for Girls | Secondary | Girls | Dammam | Dammam | 26.4295 | 50.0708 | 26.42953717,50.07077505 | KFM2120660285938 | 10006248891 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 110 | SS-ZAM-DAM1110 | الثانوية السابعة بالدمام | Seventh Dammam Secondary School | Secondary | Girls | Dammam | Dammam | 26.4466 | 50.078 | 26.44662174,50.07802434 | KFM2020660225935 | 10006230822 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 111 | SS-ZAM-DAM1111 | الثانوية السادسة بالدمام بنات | Sixth Dammam Secondary School for Girls | Secondary | Girls | Dammam | Dammam | 26.4392 | 50.0802 | 26.43915527,50.08022461 | KFM2020660220838 | 10006264375 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 112 | SS-ZAM-DAM1112 | الروضة الثانية بالدمام | Second Dammam Kindergarten | Kindergarten | Girls | Dammam | Dammam | 26.4408 | 50.1121 | 26.44076076,50.11207545 | KFM2020660219978 | 10006253390 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 113 | SS-ZAM-DAM1113 | المتوسطة الثانية بالدمام | Second Dammam Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4497 | 50.0725 | 26.44970153,50.07253728 | KFM2020660217358 | 10006253658 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 114 | SS-ZAM-DAM1114 | المتوسطة الحادية والثلاثون بالدمام | Thirty-First Dammam Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4323 | 50.0768 | 26.43232438,50.07680994 | KFM2020660075623 | 10006251027 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 115 | SS-ZAM-DAM1115 | المتوسطة الخامسة والعشرون بالدمام | Twenty-Fifth Dammam Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4469 | 50.0869 | 26.44694455,50.08688589 | KFM2020660225025 | 10006248818 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 116 | SS-ZAM-DAM1116 | ابتدائية الثالثة عشر بالدمام | Thirteenth Dammam Elementary School | Primary | Girls | Dammam | Dammam | 26.4466 | 50.1288 | 26.44664699,50.12879741 | KFM2020660225911 | 10006253685 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 117 | SS-ZAM-DAM1117 | متوسطة الخليج بالدمام بنين | Al-Khaleej Intermediate School for Boys in Dammam | Intermediate | Boys | Dammam | Dammam | 26.4399 | 50.0938 | 26.43993758,50.09380553 | KFM2120660291964 | 10006229886 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 118 | SS-ZAM-DAM1118 | متوسطة الزهور بالدمام بنين | Al-Zuhour Intermediate School for Boys in Dammam | Intermediate | Boys | Dammam | Dammam | 26.4459 | 50.0868 | 26.44594834,50.08683209 | KFM2120660266256 | 10006268946 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 119 | SS-ZAM-DAM1119 | ابتدائية نافع المدني لتحفيظ القرآن الكريم بالدمام بنين | Nafe' Al-Madani Elementary School for Quran Memorization in Dammam for Boys | Primary | Boys | Dammam | Dammam | 26.4392 | 50.1105 | 26.43918047,50.11046789 | KFM2020660225926 | 10102844306 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 120 | SS-ZAM-DAM1120 | ابتدائية عمرو بن العاص بنين بالدمام | Amr Ibn Al-Aas Elementary School for Boys in Dammam | Primary | Boys | Dammam | Dammam | 26.4398 | 50.0931 | 26.43976341,50.09308447 | KFM2020660218717 | 10006254056 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 121 | SS-ZAM-DAM1121 | ثانوية الدمام | Dammam Secondary School | Secondary | Boys | Dammam | Dammam | 26.4367 | 50.0691 | 26.43666815,50.0691003 | KFM2020660224820 | 10006263592 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 122 | SS-ZAM-DAM1122 | ثانوية القدس بنين | Al-Quds Secondary School for Boys | Secondary | Boys | Dammam | Dammam | 26.4484 | 50.0944 | 26.44843593,50.09442554 | KFM2120660290115 | 10006229545 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 123 | SS-ZAM-DAM1123 | ابتدائية سعيد بن عامر بنين | Saeed Ibn Amer Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4303 | 50.0739 | 26.43027008,50.07394169 | KFM2020660214828 | 10006266905 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 124 | SS-ZAM-DAM1124 | ابتدائية صلاح الدين | Salah Al-Din Elementary School | Primary | Boys | Dammam | Dammam | 26.4607 | 50.0533 | 26.4607155,50.05329918 | KFM2020660217350 | 10006239953 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 125 | SS-ZAM-DAM1125 | ابتدائية المقداد بن عمرو | Al-Miqdad Bin Amr Elementary School | Primary | Boys | Dammam | Dammam | 26.4659 | 50.0561 | 26.46589195,50.05606858 | KFM2020660075451 | 10006227854 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 126 | SS-ZAM-DAM1126 | ابتدائية المنهل | Al-Manhal Elementary School | Primary | Boys | Dammam | Dammam | 26.466 | 50.0564 | 26.4660095,50.05641226 | KFM2120660244316 | 10006255581 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 127 | SS-ZAM-DAM1127 | متوسطة عثمان بن العاص بنين | Uthman Bin Al-Aas Intermediate School for Boys | Intermediate | Boys | Dammam | Dammam | 26.4175 | 50.1202 | 26.41750404,50.12017656 | KFM2020660218718 | 10006255643 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 128 | SS-ZAM-DAM1128 | متوسطة سعيد بن زيد بنين | Saeed Bin Zaid Intermediate School for Boys | Intermediate | Boys | Dammam | Dammam | 26.4609 | 50.0524 | 26.46090165,50.0523528 | KFM2020660225922 | 10006228511 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 129 | SS-ZAM-DAM1129 | الثانوية الشيخ محمد بن صالح بن عثيمين | Sheikh Muhammad Bin Saleh Bin Uthaimin Secondary School | Secondary | Boys | Dammam | Dammam | 26.4661 | 50.0557 | 26.46606623,50.05570952 | KFM2020660225049 | 10006253999 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 130 | SS-ZAM-DAM1130 | ثانوية الغزالي | Al-Ghazali Secondary School | Secondary | Boys | Dammam | Dammam | 26.4581 | 50.0593 | 26.45810209,50.05927754 | KFM2120660289475 | 10006230143 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 131 | SS-ZAM-DAM1131 | متوسطة السرايا بنين | Al-Saraya Intermediate School for Boys | Intermediate | Boys | Dammam | Dammam | 26.4714 | 50.09 | 26.47143993,50.08998154 | KFM2120660290118 | 10006240337 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 132 | SS-ZAM-DAM1132 | الابتدائية السابعة بالدمام بنات | Seventh Elementary School in Dammam for Girls | Primary | Girls | Dammam | Dammam | 26.4659 | 50.0561 | 26.465895,50.05607007 | KFM2120660277589 | 10006263663 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 133 | SS-ZAM-DAM1133 | المتوسطة التاسعة بحي القزاز | Ninth Intermediate School in Al-Qazzaz District | Intermediate | Girls | Dammam | Dammam | 26.4504 | 50.1126 | 26.45044887,50.11260729 | SMR2320661031860 | 10006239944 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 134 | SS-ZAM-DAM1134 | ابتدائية القدس بنين | Al-Quds Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4158 | 50.1186 | 26.4157869,50.1186181 | LYE2020810301055 | 10005857388 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 135 | SS-ZAM-DAM1135 | ثانوية المدينة المنورة | Al-Madinah Al-Munawwarah Secondary School | Secondary | Boys | Dammam | Dammam | 26.472 | 50.0903 | 26.4720235,50.09028157 | KFM2020660224810 | 10006241245 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 136 | SS-ZAM-DAM1136 | ابتدائية سعيد بن العاص بنين | Saeed Bin Al-Aas Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4535 | 50.091 | 26.45345311,50.09095363 | KFM2020660225918 | 10006224960 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 137 | SS-ZAM-DAM1137 | ابتدائية بدر الكبرى | Badr Al-Kubra Elementary School | Primary | Boys | Dammam | Dammam | 26.451 | 50.113 | 26.45098788,50.11296493 | KFM2120660289478 | 10006242636 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 138 | SS-ZAM-DAM1138 | ابتدائية نعيم بن عبدالله النحام للطفولة المبكرة | Naeem Bin Abdullah Al-Nahham Early Childhood Elementary School | Primary | Boys | Dammam | Dammam | 26.4569 | 50.09 | 26.45688167,50.09001756 | KFM2020660221626 | 10006240220 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 139 | SS-ZAM-DAM1139 | المتوسطة الثالثة وثلاثون بالدمام بنات | Thirty-Third Intermediate School in Dammam for Girls | Intermediate | Girls | Dammam | Dammam | 26.4545 | 50.0736 | 26.45454728,50.0736235 | KFM2120660289034 | 10006229732 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 140 | SS-ZAM-DAM1140 | الابتدائية التاسعة والخمسون بالدمام بنات | The 59th Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4696 | 50.095 | 26.46962718,50.09502826 | KFM2120660290208 | 10006263743 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 141 | SS-ZAM-DAM1141 | المتوسطة الثانية والثلاثون بالدمام | The 32nd Dammam Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4179 | 50.1191 | 26.41791044,50.11912876 | KFM2120660258161 | 10006244701 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 142 | SS-ZAM-DAM1142 | متوسطة الجزيرة بنين | Al-Jazirah Intermediate School for Boys | Intermediate | Boys | Dammam | Dammam | 26.4593 | 50.0762 | 26.45933761,50.07621108 | KFM2020660214294 | 10006181352 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 143 | SS-ZAM-DAM1143 | المتوسطة الحادية والعشرون بالدمام | The 21st Dammam Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.472 | 50.0906 | 26.47199804,50.09064835 | KFM2020660225046 | 10006248854 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 144 | SS-ZAM-DAM1144 | المتوسطة الثلاثون بالدمام | The 30th Dammam Intermediate School | Intermediate | Girls | Dammam | Dammam | 26.4502 | 50.113 | 26.45021109,50.11302676 | KFM2020660055954 | 10006241307 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 145 | SS-ZAM-DAM1145 | المتوسطة الثامنة عشر بالدمام بنات | The 18th Dammam Intermediate School for Girls | Intermediate | Girls | Dammam | Dammam | 26.45 | 50.0905 | 26.44995352,50.09049275 | KFM2120660261024 | 10006239793 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 146 | SS-ZAM-DAM1146 | الثانوية العشرون بالدمام بنات | The 20th Dammam Secondary School for Girls | Secondary | Girls | Dammam | Dammam | 26.456 | 50.0986 | 26.45602375,50.09862017 | KFM2020660225045 | 10006244784 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 147 | SS-ZAM-DAM1147 | الابتدائية الرابعة عشر بالدمام بنات | The 14th Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4704 | 50.0078 | 26.47036977,50.00776265 | KFM2020660215949 | 10006248335 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 148 | SS-ZAM-DAM1148 | الابتدائية التاسعة عشر بالدمام | The 19th Dammam Elementary School | Primary | Girls | Dammam | Dammam | 26.4722 | 50.0068 | 26.47217737,50.00678474 | KFM2020660055851 | 10006246690 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 149 | SS-ZAM-DAM1149 | ثانوية الامام محمد بن سعود | Imam Muhammad bin Saud Secondary School | Secondary | Boys | Dammam | Dammam | 26.4716 | 50.0073 | 26.47164088,50.0073489 | KFM2120660289031 | 10006272448 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 150 | SS-ZAM-DAM1150 | الثانوية السابعة عشر بالدمام | The 17th Dammam Secondary School | Secondary | Girls | Dammam | Dammam | 26.4775 | 50.0542 | 26.47749226,50.05421854 | KFM2120660287220 | 10006228314 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 151 | SS-ZAM-DAM1151 | مجمع مسلمة بن عبدالملك التعليمي- القسم المتوسط بنين | Muslimah bin Abdulmalik Educational Complex - Intermediate Section for Boys | Intermediate | Boys | Dammam | Dammam | 26.4935 | 50.0326 | 26.49353742,50.03255674 | KFM2120660290209 | 10006241531 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 152 | SS-ZAM-DAM1152 | الابتدائية التاسعة والعشرون بالدمام بنات | The 29th Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.5393 | 50.0259 | 26.53929025,50.02591793 | KFM2020660217322 | 10006253424 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 153 | SS-ZAM-DAM1153 | الابتدائية الثالثة لتحفيظ القرآن الكريم بالدمام | The 3rd Dammam Elementary School for Quran Memorization | Primary | Girls | Dammam | Dammam | 26.4939 | 50.0339 | 26.4938641,50.03394207 | KFM2020660219924 | 10006231276 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 154 | SS-ZAM-DAM1154 | ابتدائية مجمع النعمان بن بشير التعليمي بنين | Al-Nu'man bin Bashir Educational Complex Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.482 | 50.0393 | 26.48202375,50.03931249 | KFM2120660291961 | 10006272072 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 155 | SS-ZAM-DAM1155 | المتوسطة الثانية لتحفيظ القرآن بالدمام بنات | The 2nd Dammam Intermediate School for Quran Memorization for Girls | Intermediate | Girls | Dammam | Dammam | 26.4661 | 50.0316 | 26.46607474,50.03155791 | SMR2220661008744 | 10006263000 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 156 | SS-ZAM-DAM1156 | الابتدائية الثانية والعشرون بالدمام بنات | The 22nd Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4738 | 50.0615 | 26.47375787,50.06150874 | KFM2120660294668 | 10006246054 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 157 | SS-ZAM-DAM1157 | الثانوية الثانية والثلاثون بالدمام بنات | 22nd Dammam Intermediate School for Girls | Intermediate | Girls | Dammam | Dammam | 26.471 | 50.0427 | 26.47096345,50.04271601 | KFM2120660282334 | 10006262405 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 158 | SS-ZAM-DAM1158 | المتوسطة الثانية والعشرون بالدمام بنات | 36th Dammam Intermediate School for Girls | Intermediate | Girls | Dammam | Dammam | 26.471 | 50.0428 | 26.47102107,50.04275892 | KFM2120660290869 | 10006229053 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 159 | SS-ZAM-DAM1159 | المتوسطة السادسة والثلاثون بالدمام بنات | 1st Intermediate School for Adult Education in Khobar | Intermediate | Girls | Dammam | Dammam | 26.4815 | 50.042 | 26.48151423,50.04199122 | KFM2020660219304 | 10006262380 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 160 | SS-ZAM-DAM1160 | المتوسطة الأولى لتعليم الكبيرات بالخبر | Al-Mazra'a Elementary School for Boys | Primary | Boys | Dammam | Dammam | 26.4708 | 50.0423 | 26.47084716,50.04229624 | KFM2020660181290 | 10006206569 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 161 | SS-ZAM-DAM1161 | ابتدائية المزرعة بنين | 8th Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.471 | 50.0427 | 26.4709872,50.04272457 | KFM2020660224556 | 10006254431 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 162 | SS-ZAM-DAM1162 | الابتدائية الثامنة بالدمام بنات | 8th Dammam Intermediate School for Girls | Intermediate | Girls | Dammam | Dammam | 26.4897 | 50.0299 | 26.48973752,50.02986404 | KFM2020660217360 | 10006213106 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 163 | SS-ZAM-DAM1163 | المتوسطة الثامنة بالدمام بنات | 21st Dammam Elementary School | Primary | Girls | Dammam | Dammam | 26.4803 | 50.0575 | 26.48027053,50.05750315 | KFM2020660224817 | 10006236307 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 164 | SS-ZAM-DAM1164 | ابتدائية الحادية والعشرون بالدمام | 48th Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4798 | 50.0563 | 26.47983749,50.05630958 | KFM2120660288929 | 10006239784 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 165 | SS-ZAM-DAM1165 | الابتدائية الثامنة والاربعون بالدمام بنات | 23rd Dammam Secondary School | Secondary | Girls | Dammam | Dammam | 26.473 | 50.055 | 26.47297701,50.05500636 | KFM2120660261021 | 10006262700 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 166 | SS-ZAM-DAM1166 | الثانوية الثالثة والعشرون بالدمام | 8th Dammam Secondary School for Girls | Secondary | Girls | Dammam | Dammam | 26.5137 | 50.0026 | 26.51368705,50.00263419 | KFM2020660225030 | 10006248792 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 167 | SS-ZAM-DAM1167 | الثانوية الثامنة بالدمام بنات | 4th Dammam Secondary School | Secondary | Girls | Dammam | Dammam | 26.5677 | 50.0793 | 26.56768742,50.07925051 | KFM2120660290747 | 10006252221 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 168 | SS-ZAM-DAM1168 | الثانوية الرابعة بالدمام | Al-Suyuti Educational Complex Secondary School for Boys | Secondary | Boys | Dammam | Dammam | 26.3101 | 50.1878 | 26.31009217,50.18782357 | KFM2020660222644 | 10006213017 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 169 | SS-ZAM-DAM1169 | ثانوية مجمع السيوطي التعليمي بنين | 29th Dammam Secondary School for Girls | Secondary | Girls | Dammam | Dammam | 26.3424 | 50.1363 | 26.34244068,50.13634284 | KFM2120660293744 | 10090650537 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 170 | SS-ZAM-DAM1170 | الثانوية التاسعة والعشرون بنات | 26th Dammam Intermediate School for Girls | Intermediate | Girls | Dammam | Dammam | 26.4303 | 50.094 | 26.4302929,50.0940273 | KFM2020660221745 | 10006241263 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 171 | SS-ZAM-DAM1171 | المتوسطة السادسة والعشرون بالدمام بنات | 41st Dammam Elementary School for Girls | Primary | Girls | Dammam | Dammam | 26.4056 | 50.182 | 26.40562362,50.18199898 | KFM2020660219921 | 10006248291 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 172 | SS-ZAM-DAM1172 | الابتدائية الحادية والاربعون بالدمام بنات | Sanabis Intermediate School in Qatif | Intermediate | Girls | Dammam | Dammam | 26.3198 | 50.2038 | 26.31982282,50.20381745 | KFM2120660289143 | 10006272223 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 173 | SS-ZAM-DAM1173 | متوسطه سنابس بالقطيف | Sanabis Intermediate School in Qatif | Intermediate | Boys | Dammam | Dammam | 26.5862 | 50.0802 | 26.5861908,50.0802176 | KFM2120660294464 | 10006287601‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 174 | SS-ZAM-DAM1174 | ثانويه النجاح بالقطيف | Al-Najh Secondary School in Qatif | Secondary | Boys | Dammam | Dammam | 26.573 | 50.0475 | 26.5729929,50.0474596 | KFM2020660229761 | 10006256883‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 175 | SS-ZAM-DAM1175 | ابتدائية سعد بن الربيع بالقطيف | Saad bin Al-Rabee Elementary School in Qatif | Primary | Boys | Dammam | Dammam | 26.5773 | 50.0236 | 26.5772802,50.0235659 | KFM2020660229766 | 10006257254‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 176 | SS-ZAM-DAM1176 | مدرسة سعيد بن المسيب المتوسطة | Saeed bin Al-Musayyab Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.5652 | 49.9897 | 26.5652313,49.989747 | KFM2020660229775 | 10006296243 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 177 | SS-ZAM-DAM1177 | ابتدائيه ابي الدرداء بالقطيف | Abi Al-Darda Elementary School in Qatif | Primary | Boys | Dammam | Dammam | 26.5769 | 50.0479 | 26.5769413,50.0478568 | KFM2120660249638 | 10006258261‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 178 | SS-ZAM-DAM1178 | متوسطة فخر الدين الرازي | Fakhr Al-Din Al-Razi Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.5766 | 50.0477 | 26.5766367,50.047733 | KFM2120660249639 | 10006258242 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 179 | SS-ZAM-DAM1179 | ثانويه القديح بالقطيف | Al-Qudaih Secondary School in Qatif | Secondary | Boys | Dammam | Dammam | 26.5723 | 49.9879 | 26.5723409,49.9879137 | KFM2020660229728 | 10006296074 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 180 | SS-ZAM-DAM1180 | ابتدائية نعيم بن مسعود | Naeem bin Masoud Elementary School | Primary | Boys | Dammam | Dammam | 26.5723 | 49.9878 | 26.5722727,49.9878107 | KFM2020660229724 | 10006296092 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 181 | SS-ZAM-DAM1181 | متوسطه عطاء بن ابي رباح بالقطيف | Ata bin Abi Rabah Intermediate School in Qatif | Intermediate | Boys | Dammam | Dammam | 26.5813 | 50.0096 | 26.5813292,50.0096139 | KFM2020660231958 | 10006258592‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 182 | SS-ZAM-DAM1182 | ابتدائيه النخيل بالقطيف | Al-Nakheel Elementary School in Qatif | Primary | Boys | Dammam | Dammam | 26.5524 | 50.009 | 26.552368,50.0090081 | KFM2020660231942 | 10006256678‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 183 | SS-ZAM-DAM1183 | ابتدائيه زين العابدين بالقطيف | Zain Al-Abidin Elementary School in Qatif | Primary | Boys | Dammam | Dammam | 26.5534 | 50.0027 | 26.5534106,50.0026589 | KFM2020660231901 | 10006254996‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 184 | SS-ZAM-DAM1184 | ثانويه القبلتين بالقطيف | Al-Qiblatain Secondary School in Qatif | Secondary | Boys | Dammam | Dammam | 26.5622 | 50.0003 | 26.56215649,50.00027965 | KFM2020660231949 | 10006256696‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 185 | SS-ZAM-DAM1185 | ثانويه دار الحكمه بالقطيف | Dar Al-Hikma Secondary School in Qatif | Secondary | Boys | Dammam | Dammam | 26.5728 | 50.0098 | 26.57283237,50.00977804 | KFM2120660261359 | 10083863115‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 186 | SS-ZAM-DAM1186 | ثانويه القطيف بالقطيف | Qatif Secondary School in Qatif | Secondary | Boys | Dammam | Dammam | 26.5613 | 50.0071 | 26.56128179,50.00714916 | MMF2420601045913 | 10006249637‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 187 | SS-ZAM-DAM1187 | ابتدائيه ذات الصواري بالقطيف | Dhat Al-Sawari Elementary School in Qatif | Primary | Boys | Dammam | Dammam | 26.5654 | 50.0096 | 26.56535205,50.009602 | KFM2120660249772 | 30038901821 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 188 | SS-ZAM-DAM1188 | مدرسة ايمن بن عبيد المتوسطة | Ayman bin Ubaid Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.526 | 50.0289 | 26.52595168,50.02892672 | KFM2020660220071 | 10006260911‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 189 | SS-ZAM-DAM1189 | مدرسة عنك الثانوية | Anik Secondary School | Secondary | Boys | Dammam | Dammam | 26.5203 | 50.0285 | 26.52034386,50.02850527 | KFM2020660220150 | 10006260017‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 190 | SS-ZAM-DAM1190 | مدرسة الخويلدية الابتدائية | Al-Khawildiyah Elementary School | Primary | Boys | Dammam | Dammam | 26.5474 | 49.991 | 26.5473975,49.99096679 | KFM2020660229742 | 10006292217‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 191 | SS-ZAM-DAM1191 | مدرسة صفوان بن اميه الابتدائية بصفوى | Safwan bin Umayyah Elementary School in Safwa | Primary | Boys | Dammam | Dammam | 26.6495 | 49.9541 | 26.64951968,49.9540746 | KFM2120660288654 | 10006282801‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 192 | SS-ZAM-DAM1192 | مدرسة حراء المتوسطة بصفوى | Hiraa Intermediate School in Safwa | Intermediate | Boys | Dammam | Dammam | 26.6557 | 49.9501 | 26.65573815,49.95011102 | KFM2120660292812 | 10006283611‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 193 | SS-ZAM-DAM1193 | مدرسة العوامية الثانوية | Al-Awamiyah Secondary School | Secondary | Boys | Dammam | Dammam | 26.5851 | 49.9827 | 26.58506919,49.98271837 | KFM2020660061801 | 10006292923‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 194 | SS-ZAM-DAM1194 | مدرسة العوامية الابتدائية | Al-Awamiyah Elementary School | Primary | Boys | Dammam | Dammam | 26.5863 | 49.9783 | 26.586314,49.97833162 | KFM2120660286724 | 10006289258‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 195 | SS-ZAM-DAM1195 | مدرسة العوامية المتوسطة | Al-Awamiyah Intermediate School | Intermediate | Boys | Dammam | Dammam | 26.5863 | 49.9784 | 26.58634127,49.97836786 | KFM2120660275872 | 10006289230‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 196 | SS-ZAM-DAM1196 | مدرسة قرطبة الابتدائية بالعوامية | Qurtuba Elementary School in Awamiyah | Primary | Boys | Dammam | Dammam | 26.5862 | 49.979 | 26.5862416,49.9790149 | SMR2220661014417 | 10006289202 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 197 | SS-ZAM-DAM1197 | مدرسة صفوى الثانوية | Safwa Secondary School | Secondary | Boys | Dammam | Dammam | 26.6571 | 49.9506 | 26.65706122,49.95063595 | KFM2120660288652 | 10006293241 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 198 | SS-ZAM-DAM1198 | مدرسة تاروت الثانوية | Tarout Secondary School | Secondary | Boys | Dammam | Dammam | 26.5586 | 50.0719 | 26.5586256,50.0718854 | KFM2020660232169 | 10006284618 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 199 | SS-ZAM-DAM1199 | المدرسة المتوسطة الرابعة بالقطيف | Fourth Intermediate School in Qatif | Intermediate | Girls | Dammam | Dammam | 26.5663 | 50.0108 | 26.5662602,50.0108167 | KFM2120660249716 | 10006256060 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 200 | SS-ZAM-DAM1200 | الثانوية الثانية بالقطيف | Second Secondary School in Qatif | Secondary | Girls | Dammam | Dammam | 26.5664 | 50.0105 | 26.5664099,50.0104571 | KFM2120660249719 | 10006251018 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
[14 empty] | Total | Completed | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 200
[15 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on O4: 4/2/2025
Note on P4: 4/2/2025

## Madina Schools -1
|  | Report Date | 2026-03-03
Project |  | Schools Information | [10 empty] | Installation Start date | Mechanical |  |  |  |  | Electrcical | [7 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School No | School ID | School Name (Arabic) | School Name (English) | School Level | School Gender (Boys / Girls) | Region | City | Schools Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Madina -1 | 1 | SS-ZAM-MAD1001 | ب/ العز بن عبدالسلام بنين | Primary Al-Izz ibn Abd al-Salam Banin | Primary | Boys | Madina | Madina | 24.469814346876298, 39.58362062449357 | HLY2020627035968 | 10053560733 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Primary | Boys | Not Started
| 2 | SS-ZAM-MAD1002 | م/ عبدالقدوس الأنصاري بنين | Intermediate Abdul Quddus Al-Ansari Banin | Intermediate | Boys | Madina | Madina | 24.480399865261763, 39.58252889565849 | SXE2020627027992 | 10053741908 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Intermediate | Girls | In Progress
| 3 | SS-ZAM-MAD1003 | ث/ الثالثة والعشرون بالمدينة (مقررات) بنات | High Twenty-third in the city (curriculum) Girls | Secondary | Girls | Madina | Madina | 24.485641008756367, 39.57631054003615 | HLY202062703387 | 10053676981 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Secondary | NA | Completed
| 4 | SS-ZAM-MAD1004 | ث/ السابعة بالمدينة بنات | High Seventh Girls School in the City | Secondary | Girls | Madina | Madina | 24.479669094325818, 39.583173042570195 | SXE2020627076735 | 10053371558 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Kindergarten |  | NA
| 5 | SS-ZAM-MAD1005 | ب/ الثالثة والسبعون بنات | Primary Seventy-third girls | Primary | Girls | Madina | Madina | 24.475087344020427, 39.589074813471186 | HLY2020627016433 | 10053370837 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | Early Childhood
| 6 | SS-ZAM-MAD1006 | ث/ عبدالعزيز الربيع (مقررات) بنين | High Abdulaziz Al-Rabee (Curriculum) Boys | Secondary | Boys | Madina | Madina | 24.451718343683417, 39.62110025332814 | HLY2020627016467 | 10053864855 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed | NA
| 7 | SS-ZAM-MAD1007 | م/ علي بن أبي طالب بنين | Intermediate Ali bin Abi Talib Banin | Intermediate | Boys | Madina | Madina | 24.48655897240963, 39.595975417105706 | SXE2020627027987 | 10053741391 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 8 | SS-ZAM-MAD1008 | ث/ الامير مقرن بنين | Prince Muqrin Binin | Secondary | Boys | Madina | Madina | 24.47057611075996, 39.55365960915235 | SXE2020627082332 | 10053251166 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 9 | SS-ZAM-MAD1009 | ب/ الثانية عشر بالمدينة بنات | Primary Twelfth in the city, girls | Primary | Girls | Madina | Madina | 24.45751180237377, 39.49284319565786 | HLY2020627016361 | 10053306541 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 10 | SS-ZAM-MAD1010 | ب/ عامر بن ربيعة بنين | Primary Amer bin Rabi’ah Banin | Primary | Boys | Madina | Madina | 24.460973739451177, 39.526892756992744 | SXE2020627083836 | 10053737155 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 11 | SS-ZAM-MAD1011 | ب/ العزيزية بنين | Primary Al-Aziziyah Banin | Primary | Boys | Madina | Madina | 24.45471032054875, 39.54163438798704 | SMR2420628007854 | 10053372751 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 12 | SS-ZAM-MAD1012 | ب/ حاطب بن أبي بلتعة بنين | Primary Hatib ibn Abi Balta’ah Banin | Primary | Boys | Madina | Madina | 24.4667655089983, 39.516636022646445 | SXE2020627083828 | 10053247520 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 13 | SS-ZAM-MAD1013 | ب/ وائل بن حجر الحضرمي بنين | Primary Wael bin Hajar Al-Hadrami Banin | Primary | Boys | Madina | Madina | 24.495107568862885, 39.52466019565901 | SXE2020627083702 | 10093611748 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 14 | SS-ZAM-MAD1014 | الروضة السادسة والاربعون بنات | Kindergarten number forty-six, girls | Kindergarten | Girls | Madina | Madina | 24.484402159047537, 39.575310066823356 | HLY2020627035966 | 10102722662 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 15 | SS-ZAM-MAD1015 | ب/ الرابعة بالمدينة بنات | Primary Fourth in the city, girls | Primary | Girls | Madina | Madina | 24.4374870795406, 39.5012915599554 | SXE2020627083700 | 10088727214 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 16 | SS-ZAM-MAD1016 | ث/ التاسعة بالمدينة بنات | Ninth grade girls in the city | Secondary | Girls | Madina | Madina | 24.45375146565906, 39.5335756269543 | SXE2020627083620 | 10053676560 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 17 | SS-ZAM-MAD1017 | ث/ ميمونة بنت الحارث بنات | High Maimouna bint Al-Harith girls | Secondary | Girls | Madina | Madina | 24.461635992493026, 39.52132053297037 | HLY2020627033610 | 10097169622 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 18 | SS-ZAM-MAD1018 | م/ الخامسة والعشرون بالمدينة بنات | Intermediate Twenty-fifth in the city, girls | Intermediate | Girls | Madina | Madina | 24.466589355055284, 39.63180121702137 | SXE2020627081824 | 10053740123 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 19 | SS-ZAM-MAD1019 | متوسطة الحسن بن علي بنين | Al-Hassan Bin Ali Intermediate School for Boys | Intermediate | Boys | Madina | Madina | 24.452992641847615, 39.60021729565754 | SXE2020627078309 | 10053678822 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 20 | SS-ZAM-MAD1020 | م/ السادسة والسبعون بنات | Intermediate Seventy-sixth Girls | Intermediate | Girls | Madina | Madina | 24.420121370673446, 39.59346495702121 | ALH2020807203086 | 10087927417 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 21 | SS-ZAM-MAD1021 | ب/ التاسعة والسبعون بالمدينة بنات | Primary Seventy-ninth in the city, girls | Primary | Girls | Madina | Madina | 24.49362236472899, 39.59758916682364 | SXE2020627082920 | 10053503942 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 22 | SS-ZAM-MAD1022 | ب/ زيد الخير بنين | Primary Zaid Al-Khair Banin | Primary | Boys | Madina | Madina | 24.45747021370707, 39.65815938233104 | HLY2020627034412 | 10053790009 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 23 | SS-ZAM-MAD1023 | م/ الثالثة عشر بالمدينة بنات | Intermediate Thirteenth in the city, girls | Intermediate | Girls | Madina | Madina | 24.481992151083617, 39.62413889549428 | SXE2020627068881 | 10053436877 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 24 | SS-ZAM-MAD1024 | ث/ النعمان بن مالك بنين | High Al-Nu'man bin Malik Banin | Secondary | Boys | Madina | Madina | 24.51575553356764, 39.576170824494874 | HLY2020627013466 | 10053497381 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 25 | SS-ZAM-MAD1025 | ب/ الفهدية بنين | Primary Al-Fahdiyah Banin | Primary | Boys | Madina | Madina | 24.483817216347965, 39.67131298031749 | HLY2020627016362 | 10053306818 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 26 | SS-ZAM-MAD1026 | م/ الثلاثون بالمدينة بنات | Intermediate Thirty in the city, girls | Intermediate | Girls | Madina | Madina | 24.42544971324434, 39.51254386682151 | HLY2020627016382 | 10053563978 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 27 | SS-ZAM-MAD1027 | ب/ الشيخ محمد بن صالح بن عثيمين بنين | Primary Sheikh Muhammad bin Saleh bin Uthaymeen, sons | Primary | Boys | Madina | Madina | 24.550006757049694, 39.567479953331485 | SMR2220621010498 | 10105379095 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 28 | SS-ZAM-MAD1028 | ب/ أسعد بن زرارة بنين | Primary As'ad ibn Zurarah Banu | Primary | Boys | Madina | Madina | 24.434505731057527, 39.61309931438188 | SXE2020627082957 | 10053787166 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 29 | SS-ZAM-MAD1029 | ب/ دار التقوى بنين | Primary Dar Al-Taqwa for Boys | Primary | Boys | Madina | Madina | 24.45219037523838, 39.613366212845854 | SXE2020627067642 | 10053787694 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 30 | SS-ZAM-MAD1030 | ث/ الثانية عشرة بالمدينة (مقررات) بنات | Twelfth grade in the city (curriculum) for girls | Secondary | Girls | Madina | Madina | 24.50919938515398, 39.56628646307346 | HLY2020627033386 | 10053682290 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 31 | SS-ZAM-MAD1031 | ب/ الثامنة والعشرون بعد المائة بنات | Primary One hundred and twenty-eighth girls | Primary | Girls | Madina | Madina | 24.464520858721826, 39.56311976682266 | SXE2020627082256 | 10100983866 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 32 | SS-ZAM-MAD1032 | ث/ الإمام السمهودي (مقررات) بنين | Imam Al-Samhudi (Curriculum) Boys | Secondary | Boys | Madina | Madina | 24.46011833080322, 39.60583369565784 | SXE2020627082919 | 10053679811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 33 | SS-ZAM-MAD1033 | ث/ الأولى بالمدينة (مقررات) بنات | First secondary school in the city (curriculum) for girls | Secondary | Girls | Madina | Madina | 24.460146771352406, 39.62804603604637 | HLY2020627033801 | 10053808088 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 34 | SS-ZAM-MAD1034 | ب/ الثلاثون بعد المائة بالمدينة بنات | Primary Thirty after one hundred in the city, girls | Primary | Girls | Madina | Madina | 24.45319545293729, 39.685906741429804 | SXE2020627083830 | 10053367466 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 35 | SS-ZAM-MAD1035 | ث/ الأقصى بنين | Al-Aqsa Boys | Secondary | Boys | Madina | Madina | 24.448951946090638, 39.639251055175116 | HLY2020627033897 | 10053844119 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 36 | SS-ZAM-MAD1036 | ب/ الأحنف بن قيس التميمي بنين | Primary Al-Ahnaf ibn Qays al-Tamimi Banin | Primary | Boys | Madina | Madina | 24.476188677737532, 39.64491786682309 | HLY2020627013621 | 10053308231 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 37 | SS-ZAM-MAD1037 | ث/ النهروان (مقررات) بنين | Al-Nahrawan (Curriculum) Boys | Secondary | Boys | Madina | Madina | 24.483561832121183, 39.67760176682322 | HLY2020627013645 | 10053249758 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 38 | SS-ZAM-MAD1038 | ب/ الإمام احمد بن حنبل بنين | Primary Imam Ahmad ibn Hanbal Banin | Primary | Boys | Madina | Madina | 24.463380223042375, 39.635069995658085 | HLY2020627013569 | 10053788486 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 39 | SS-ZAM-MAD1039 | ب/ المحمدية بنين | Primary Mohammedia Benin | Primary | Boys | Madina | Madina | 24.455731969817045, 39.61488549565756 | SXE2020627067606 | 10053496973 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 40 | SS-ZAM-MAD1040 | ب/ المقداد بن عمرو بنين | Primary Al-Miqdad ibn Amr ibn | Primary | Boys | Madina | Madina | 24.62811382552191, 39.587752452941174 | HLY2020627014263 | 10053847818 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 41 | SS-ZAM-MAD1041 | ب/ زيد بن حارثة بنين | Primary Zayd ibn Haritha Banin | Primary | Boys | Madina | Madina | 24.459228248450664, 39.64226601895186 | HLY2020627033268 | 10053852809 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 42 | SS-ZAM-MAD1042 | م/ النعمان بن مقرن بنين | Intermediate Al-Nu'man bin Muqrin Banin | Intermediate | Boys | Madina | Madina | 24.480848300239053, 39.51730762449392 | HLY2020627033607 | 10100670048 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 43 | SS-ZAM-MAD1043 | ب/ عمرو بن الجموح الأنصاري بنين | Primary Amr ibn al-Jamuh al-Ansari Banin | Primary | Boys | Madina | Madina | 24.49328199181534, 39.60833358031779 | HLY2020627035361 | 10053310866 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 44 | SS-ZAM-MAD1044 | ب/ الثانية والعشرون بعد المائة بنات | Primary One hundred and twenty-second girls | Primary | Girls | Madina | Madina | 24.46935589364079, 39.5996774954499 | HLY2020627013626 | 10053619671 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 45 | SS-ZAM-MAD1045 | ث/ الثامنة عشر بنات | High Eighteenth Girls | Secondary | Girls | Madina | Madina | 24.46409990232988, 39.58732227672561 | HLY2020627016360 | 10053794831 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 46 | SS-ZAM-MAD1046 | ث/ الحادية عشرة بالمدينة (مقررات) بنات | High Eleventh in the city (curriculum) Girls | Secondary | Girls | Madina | Madina | 24.481387217308963, 39.624383520352424 | HLY2020627033815 | 10053441554 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 47 | SS-ZAM-MAD1047 | ث/ أبي سفيان بن حرب بنين | High Abu Sufyan bin Harb Banin | Secondary | Boys | Madina | Madina | 24.479012016149273, 39.62992616497609 | SXE2120627100423 | 10053682253 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 48 | SS-ZAM-MAD1048 | ب/ ابن منظور بنين | Primary Ibn Manzur Banin | Primary | Boys | Madina | Madina | 24.551487545578052, 39.750950172270336 | HLY2020627033183 | 10052294221 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 49 | SS-ZAM-MAD1049 | ث/ الأندلس بنين | High Al-Andalus Boys | Secondary | Boys | Madina | Madina | 24.54078200170585, 39.66216297070265 | HLY2020627033274 | 10053295966 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 50 | SS-ZAM-MAD1050 | ب/ الحسين بن علي بنين | Primary Al-Hussein bin Ali binin | Primary | Boys | Madina | Madina | 24.445744082663172, 39.63303446682197 | SXE2020627067289 | 10053811520 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 51 | SS-ZAM-MAD1051 | ث/ عمر بن علي بن أبي طالب بنين | High Omar bin Ali bin Abi Talib bin | Secondary | Boys | Madina | Madina | 24.423596022121565, 39.59101300915081 | HLY2020627033831 | 10083128744 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 52 | SS-ZAM-MAD1052 | م/ هشام بن عامر الأنصاري بنين | Intermediate Hisham bin Amer Al-Ansari Banin | Intermediate | Boys | Madina | Madina | 24.43439546491611, 39.59767096866867 | SXE2020627067331 | 10095842735 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 53 | SS-ZAM-MAD1053 | ب/ الثالثة لتحفيظ القرآن الكريم بالمدينة بنات | Primary The third for memorizing the Holy Quran in Madinah for girls | Primary | Girls | Madina | Madina | 24.45649410235953, 39.667215439834315 | HLY2020627034497 | 10053789053 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 54 | SS-ZAM-MAD1054 | ب/ سعيد بن الحارث القرشي بنين | Primary Saeed bin Al-Harith Al-Qurashi Banin | Primary | Boys | Madina | Madina | 24.48694197199314, 39.572613364976434 | HLY2020627033637 | 10053559661 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 55 | SS-ZAM-MAD1055 | م/ نعيم بن عبدالله النحام بنين | Intermediate Naeem bin Abdullah Al-Nahham Banin | Intermediate | Boys | Madina | Madina | 24.562601373677023, 39.555479884296574 | HLY2020627035392 | 10101670196 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 56 | SS-ZAM-MAD1056 | ث/ هشام بن العاص بنين | High Hisham bin Al-Aas Boys | Secondary | Boys | Madina | Madina | 24.56231034038264, 39.68199343885977 | HLY2020627013353 | 10053298851 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 57 | SS-ZAM-MAD1057 | ث/ الثالثة والأربعون بالمدينة بنات | High Forty-third in the city, girls | Secondary | Girls | Madina | Madina | 24.44627632235301, 39.66310339565739 | HLY2020627013628 | 10088061521 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 58 | SS-ZAM-MAD1058 | م/ عباد بن بشر الأنصاري بنين | Intermediate Abbad bin Bishr Al-Ansari Banin | Intermediate | Boys | Madina | Madina | 24.483172960956164, 39.62125628827028 | HLY2020627013527 | 10053504921 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 59 | SS-ZAM-MAD1059 | م/ السادسة والأربعون بالمدينة بنات | Intermediate Forty-sixth in the city, girls | Intermediate | Girls | Madina | Madina | 24.49010602216838, 39.67390178248499 | HLY2020627013538 | 10053821615 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 60 | SS-ZAM-MAD1060 | ب/ الإمام يعقوب بن اسحاق الحضرمي لتحفيظ القرآن الكريم بنين | Primary Imam Yaqub bin Ishaq Al-Hadrami for Memorizing the Holy Quran for Boys | Primary | Boys | Madina | Madina | 24.44011808789781, 39.66060366866894 | HLY2020627016464 | 10053676864 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 61 | SS-ZAM-MAD1061 | ب/ السابعة عشر بالمدينة بنات | Primary Seventeenth in the city, girls | Primary | Girls | Madina | Madina | 24.4839879981667, 39.57565395594196 | HLY2020627033389 | 10053679196 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 62 | SS-ZAM-MAD1062 | م/ الإمام الشوكاني لتحفيظ القرآن الكريم بنين | Imam Al-Shawkani School for Quran Memorization (Boys) | Intermediate | Boys | Madina | Madina | 24.434528193097975, 39.65320839565687 | HLY2020627013582 | 10086271109 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 63 | SS-ZAM-MAD1063 | ب/ شوران بنين | Primary Shuran Banin | Primary | Boys | Madina | Madina | 24.419003330817098, 39.651927683303114 | HLY2020627033835 | 10053814497 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 64 | SS-ZAM-MAD1064 | ث/ الثامنة والأربعون بالمدينة (مقررات) بنات | High Forty-eighth in the city (curriculum) Girls | Secondary | Girls | Madina | Madina | 24.47254688143168, 39.64230073054563 | SXE2020627083839 | 10053367715 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 65 | SS-ZAM-MAD1065 | ث/ السابعة والأربعون بالمدينة بنات | High Forty-seventh in the city, girls | Secondary | Girls | Madina | Madina | 24.500299708722096, 39.651096411000296 | SXE2020627055303 | 10053443129 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 66 | SS-ZAM-MAD1066 | ب/ وادي بطحان بنين | Primary Wadi Bat'han Banin | Primary | Boys | Madina | Madina | 24.424230833965204, 39.63741390915078 | SXE2020627078362 | 10053738368 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 67 | SS-ZAM-MAD1067 | م/ الإمام الذهبي لتحفيظ القرآن الكريم بنين | Imam Al-Dhahabi School for Quran Memorization (Boys) | Intermediate | Boys | Madina | Madina | 24.40551191540971, 39.50163268915441 | SXE2020627082357 | 10099957858 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 68 | SS-ZAM-MAD1068 | م/ شجاع بن وهب بن ربيعة بنين | Intermediate Shuja' bin Wahb bin Rabi'ah bin Banin | Intermediate | Boys | Madina | Madina | 24.488614752505757, 39.59999039565876 | SXE2020627078305 | 10053371905 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 69 | SS-ZAM-MAD1069 | ب/ جابر بن سمرة العامري بنين | Primary Jaber bin Samra Al-Amri, sons | Primary | Boys | Madina | Madina | 24.400736247688855, 39.501957666820644 | SXE2020627082356 | 10099957811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 70 | SS-ZAM-MAD1070 | ب/ التاسعة والأربعون بالمدينة بنات | Primary Forty-ninth in the city, girls | Primary | Girls | Madina | Madina | 24.441023701704093, 39.63384500468524 | SXE2020627078363 | 10053679310 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 71 | SS-ZAM-MAD1071 | م/ ابن هشام بنين | Intermediate Ibn Hisham Banin | Intermediate | Boys | Madina | Madina | 24.45569087222465, 39.65796983798702 | HLY2020627013581 | 10053818923 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 72 | SS-ZAM-MAD1072 | هـ/ التاسع والأربعون للبنات | E/ Forty-ninth for girls | Secondary | Girls | Madina | Madina |  | HLY2020627013595 | 10053254444 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 73 | SS-ZAM-MAD1073 | ب/ الستون بالمدينة بنات | Primary Sixty girls in the city | Primary | Girls | Madina | Madina | 24.45489433140154, 39.58606680782799 | HLY2020627033840 | 10053788691 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 74 | SS-ZAM-MAD1074 | ب/ الرابعة والخمسون بالمدينة بنات | Primary Fifty-fourth in the city, girls | Primary | Girls | Madina | Madina | 24.461341248076373, 39.62904410947499 | HLY2020627033857 | 10053808300 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 75 | SS-ZAM-MAD1075 | ث/ أم القرى بنين | High Umm Al-Qura Boys | Secondary | Boys | Madina | Madina | 24.40078617616885, 39.50195513429119 | SXE2020627082360 | 10099967068 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 76 | SS-ZAM-MAD1076 | الروضة الحادية عشر بنات | Eleventh Kindergarten for Girls | Kindergarten | Girls | Madina | Madina | 24.464132841062362, 39.62817374369547 | HYL2020627033783 | 10053836181 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 77 | SS-ZAM-MAD1077 | ث/ الأولى بالعاقول بنات | High First in Al-Aqoul, girls | Secondary | Girls | Madina | Madina | 24.551001432132956, 39.751199237990356 | HLY2020627033181 | 10053864953 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 78 | SS-ZAM-MAD1078 | ب/ سكينة بنت ابي وقاص بنات | Primary Sakina bint Abi Waqqas, daughters | Primary | Girls | Madina | Madina | 24.56583644308988, 39.54854659982482 | HLY2020627035365 | 10101108817 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 79 | SS-ZAM-MAD1079 | ب/ عمار بن ياسر بنين | Primary Ammar bin Yasir Banin | Primary | Boys | Madina | Madina | 24.55282388760717, 39.68011209566086 | SXE2020627082292 | 10053440593 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 80 | SS-ZAM-MAD1080 | ث/ القدس بنين | Jerusalem Boys | Secondary | Boys | Madina | Madina | 21.44159261067841, 39.79377125323434 | SXE2020627082354 | 10053440341 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 81 | SS-ZAM-MAD1081 | ث/ الجرف بنين | Al-Jarf Boys | Secondary | Boys | Madina | Madina | 24.56199865441982, 39.556335382167134 | HLY2020627035391 | 10101672038 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 82 | SS-ZAM-MAD1082 | م/ الرابعة والعشرون بالمدينة بنات | Intermediate Twenty-fourth in the city, girls | Intermediate | Girls | Madina | Madina | 24.443931937010213, 39.61175934685198 | SXE2020627081341 | 10053823066 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 83 | SS-ZAM-MAD1083 | م/ الحادية والستون بالمدينة بنات | Intermediate Sixty-one in the city, girls | Intermediate | Girls | Madina | Madina | 24.464229180935007, 39.53911322449321 | SXE2020627083826 | 10090403616 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 84 | SS-ZAM-MAD1084 | ب/ السقاف بنين | Primary Al-Saqqaf Banin | Primary | Boys | Madina | Madina | 24.48655170017852, 39.621995782164674 | SXE2020627054645 | 10053785887 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 85 | SS-ZAM-MAD1085 | ب/ الثامنة والثلاثون بالمدينة بنات | Primary Thirty-eighth in the city, girls | Primary | Girls | Madina | Madina | 24.454617310113363, 39.5328599986443 | SXE2020627076734 | 10053371342 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 86 | SS-ZAM-MAD1086 | ب/ عقيل بن أبي طالب بنين | Primary Aqeel bin Abi Talib, sons | Primary | Boys | Madina | Madina | 24.56952775994909, 39.642738771783925 | HLY2020627033852 | 10085634292 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 87 | SS-ZAM-MAD1087 | م/ الامام نافع الليثي بنين | Imam Nafi' al-Laythi Boys' School | Intermediate | Boys | Madina | Madina | 24.47355738974771, 39.638185666823034 | SXE2020627079899 | 10053681775 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Not Started | Completed | Completed | Completed | 2 | 0 | 13 | In Progress
| 88 | SS-ZAM-MAD1088 | م/ عبدالله بن أم مكتوم بنين | Abdullah bin Umm Maktoum Banin | Intermediate | Boys | Madina | Madina | 24.460738295775897, 39.53430206682262 | HLY2020627016363 | 10053371932 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 89 | SS-ZAM-MAD1089 | ب/ العاشرة بالمدينة بنات | Primary Tenth in the city, girls | Primary | Girls | Madina | Madina | 24.522657882844793, 39.572899112848134 | SXE2020627082516 | 10053441231 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 90 | SS-ZAM-MAD1090 | ب/ الشيخ عبدالعزيز بن صالح بنين | Primary Sheikh Abdulaziz bin Saleh Banin | Primary | Boys | Madina | Madina | 24.45220504246404, 39.6203708533282 | HLY2020627016466 | 10053863974 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 91 | SS-ZAM-MAD1091 | م/ حواء بنات | Intermediate Hawa Banat | Intermediate | Girls | Madina | Madina | 24.443475822547658, 39.480508853328004 | HLY2020627016766 | 10100670253 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 92 | SS-ZAM-MAD1092 | م/ الخمسون بالمدينة بنات | Intermediate Al-Khamsoun, girls of the city | Intermediate | Girls | Madina | Madina | 24.498674862766947, 39.58197226682386 | HLY2020627033655 | 10053251845 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 93 | SS-ZAM-MAD1093 | ب/ هالة بنت عوف بنات | Primary Hala bint Awf Banat | Primary | Girls | Madina | Madina | 24.48195891981019, 39.52095579935271 | HLY2020627033606 | 10102172026 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 94 | SS-ZAM-MAD1094 | الروضة السابعة بنات | Seventh Kindergarten for Girls | Kindergarten | Girls | Madina | Madina | 24.694658881250398, 46.73433238799513 | SXE2020627083622 | 10053676265 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 95 | SS-ZAM-MAD1095 | الروضة الخامسة بنات | Fifth Kindergarten for Girls | Kindergarten | Girls | Madina | Madina | 21.53866240330601, 39.213756363989276 | HLY2020627035398 | 10052041941 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 96 | SS-ZAM-MAD1096 | ث/ الأمير عبدالمحسن بن عبدالعزيز (مقررات) بنين | Prince Abdulmohsen bin Abdulaziz Secondary School (Curriculum) for Boys | Secondary | Boys | Madina | Madina | 24.45795010179582, 39.659865666822476 | HLY2020627016840 | 10053787068 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 97 | SS-ZAM-MAD1097 | م/ التاسعة عشرة بالمدينة بنات | Intermediate Nineteenth in the city, girls | Intermediate | Girls | Madina | Madina | 24.46413369200677, 39.64220031977597 | HLY2020627033287 | 10053791294 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 98 | SS-ZAM-MAD1098 | الروضة السادسة بنات | Sixth Kindergarten for Girls | Kindergarten | Girls | Madina | Madina | 24.458503633291734, 39.66366123198121 | HLY2020627034451 | 10053790770 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 99 | SS-ZAM-MAD1099 | م/ الأربعون بالمدينة بنات | Intermediate Al-Arba'un, girls of the city | Intermediate | Girls | Madina | Madina | 24.477836874989137, 39.5568407533158 | SXE2020627082326 | 10053815411 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 100 | SS-ZAM-MAD1100 | ب/ الرابعة بعد المائة بالمدينة بنات | Primary The 104th in the city, girls | Primary | Girls | Madina | Madina | 24.488660715266278, 39.59314979381168 | HLY2020627016434 | 10095836916 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 101 | SS-ZAM-MAD1101 | م/ عبدالله بن مظعون بنين | Intermediate Abdullah bin Mazoun Banin | Intermediate | Boys | Madina | Madina | 24.458290006709557, 39.64184452079891 | HLY2020627033286 | 10053793154 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 102 | SS-ZAM-MAD1102 | ث/ السادسة والأربعون بالمدينة بنات | High Forty-sixth in the city, girls | Secondary | Girls | Madina | Madina | 24.46321581082852, 39.63958489966107 | HLY2020627033288 | 10053786679 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 103 | SS-ZAM-MAD1103 | ث/ التاسعة عشرة بالمدينة (مقررات) بنات | High Nineteenth in the city (curriculum) Girls | Secondary | Girls | Madina | Madina | 24.457364195797403, 39.667177100964366 | HLY2020627034414 | 10053787531 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 104 | SS-ZAM-MAD1104 | ث/ الأمير عبدالمجيد بن عبدالعزيز(مقررات) بنين | Prince Abdulmajid bin Abdulaziz Secondary School (Curriculum) for Boys | Secondary | Boys | Madina | Madina | 24.40584823923769, 39.523524646253264 | SXE2020627067710 | 10105602265 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 105 | SS-ZAM-MAD1105 | ب/ الثامنة والسبعون بالمدينة بنات | Primary Seventy-eighth in the city, girls | Primary | Girls | Madina | Madina | 24.45530224006962, 39.52692301099889 | SXE2020627083837 | 10053739427 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 106 | SS-ZAM-MAD1106 | ب/ الثانية بالمدينة بنات | Primary Second in the city, girls | Primary | Girls | Madina | Madina | 24.516196094398367, 39.54705929565974 | HLY2020627033427 | 10053821099 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 107 | SS-ZAM-MAD1107 | ث/ ابن حزم بنين | Ibn Hazm Banin | Secondary | Boys | Madina | Madina | 24.442705898763839.4735080499999 | HLY2020627016760 | 10101245754 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 108 | SS-ZAM-MAD1108 | الروضة السابعة والعشرون بنات | The twenty-seventh kindergarten for girls | Kindergarten | Girls | Madina | Madina | 24.47250513741963, 39.50568123798778 | SXE2020627083759 | 10087547571 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 109 | SS-ZAM-MAD1109 | ب/ سلمى بنت قيس بنات | Primary Salma bint Qais Banat | Primary | Girls | Madina | Madina | 24.496382851079776, 39.53689380915307 | HLY2020627033634 | 10099363422 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 110 | SS-ZAM-MAD1110 | ب/ بني النجار بنين | Primary Bani Najjar Banin | Primary | Boys | Madina | Madina | 24.44669585721132, 39.61036352449278 | SXE2020627078312 | 10102491064 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 111 | SS-ZAM-MAD1111 | ب/ الحادية والعشرون بعد المائة بالمدينة بنات | Primary One hundred and twenty-first in the city, girls | Primary | Girls | Madina | Madina | 24.4518034123867, 39.4865145965301 | HLY2020627033666 | 10100476004 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 112 | SS-ZAM-MAD1112 | م/ الثامنة والثلاثون بالمدينة بنات | Intermediate Thirty-eighth in the city, girls | Intermediate | Girls | Madina | Madina | 24.406833960964807, 39.50032074199047 | SXE2020627082358 | 10103190664 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 113 | SS-ZAM-MAD1113 | ث/ الثانية والخمسون بنات | High Fifty-second Girls | Secondary | Girls | Madina | Madina | 24.422935003879104, 39.50904608216257 | SXE2020627082368 | 10102662359 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 114 | SS-ZAM-MAD1114 | ب/ الثالثة والستون بالمدينة بنات | Primary Sixty-third in the city, girls | Primary | Girls | Madina | Madina | 24.423225853335605, 39.50966003983313 | SXE2120627113099 | 10053502453 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 115 | SS-ZAM-MAD1115 | ث/ العشرون بالمدينة بنات | High Twenty girls in the city | Secondary | Girls | Madina | Madina | 24.42467083359024, 39.51181411099791 | HLY2020627033789 | 10053558225 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 116 | SS-ZAM-MAD1116 | م/ الثامنة والعشرون بالمدينة بنات | Intermediate Twenty-eighth in the city, girls | Intermediate | Girls | Madina | Madina | 24.522309754205452, 39.54650084369544 | HLY2020627033429 | 10053821311 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 117 | SS-ZAM-MAD1117 | ب/ الرابعة والعشرون بالمدينة بنات | Primary Twenty-fourth in the city, girls | Primary | Girls | Madina | Madina | 24.44383539.612317 | SXE2020627078383 | 10053794090 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 118 | SS-ZAM-MAD1118 | ب/ السابعة والخمسون بالمدينة بنات | Primary Fifty-seventh in the city, girls | Primary | Girls | Madina | Madina | 24.438622775698639.6074616909027 | MMF2020807358095 | 10071285851 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 119 | SS-ZAM-MAD1119 | ب/ الخامسة عشر بعد المائة بالمدينة بنات | Primary One hundred and fifteenth in the city, girls | Primary | Girls | Madina | Madina | 24.45756498704104, 39.65276555548459 | HLY2020627013603 | 10053561436 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 120 | SS-ZAM-MAD1120 | ب/ التاسعة لتحفيظ القرآن الكريم بـالمدينة بنات | Primary Ninth Quran Memorization Center in Madinah (Girls) | Primary | Girls | Madina | Madina | 24.45090734450117, 39.65337878031639 | HLY2020627013604 | 10053619438 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 121 | SS-ZAM-MAD1121 | ب/ التاسعة بعد المائة بالمدينة بنات | Primary One hundred and nine in the city, girls | Primary | Girls | Madina | Madina | 24.356568551414917, 39.56598473321245 | SXE2020627082902 | 10053373006 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 122 | SS-ZAM-MAD1122 | ب/ عبدالله بن جحش بنين | Primary Abdullah bin Jahsh Banin | Primary | Boys | Madina | Madina | 24.518978121228297, 39.57138396682461 | HLY2020627013409 | 10053355591 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 123 | SS-ZAM-MAD1123 | ب/ ذي الشهادتين بنين | Primary Two-testimony boys | Primary | Boys | Madina | Madina | 24.50546869662269, 39.568134399661076 | SXE2020627082517 | 10053313198 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 124 | SS-ZAM-MAD1124 | ب/ السادسة والأربعون بالمدينة بنات | Primary Forty-sixth in the city, girls | Primary | Girls | Madina | Madina | 24.462758552495703, 39.64218018401097 | HLY2020627033289 | 10053743312 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 125 | SS-ZAM-MAD1125 | م/ الحادية والخمسون بالمدينة بنات | Intermediate Fifty-first in the city, girls | Intermediate | Girls | Madina | Madina | 24.45432477642326, 39.66666581895172 | HLY2020627016430 | 10053789296 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 126 | SS-ZAM-MAD1126 | م/ الأرقم بن أبي الأرقم بنين | Intermediate Al-Arqam bin Abi Al-Arqam bin | Intermediate | Boys | Madina | Madina | 24.46590326440278, 39.66160784019402 | HLY2020627033298 | 10053821141 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 127 | SS-ZAM-MAD1127 | ب/ السعودية بنين | Primary Saudi Arabia, Benin | Primary | Boys | Madina | Madina | 24.4508970305648, 39.64842633249118 | HLY2020627013534 | 10053442159 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 128 | SS-ZAM-MAD1128 | م/ الثامنة عشر بالمدينة بنات | Intermediate Eighteenth in the city, girls | Intermediate | Girls | Madina | Madina | 24.45778339.541699 | SXE2020627083832 | 10053845538 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 129 | SS-ZAM-MAD1129 | ب/ الثانية والستون بالمدينة بنات | Primary Sixty-second in the city, girls | Primary | Girls | Madina | Madina | 24.475747662895312, 39.55508206660622 | SXE2020627082325 | 10053246139 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 130 | SS-ZAM-MAD1130 | ث/ المأمون بنين | High Al-Ma'moun Banin | Secondary | Boys | Madina | Madina | 24.456157808033428, 39.51955205332823 | SXE2020627083840 | 10053821419 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 131 | SS-ZAM-MAD1131 | ب/ صفية بن عمر بن الخطاب | Primary Safiyya bint Umar ibn al-Khattab | Primary | Girls | Madina | Madina | 24.435186117262692, 39.48131706796192 | HLY2020627016800 | 10101667619 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 132 | SS-ZAM-MAD1132 | م/ الأولى لتحفيظ القرآن الكريم بـالمدينة بنات | First Quran Memorization School for Girls in Madinah | Intermediate | Girls | Madina | Madina | 24.459109078772627, 39.6643853808973 | HLY2020627034498 | 10053792415 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 133 | SS-ZAM-MAD1133 | ب/ عبدالله بن عمرو بن العاص بنين | Primary Abdullah bin Amr bin Al-Aas bin | Primary | Boys | Madina | Madina | 24.498072439939.5840695024 | HLY2020627034478 | 10053311999 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 134 | SS-ZAM-MAD1134 | ث/ الرابعة والعشرون بالمدينة (مقررات) بنات | High Twenty-fourth in the city (curriculum) Girls | Secondary | Girls | Madina | Madina | 24.504228243726086, 39.58008814336018 | HLY2020627033657 | 10053851884 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 135 | SS-ZAM-MAD1135 | ث/ الأمير محمد بن عبدالعزيز | High Prince Mohammed bin Abdulaziz | Secondary | Boys | Madina | Madina | 24.450242962130105, 39.6329025109051 | SXE2020627067288 | 10053812204 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 136 | SS-ZAM-MAD1136 | م/ الرابعة والثلاثون بالمدينة بنات | Intermediate Thirty-fourth in the city, girls | Intermediate | Girls | Madina | Madina | 24.54491029291204, 39.565410934613375 | HLY2020627035394 | 10101098855 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 137 | SS-ZAM-MAD1137 | ث/ السادسة والعشرون بالمدينة بنات | High Twenty-sixth in the city, girls | Secondary | Girls | Madina | Madina | 24.543746726234247, 39.56615870915472 | SXE2020627082344 | 10053725593 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 138 | SS-ZAM-MAD1138 | م/ الشيخ محمد بن ابراهيم بنين | Sheikh Mohammed bin Ibrahim Banin | Intermediate | Boys | Madina | Madina | 24.476681030646052, 39.65609485702305 | HLY2020627013451 | 10099637705 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 139 | SS-ZAM-MAD1139 | الابتدائية السابعة والسبعون بنات | Seventy-seventh Girls' Elementary School | Primary | Girls | Madina | Madina | 24.492570309217648, 39.617868049118236 | HLY2020627016500 | 10053847531 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 140 | SS-ZAM-MAD1140 | ب/ معاذ بن الحارث بنين | Primary Mu'adh ibn al-Harith ibn | Primary | Boys | Madina | Madina | 24.449225582196366, 39.638314788269106 | HLY2020627033896 | 10053813542 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 141 | SS-ZAM-MAD1141 | ث/ الملك عبدالله بن عبدالعزيز بنين | King Abdullah bin Abdulaziz, sons | Secondary | Boys | Madina | Madina | 24.446107018468126, 39.651187395657445 | HLY2020627013553 | 10053618904 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 142 | SS-ZAM-MAD1142 | ب/ مجاهد بن جبر بنين | Primary Mujahid bin Jabr binin | Primary | Boys | Madina | Madina | 24.418432461354993, 39.59440998216236 | SXE2020627082997 | 10053498421 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 143 | SS-ZAM-MAD1143 | ب/ الثامنة والتسعون بالمدينة بنات | Primary Ninety-eighth in the city, girls | Primary | Girls | Madina | Madina | 24.551407313714293, 39.67570781100197 | SXE2020627082338 | 10053725360 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 144 | SS-ZAM-MAD1144 | م/ الرابعة والسبعون بالمدينة بنات | Intermediate Seventy-fourth in the city, girls | Intermediate | Girls | Madina | Madina | 24.44507765166766, 39.670540824492704 | HLY2020627033805 | 10086125521 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 145 | SS-ZAM-MAD1145 | ب/ عبادة بن قيس الأنصاري بنين | Primary Ubadah ibn Qays al-Ansari Banin | Primary | Boys | Madina | Madina | 24.538477734843426, 39.68679979566045 | HLY2020627013387 | 10053860032 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 146 | SS-ZAM-MAD1146 | ث/ مأرز الإيمان (مقررات) بنين | High Marz Al-Iman (Curriculum) Boys | Secondary | Boys | Madina | Madina | 24.496028535825243, 39.58634582449434 | HLY2020627033652 | 10053608560 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 147 | SS-ZAM-MAD1147 | م/ الشيخ عبدالعزيز بن باز بنين | Intermediate Sheikh Abdulaziz bin Baz Banin | Intermediate | Boys | Madina | Madina | 24.492830979839.5685267448 | HLY2020627033651 | 10053608318 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 148 | SS-ZAM-MAD1148 | ب/ الثالثة والخمسون بالمدينة بنات | Primary Fifty-third in the city, girls | Primary | Girls | Madina | Madina | 24.557256959519826, 39.67560293732401 | SXE22020627082289 | 10053441518 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 149 | SS-ZAM-MAD1149 | م/ عمرو بن عثمان القرشي بنين | Intermediate Amr bin Othman Al-Qurashi Banin | Intermediate | Boys | Madina | Madina | 24.471961913344057, 39.63766828031703 | HLY2020627033886 | 10053624591 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 150 | SS-ZAM-MAD1150 | الروضة الخامسة عشر بنات | Fifteenth Kindergarten for Girls | Kindergarten | Girls | Madina | Madina | 24.55502632006703, 39.739117411548214 | HLY2020627033236 | 10053295831 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 151 | SS-ZAM-MAD1151 | ب/ الثالثة والثلاثون بالمدينة بنات | Primary Thirty-third in the city, girls | Primary | Girls | Madina | Madina | 24.460910435839.6217942267 | SXE2020627055297 | 10053442669 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 152 | SS-ZAM-MAD1152 | ب/ صفية بنت عبدالمطلب بنات | Primary Safiyya bint Abd al-Muttalib, daughters | Primary | Girls | Madina | Madina | 24.502832786314418, 39.611200743695456 | HLY2020627033876 | 10053562710 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 153 | SS-ZAM-MAD1153 | ب/ مكة المكرمة | Primary Mecca | Primary | Boys | Madina | Madina | 24.468074612140477, 39.60826069707827 | SXE2020627082938 | 10053679338 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 154 | SS-ZAM-MAD1154 | م/ السابعة عشر بالمدينة بنات | Intermediate Seventeenth in the city, girls | Intermediate | Girls | Madina | Madina | 24.495866831419224, 39.56947888549511 | HLY2020627033744 | 10053496731 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 155 | SS-ZAM-MAD1155 | ث/ دار الأبرار (مقررات) بنين | High Dar Al-Abrar (Curriculum) Boys | Secondary | Boys | Madina | Madina | 24.479405680185874, 39.58183903798797 | HLY2020627033866 | 10053368712 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 156 | SS-ZAM-MAD1156 | ب/ أبي أيوب الأنصاري بنين | Primary Abu Ayyub al-Ansari Banin | Primary | Boys | Madina | Madina | 24.523142625839.6704185009 | HLY2020627034477 | 10053312243 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 157 | SS-ZAM-MAD1157 | ب/ أبي بن كعب لتحفيظ القران الكريم بنين | Primary Abi Bin Kaab for Memorizing the Holy Quran for Boys | Primary | Boys | Madina | Madina | 24.488209424376063, 39.60236463700668 | HLY2020627033834 | 10053372171 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 158 | SS-ZAM-MAD1158 | م/ الثانية والعشرون بنات | Intermediate Twenty-second Girls | Intermediate | Girls | Madina | Madina | 24.451281864471298, 39.6086686972886 | SXE2020627000963 | 10053684221 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 159 | SS-ZAM-MAD1159 | ب/ أبي الطيب المتنبي بنين | Primary Abu al-Tayyib al-Mutanabbi Banin | Primary | Boys | Madina | Madina | 24.409150938419664, 39.633577487235975 | HLY2020627033776 | 10088065235 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 160 | SS-ZAM-MAD1160 | الروضة الحادية والعشرون بالمدينة | The twenty-first kindergarten in the city | Kindergarten | Girls | Madina | Madina | 24.508670456533366, 39.679567695659415 | SMR2320621014254 | 10105656373 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 161 | SS-ZAM-MAD1161 | ب/ المنذر بن قيس بنين | Primary Al-Mundhir ibn Qays ibn Banin | Primary | Boys | Madina | Madina | 24.386848995424103, 39.607876895655416 | HLY2020627033788 | 10101245727 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 162 | SS-ZAM-MAD1162 | ثانوية السادسة | Sixth Secondary | Secondary | Girls | Madina | Madina | 24.459489745232975, 39.60846170908593 | SXE2020627000961 | 10053684955 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 163 | SS-ZAM-MAD1163 | م/ الخوارزمي بنين | Al-Khwarizmi Boys | Intermediate | Boys | Madina | Madina | 24.489945379239.6744147242 | HLY2020627013555 | 10053848889 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 164 | SS-ZAM-MAD1164 | ب/ العاشرة بعد المائة بالمدينة بنات | Primary One hundred tenth in the city, girls | Primary | Girls | Madina | Madina | 24.497208773363198, 39.674865404055275 | HLY2020627013549 | 10053821428 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 165 | SS-ZAM-MAD1165 | م/ الثانية والسبعون بالمدينة بنات | Intermediate Seventy-two in the city, girls | Intermediate | Girls | Madina | Madina | 24.507980373543237, 39.67972573798892 | HLY2020627013532 | 10053254669 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 166 | SS-ZAM-MAD1166 | ث/ التاسعة والعشرون بالمدينة (مقررات) بنات | High Twenty-ninth in the city (curriculum) Girls | Secondary | Girls | Madina | Madina | 24.545101689793704, 39.67955517094319 | SXE2020627082376 | 10053374148 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 167 | SS-ZAM-MAD1167 | ب/ العريض بنين | Primary Al-Aridh Banin | Primary | Boys | Madina | Madina | 24.48663952215761, 39.65505313798806 | SXE2020627082482 | 10053442426 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 168 | SS-ZAM-MAD1168 | ث/ الخامسة والعشرون بالمدينة بنات | High Twenty-fifth in the city, girls | Secondary | Girls | Madina | Madina | 24.505925643715475, 39.61563265224959 | HLY2020627033393 | 10053498403 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 169 | SS-ZAM-MAD1169 | ث/ الخامسة عشر بالمدينة بنات | High Fifteenth in the city, girls | Secondary | Girls | Madina | Madina | 24.495046726634467, 39.5969135307544 | SXE2020627082913 | 10053502598 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 170 | SS-ZAM-MAD1170 | ب/ السادسة والعشرون بعد المائة بالمدينة بنات | Primary The 126th in the city, girls | Primary | Girls | Madina | Madina | 24.53326374643979, 39.645245425871096 | HLY2020627016448 | 10053562086 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 171 | SS-ZAM-MAD1171 | م/ السبعون بالمدينة بنات | Intermediate Al-Sab'un in the city, girls | Intermediate | Girls | Madina | Madina | 24.53169580209823, 39.64619552993005 | HLY2020627016450 | 10053617317 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 172 | SS-ZAM-MAD1172 | الروضة الخامسة والعشرون بنات | The twenty-fifth kindergarten for girls | Kindergarten | Girls | Madina | Madina | 24.450947044385988, 39.64940778031631 | SXE2020717039579 | 10053501106 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Not Started | Completed | Completed | Completed | 2 | 0 | 13 | In Progress
| 173 | SS-ZAM-MAD1173 | م/ عمر بن الخطاب بنين | Omar Ibn Al-Khattab Boys | Intermediate | Boys | Madina | Madina | 24.460833068617838, 39.62214315332853 | HLY2020627013615 | 10053476952 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 174 | SS-ZAM-MAD1174 | ث/ أبي بكر الرازي بنين | High Abu Bakr Al-Razi Boys | Secondary | Boys | Madina | Madina | 24.47692048165755, 39.6556663036113 | HLY2020627033229 | 10053847630 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 175 | SS-ZAM-MAD1175 | ث/ دار الإيمان (مقررات) بنين | High Dar Al-Iman (Curriculum) Boys | Secondary | Boys | Madina | Madina | 24.498298131870484, 39.60554641942669 | SMR2420628004480 | 10053546055 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 176 | SS-ZAM-MAD1176 | ب/ حمزة بن عبدالمطلب بنين | Primary Hamza bin Abdul-Muttalib Banin | Primary | Boys | Madina | Madina | 24.609699926205234, 39.6181945641427 | SXE2020627079202 | 10053500486 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 177 | SS-ZAM-MAD1177 | ث/ الاميرة نورة بنت عبدالرحمن بنات | Princess Noura bint Abdulrahman's daughters | Primary | Girls | Madina | Madina | 24.450092312288348, 39.6185299668222 | SXE2020627078380 | 10053438325 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 178 | SS-ZAM-MAD1178 | ب/ نسيبة بنت الحارث بنات | Primary Nusaybah bint al-Harith daughters | Primary | Girls | Madina | Madina | 24.54914330282048, 39.74023100730787 | HLY2020627033240 | 10053296088 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 179 | SS-ZAM-MAD1179 | م/ السادسة والعشرون بالمدينة بنات | Intermediate Twenty-sixth in the city, girls | Intermediate | Girls | Madina | Madina | 24.52546020171462, 39.669713194577184 | SXE2020627082295 | 10053369040 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 180 | SS-ZAM-MAD1180 | المدرسة الإبتدائية الثلاثون | Thirtieth Elementary School | Primary | Girls | Madina | Madina | 24.478291339486113, 39.63593121099967 | SXE2020627077341/SXE2020627077362 | 10053249382 10052043211 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 181 | SS-ZAM-MAD1181 | الابتدائية العشرون (طفولة مبكرة) | The twentieth elementary school (early childhood) | Early Childhood | Girls | Madina | Madina | 24.481767263138742, 39.62365246497608 | HLY2020627013506 | 10053435691 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 182 | SS-ZAM-MAD1182 | متوسطة القعقاع بن عمرو | Al-Qaqa'a Bin Amr Intermediate School | Intermediate | Boys | Madina | Madina | 24.455430331189394, 39.625594349634135 | SXE2020627029643/SXE2020627080226 | 10053480801 10053484426 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 183 | SS-ZAM-MAD1183 | المدرسة الابتدائية الثانية بنات لتحفيظ القرآن الكريم | Second Girls' Primary School for Memorizing the Holy Quran | Primary | Girls | Madina | Madina | 24.457970831064873, 39.49301486000903 | SXE2020627078310 | 10053787569 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 184 | SS-ZAM-MAD1184 | الثانوية الثامنة والعشرون والمتوسطة الثانية والثلاثون | The 28th High School and the 32nd Intermediate School | Secondary | Girls | Madina | Madina | 24.44524831979949, 39.5847618244927 | SXE2020627054902 | 10053311406 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 185 | SS-ZAM-MAD1185 | المتوسطة الثامنه والستون | Sixty-eighth Intermediate School | Intermediate | Girls | Madina | Madina | 24.43220396763341, 39.63358299565695 | SXE2020627078361 | 10053735787 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 186 | SS-ZAM-MAD1186 | المدرسة الواحدة والسبعون المتوسطة | Seventy-oneth Intermediate School | Intermediate | Girls | Madina | Madina | 24.620074561141074, 39.493366670911186 | SXE2020627083839 | 10053367715 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 187 | SS-ZAM-MAD1187 | مدرسة عقبة بن عامر الابتدائية وكعب بن عدي المتوسطة | Aqaba Bin Amer Elementary School and Kaab Bin Adi Intermediate School | Primary | Boys | Madina | Madina | 24.495122315961634, 39.64135545332954 | SMR2020865017380/ALH2020807216571 | 30061554394 10052292530 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 188 | SS-ZAM-MAD1188 | المدرسة الواحد والستون الإبتدائية | Sixty-oneth Elementary School | Primary | Girls | Madina | Madina | 24.416279587371612, 39.59476385332689 | SXE2020627082994 | 10083103001 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 189 | SS-ZAM-MAD1189 | مدرسة محمد بن سليمان بن رفاعة المتوسطة | Mohammed Bin Suleiman Bin Rifaa Intermediate School | Intermediate | Girls | Madina | Madina | 24.51461742492157, 39.66354381284794 | HLY2020627033223 | 10052292191 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 190 | SS-ZAM-MAD1190 | مدرسة حطين الابتدائية (طفولة مبكرة ) | Hattin Elementary School (Early Childhood) | Primary | Boys | Madina | Madina | 24.45273500819006, 39.6629132938106 | HLY2020627034452 | 10053819214 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 191 | SS-ZAM-MAD1191 | ثانوية رقية بنت النبي ﷺ | Ruqayya Bint Al-Nabi Secondary School ﷺ | Secondary | Girls | Madina | Madina | 24.398696333296297, 39.52722936682057 | HLY2020627016787 | 10101245763 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 192 | SS-ZAM-MAD1192 | مدرسة الإمام حمزة بن حبيب الزيات | Imam Hamza Bin Habib Al-Zayyat School | Primary | Boys | Madina | Madina | 24.44216648992665, 39.58431459565717 | SXE2020627054900 | 10053441831 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 193 | SS-ZAM-MAD1193 | مدرسة الثانوية الخامسة | Fifth High School | Secondary | Girls | Madina | Madina | 24.478884417614545, 39.63525472847016 | SMR2320621012923 SXE2020627077341 KFM2120655006088 SXE2020627077338 SXE2020627077362 | 10105384344 10053249382 10105114803 10053248723 10052043211 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 194 | SS-ZAM-MAD1194 | المتوسطة السابعه والثلاثون | The thirty-seventh intermediate | Intermediate | Girls | Madina | Madina | 24.548326793900326, 39.678970458727775 | SXE2020627082294 | 10053373061 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 195 | SS-ZAM-MAD1195 | لمدرسة الابتدائية الثانية والثمانون للبنات | For the 82nd Girls' Elementary School | Primary | Girls | Madina | Madina | 24.44559784298602, 39.61718065702219 | SXE2020627068975 SXE2020627068974 SXE2020627000135 | 10100425079 10100401578 10053365013 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 196 | SS-ZAM-MAD1196 | ثانوية عاصم بن الحكم | Asim Bin Al-Hakam High School | Secondary | Boys | Madina | Madina | 24.447920781896634, 39.60537695332813 | SXE2020627078311 | 10052039783 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 197 | SS-ZAM-MAD1197 | ثانوية العباس بن عبدالمطلب بنين | Al-Abbas Bin Abdul-Muttalib Secondary School for Boys | Secondary | Boys | Madina | Madina | 24.45274460915015, 39.52443249565752 | SXE2020627066166 SXE2020627083825 | 10053819241 10053623216 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 198 | SS-ZAM-MAD1198 | ثانوية ابن القيم | Ibn Al-Qayyim High School | Secondary | Boys | Madina | Madina | 24.473197411522303, 39.56240573798763 | SXE2020627068889 | 10053435735 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 199 | SS-ZAM-MAD1199 | مدرسة محمد بن سعود الثانوية للبنين | Mohammed Bin Saud Secondary School for Boys | Secondary | Boys | Madina | Madina | 24.465801525949697, 39.587830253328484 | HLY2020627016358 | 10053816141 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 200 | SS-ZAM-MAD1200 | مدرسة وهب بن سعد الابتدائية | Wahb Bin Saad Elementary School | Primary | Boys | Madina | Madina | 24.50983333331281, 39.54898130915349 | HLY2020627033430 | 10053817102 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
Total | [11 empty] | Total | Completed | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 198 | 200 | 198 | 200 | 200 | 200 |  |  |  | 199.7333
[13 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0
Note on M4: 4/2/2025
Note on N4: 4/2/2025
Note on Y90: Muhammad Rafique / CoolCare MRO Solar Energy: No Space
Note on Y175: Muhammad Rafique / CoolCare MRO Solar Energy: No Space

## Qassim Schools -1
|  | Report Date | 2026-02-23
Project | Schools Information | [10 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Qassim-1 | SS-ZAM-QAS1001 | متوسطة أبي عبيدة - بنين | Abu Ubaidah Intermediate School - Boys | Intermediate | Boys | Qassim | Buraidah | 26.377565371878394, 43.9531232 | KFM2120660298585 | 10091788928 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | Primary | Boys | Not Started
| SS-ZAM-QAS1002 | ثانوية الامام الطحاوي ببريدة - بنين | Imam Al-Tahawi Secondary School in Buraydah - Boys | Secondary | Boys | Qassim | Buraidah | 26.378638081566947, 43.9632862981472 | KFM2020660207744 | 10041261615 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | Intermediate | Girls | In Progress
| SS-ZAM-QAS1003 | ابتدائية الفاروق ببريدة - بنين | Al-Farouq Primary School in Buraydah - Boys | Primary | Boys | Qassim | Buraidah | 26.314535938770497, 43.97916734232776 | KFM2020660194245 | 10041839321 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | Secondary | NA | Completed
| SS-ZAM-QAS1004 | ابتدائية عثمان بن عفان - بنين | Uthman Ibn Affan Primary School - Boys | Primary | Boys | Qassim | Buraidah | 26.36656987398822, 43.95879028079699 | KFM2020660194788 | 10041458147 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | NA |  | NA
| SS-ZAM-QAS1005 | ابتدائية الفيصلية - بنين | Al-Faisaliyah Primary School - Boys | Primary | Boys | Qassim | Buraidah | 26.350849068455826, 43.96486583862219 | KFM2020660205336 | 10041394424 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1006 | متوسطة سيبويه - بنين | Sibawayh Intermediate School - Boys | Intermediate | Boys | Qassim | Buraidah | 26.421786846547906, 43.92867671694747 | KFM2020660187506 | 10093142685 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1007 | المتوسطة الخامسة والخمسون - بنات | Fifty-Fifth Intermediate School - Girls | Intermediate | Girls | Qassim | Buraidah | 26.31762513871044, 44.0157636981472 | SRM2320661033214 | 10105752709 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1008 | ثانوية قيس بن عاصم رضى الله عنه - بنين | Qais Ibn Asim Secondary School - Boys | Secondary | Boys | Qassim | Buraidah | 26.429288367147016, 43.92249690734597 | KFM2020660187503 | 10093149041 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1009 | الثانوية الخامسة والعشرون ببريدة - مسارات - بنات | Twenty-Fifth Secondary School in Buraydah - Tracks - Girls | Secondary | Girls | Qassim | Buraidah | 26.33457611928418, 44.02365450753766 | KFM2120660265817 | 10041713114 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1010 | مدرسة أم المؤمنين صفية بنت حيي للطفولة المبكرة والابتدائية ببريدة - بنات | Umm Al-Mu'minin Safiyyah Bint Huyayy Early Childhood and Primary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.35850960225151, 43.99530875396663 | KFM2120660301083 | 10041960204‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1011 | الابتدائية الثانية لتحفيظ القران ببريدة - بنات | Second Elementary School for Quran Memorization in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.341639525760833, 43.98283699999999 | KFM2020660211765 | 10042006958‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1012 | الابتدائية السادسة والثلاثون ببريدة - بنات | Thirty-Sixth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.342109361437224, 43.9824027962944 | KFM2020660194922 | 10041954781‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1013 | الابتدائية السابعة لتحفيظ القران ببريدة - بنات | Seventh Elementary School for Quran Memorization in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.31284069234813, 43.963026367980376 | KFM2120660263561 | 10099573152‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1014 | المتوسطة السادسة والأربعون ببريدة - بنات | Forty-Sixth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.30930340608794, 44.0394545968165 | KFM2020660194381 | 10090562499‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1015 | الابتدائية الرابعة والاربعون ببريدة - بنات | Forty-Fourth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.37959284467777, 43.97124627116389 | KFM2020660205572 | 10041468205‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1016 | الأبتدائية الثانية بالشقة- بنات | Second Elementary School in Al-Shaqqah - Girls | Primary | Girls | Qassim | Buraidah | 26.38233964845454, 43.86308381534445 | KFM2020660211704 | 10089582784‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1017 | الثانوية الثانية بالشقة - بنات | Second Secondary School in Al-Shaqqah - Girls | Secondary | Girls | Qassim | Buraidah | 26.38471803685407, 43.864888596294406 | KFM2120660246812 | 10041525231‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1018 | الابتدائية الثلاثون ببريدة - بنات | Thirtieth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.338008220827337, 43.97967345767223 | KFM2020660204801 | 10041716180‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1019 | ثانوية المليداء ببريدة - بنات | Al-Mulayda Secondary School in Buraydah - Girls | Secondary | Girls | Qassim | Buraidah | 26.3159592371164, 43.78489492327772 | KFM2120660304756 | 10041931051‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1020 | الابتدائية الثالثة ببريدة - بنات | Third Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.33878430851326, 44.05046893590979 | KFM2120660248042 | 10041559346‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1021 | الابتدائية الرابعة بالشقة - بنات | Fourth Elementary School in Al-Shaqqa - Girls | Primary | Girls | Qassim | Buraidah | 26.36832347696112, 43.86238881349165 | KFM2020660204853 | 10041559471‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1022 | متوسطة ام المؤمنين حفصة رضى الله عنها - بنات | Umm Al-Mu'minin Hafsa Intermediate School - Girls | Intermediate | Girls | Qassim | Buraidah | 26.379869620922396, 43.91422657116387 | KFM2020660204691 | 10088604869‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1023 | الابتدائية الثامنة ببريدة - بنات | Eighth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.32394673981208, 43.96395886805202 | KFM2020660193845 | 10041716662‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1024 | المتوسطة الثامنة عشرة ببريدة - بنات | Eighteenth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.32904751397411, 44.02574537472621 | KFM2120660265820 | 10041778709‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1025 | الابتدائية الثانية عشرة ببريدة - بنات | Twelfth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.319494666557546, 43.95655717843181 | KFM2020660153836 | 10041816013‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1026 | الابتدائية الرابعة لتحفيظ القران ببريدة - بنات | Fourth Elementary School for Quran Memorization in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.330200483184264, 43.963206492537836 | KFM2120660265200 | 10041848625‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1027 | مدرسة سهلة بنت سهيل للطفولة المبكرة والابتدائية ببريدة - بنات | Sahla Bint Suhayl Early Childhood and Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.32279582404724, 44.038697957672234 | KFM2020660194286 | 10041896211‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1028 | مجمع خضبراء التعليمي -بنات | Khadhra Educational Complex - Girls |  | Girls | Qassim | Buraidah | 26.301624323358322, 44.01321574774289 | KFM2020660206346 | 10041815901‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1029 | الثانوية الخامسة عشر ببريدة - مسارات - بنات | Fifteenth Secondary School in Buraydah - Masarat - Girls | Secondary | Girls | Qassim | Buraidah | 26.32470672160058, 43.98975740897745 | KFM2020660194861 | 10041349797‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1030 | الابتدائية السابعة والثمانون ببريدة - بنات | Eighty-Seventh Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.411313246560834, 43.92881765296699 | KFM2020660207743 | 10041862624 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1031 | متوسطة الجزيرة ببريدة - بنين | Al-Jazira Intermediate School in Buraydah - Boys | Intermediate | Boys | Qassim | Buraidah | 26.376439485956773, 43.97463795767222 | SMR2320661024096 | 10041281501‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1032 | الابتدائية السابعة ببريدة - بنات | Seventh Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.317296626174514, 43.98055042572424 | KFM2120660248033 | 10041615740‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1033 | المتوسطة الثانية بالشقة - بنات | Second Intermediate School in Al-Shaqqa - Girls | Intermediate | Girls | Qassim | Buraidah | 26.382602096476422, 43.861201071163876 | KFM2020660211706 | 10089583816‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1034 | الابتدائية السابعة عشرة ببريدة - بنات | Seventeenth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.31241804812618, 44.049906169311086 | KFM2020660194301 | 10041170708‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1035 | ابتدائية آبي موسى الاشعري لتحفيظ القران ببريدة - بنين | Abi Musa Al-Ash'ari Elementary School for Quran Memorization in Buraydah - Boys | Primary | Boys | Qassim | Buraidah | 26.376231062490895, 43.975591571163875 | KFM2020660205320 | 10041544147‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1036 | ابتدائية ام القرى ببريدة - بنين | Umm Al-Qura Elementary School in Buraydah - Boys | Primary | Boys | Qassim | Buraidah | 26.37571274734229, 43.97458145767222 | KFM2120660303672 | 10092566853‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1037 | مدرسة رابعة بنت ثابت للطفولة المبكرة ببريدة - بنات | Rabia Bint Thabit Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.321960364370632, 43.992020830545634 | KFM2120660273099 | 10041163276‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1038 | المتوسطة الرابعة ببريدة - بنات | Fourth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.324600368916112, 43.98639152016585 | SMR2220661003533 | 10041571378‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1039 | آمنة بنت عثمان بن عفان ببريدة - بنات | Amina Bint Uthman Bin Affan School in Buraydah - Girls |  | Girls | Qassim | Buraidah | 26.374335293387343, 43.85332699999999 | KFM2120660301427 | 10041849856‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1040 | المتوسطة الخامسة والثلاثون ببريدة - بنات | Thirty-Fifth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.347307744090386, 43.96624915952503 | KFM2020660204870 | 10041906068‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1041 | مدرسة سعاد بنت سلمة للطفولة المبكرة ببريدة - بنات | Suad Bint Salma Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.393832861696563, 43.85994402698332 | SRM2320661021337 | 10041395628‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1042 | مدرسة العريمضي للطفولة المبكرة والابتدائية - بنات | Al-Uraymdi Early Childhood and Elementary School - Girls | Primary | Girls | Qassim | Buraidah | 26.291501333642245, 43.9229215275054 | KFM2120660304332 | 10083696062‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1043 | ابتدائية محمد بن مالك ببريدة - بنين | Muhammad Bin Malik Elementary School in Buraydah - Boys | Primary | Boys | Qassim | Buraidah | 26.37020224713368, 43.9700071944416 | KFM2020660194776 | 10041288904‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1044 | الثانوية الأولى بالمريدسية - مقررات - بنات | First Secondary School in Al-Muraydisiyah - Curriculum - Girls | Secondary | Girls | Qassim | Buraidah | 26.311027734517022, 43.93207346007274 | KFM2020660187281 | 10041612953‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1045 | ابتدائية الامام مجاهد ببريدة - بنين | Imam Mujahid Elementary School in Buraydah - Boys | Primary | Boys | Qassim | Buraidah | 26.379858168868818, 43.96285143280276 | KFM2020660204873 | 10041498321‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1046 | الثانوية التاسعة ببريدة - مقررات - بنات | Ninth Secondary School in Buraydah - Curriculum - Girls | Secondary | Girls | Qassim | Buraidah | 26.320849099166402, 43.98245987909717 | KFM2120660304327 | 10041432472‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1047 | الابتدائية الخامسة والأربعون ببريدة - بنات | Forty-Fifth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.313418848958282, 43.96353614788615 | KFM2020660194524 | 10041757932 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1048 | مدرسة زينب بنت عمر بن الخطاب للطفولة المبكرة والابتدائية ببريدة - بنات | Zainab Bint Omar Bin Al-Khattab Early Childhood and Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.332593004571695, 43.97315585767222 | KFM2120660304324 | 10041535809‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1049 | الثانوية العاشرة ببريدة - مقررات - بنات | Tenth Secondary School in Buraydah - Curriculum - Girls | Secondary | Girls | Qassim | Buraidah | 26.319108766819472, 43.95657777301668 | KFM2020660166406 | 10041171090‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1050 | الابتدائية الرابعة والستون ببريدة - بنات | Sixty-Fourth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.417416428403282, 43.89447228220243 | SMR2320661030271 | 10105885044 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1051 | متوسطة الخضر والوجيعان ببريدة - بنات | Al-Khader and Al-Wajee'an Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.277119262889055, 43.98425871163887 | KFM2020660194782 | 10041784635‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1052 | مدرسة كريمة الكندية للطفولة المبكرة ببريدة - بنات | Karimah Al-Kindiyyah Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.338229354981287, 43.978952171711065 | KFM2020660196170 | 10041257318‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1053 | الابتدائية الاولى بحويلان - بنات | First Elementary School in Huwaylan - Girls | Primary | Girls | Qassim | Buraidah | 26.29979415939092, 43.946270637363114 | KFM2020660195287 | 10041664726‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1054 | مدرسة أم العلاء الأنصارية للطفولة المبكرة ببريدة - بنات | Umm Al-Ala' Al-Ansariyah Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.31139037314534, 43.901889446033366 | KFM2020660211723 | 10041785356‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1055 | إبتدائية عبدالرحمن بن عوف (رضى الله عنه ) - بنين | Abdul Rahman Bin Auf Elementary School (may God be pleased with him) - Boys | Primary | Boys | Qassim | Buraidah | 26.343210472889155, 43.922067121163884 | KFM2020660194450 | 10041772680‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1056 | الابتدائية السادسة لتحفيظ القران ببريدة - بنات | Sixth Elementary School for Quran Memorization in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.380217364278348, 43.97081228094994 | KFM2020660205359 | 10041170145 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1057 | الثانوية الأولى بضراس - مقررات - بنات | First Secondary School in Dhiras - Curriculum - Girls | Secondary | Girls | Qassim | Buraidah | 26.31362338615485, 43.88969244076161 | KFM2120660278912 | 10041716878 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1058 | ابتدائية عقبة بن عامر | Uqbah Bin Amer Elementary School | Primary |  | Qassim | Buraidah | 26.28881142484351, 43.870193986221814 | KFM2120660266841 | 10041304811‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1059 | حويلان | Huwaylan |  |  | Qassim | Buraidah | 26.297134752077834, 43.9470385048214 | KFM2020660195286 | 10041773060 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1060 | البصر | Al-Basr |  |  | Qassim | Buraidah | 26.30062884565418, 43.868010958716404 | KFM2120660266830 | 10085393386‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1061 | ابتدائية العز بن عبدالسلام | Al-Izz Bin Abdul Salam Elementary School | Primary |  | Qassim | Buraidah | 26.329769579059793, 43.94388911349165 | KFM2120660301870 | 10041287649 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1062 | الأمير عبدالعزيز بن مساعد | Prince Abdulaziz bin Musaed Elementary School | Primary |  | Qassim | Buraidah | 26.320032665241932, 43.78165145767223 | KFM2120660266793 | 10041882897‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1063 | ابتدائية التضامن الاسلامي | Al-Tadhamun Al-Islami Elementary School | Primary |  | Qassim | Buraidah | 26.33418730794302, 44.000028152349394 | KFM2120660236017 | 10041643593‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1064 | تحفيظ ابتدائية الشيخ صالح البليهي لتحفيظ القران الكريم | Sheikh Saleh Al-Bulaihi Elementary School for Quran Memorization | Primary |  | Qassim | Buraidah | 26.318055775856685, 43.975305775105035 | KFM2120660237486 | 10041762665 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1065 | المعهد العلمي ببريدة - ثانوي | Buraidah Scientific Institute - Secondary Level | Secondary |  | Qassim | Buraidah | 26.329352158232364, 43.976792336104026 | KFM2120660248045 | 10041149034‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1066 | متوسطة الشيخ محمد بن عثيمين لتحفيظ القرآن الكريم | Sheikh Muhammad bin Uthaimin Intermediate School for Quran Memorization | Intermediate |  | Qassim | Buraidah | 26.34100821614053, 43.9599191018528 | KFM2020660194300 | 10041717285‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1067 | ثانوية الملك سعود - مسارات | King Saud Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.31595478152602, 43.95927945605498 | KFM2120660235954 | 10041313257‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1068 | مدرسة الإمام النووي الابتدائية | Imam Al-Nawawi Elementary School | Primary |  | Qassim | Buraidah | 26.31665865725146, 43.9628236931109 | KFM2020660194529 | 10041737911 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1069 | ابتدائية القدس | Al-Quds Elementary School | Primary |  | Qassim | Buraidah | 26.316858694522594, 43.983174631733085 | KFM2120660263559 | 10083090048‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1070 | ثانوية مكةالمكرمة - مسارات | Makkah Al-Mukarramah Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.308874500225702, 43.981028207105275 | KFM2120660298646 | 10041772812‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1071 | متوسطة امام الدعوة ببريدة | Imam Al-Da'wah Intermediate School in Buraidah | Intermediate |  | Qassim | Buraidah | 26.336672334839776, 43.97651995767224 | KFM2020660205333 | 10041262499‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1072 | مجمع الشيخ عبدالعزيز المسند لحفيظ القرآن الكريم - القسم الابتدائي | Sheikh Abdulaziz Al-Musnad Complex for Quran Memorization - Elementary Section | Primary |  | Qassim | Buraidah | 26.3871174535979, 43.94129152883611 | KFM2120660235980 | 10041823377‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1073 | مجمع الشيخ عبدالعزيز المسند لحفيظ القرآن الكريم - القسم المتوسط | Sheikh Abdulaziz Al-Musnad Complex for Quran Memorization - Intermediate Section | Intermediate |  | Qassim | Buraidah | 26.3870790095243, 43.94117351163886 | KFM2120660235981 | 10041823500‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1074 | تحفيظ ابتدائية الإمام نافع المدني لتحفيظ القرآن الكريم | Imam Nafi' Al-Madani Elementary School for Quran Memorization | Primary |  | Qassim | Buraidah | 26.37987083255587, 43.93275596931109 | KFM2020660187393 | 10041762066‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1075 | ابتدائية معاذ بن جبل | Mu'adh bin Jabal Elementary School | Primary |  | Qassim | Buraidah | 26.387546057842513, 43.937181173066996 | KFM2020660194545 | 10041494143‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1076 | ابتدائية الخوارزمي | Al-Khwarizmi Elementary School | Primary |  | Qassim | Buraidah | 26.391087471084507, 43.935849611638865 | KFM2020660187384 | 10041810118‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1077 | متوسطة العقيلات | Al-Uqailat Intermediate School | Intermediate |  | Qassim | Buraidah | 26.391013992594548, 43.93669404603337 | KFM2020660187400 | 10041850006‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1078 | مدرسة القصيعة | Al-Qasai'ah School |  |  | Qassim | Buraidah | 26.265311612886602, 43.965557307945524 | KFM2020660204986 | 10041382479 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1079 | ابتدائية المريدسية | Al-Muraydisiyah Elementary School | Primary |  | Qassim | Buraidah | 26.3173393708925, 43.92695851244751 | KFM2020660204683 | 10041212657 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1080 | ابتدائية معهد التربية الفكرية | Institute of Intellectual Education Elementary School | Primary |  | Qassim | Buraidah | 26.30873405516097, 43.92011791683302 | KFM2120660268425 | 10041290303 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1081 | متوسطة عبدالله بن الزبير | Abdullah bin Al-Zubair Intermediate School | Intermediate |  | Qassim | Buraidah | 26.27447048807195, 43.96482441483462 | KFM2020660204761 | 10041734400 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1082 | مدرسة اشبيليا | Ashbilia School |  |  | Qassim | Buraidah | 26.34381368033462, 43.90822034418056 | KFM2020660194447 | 10041660404 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1083 | ابتدائية احمد بن حنبل | Ahmed bin Hanbal Elementary School | Primary |  | Qassim | Buraidah | 26.382671836698457, 43.908229713491664 | KFM2020660204670 | 10041899938 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1084 | ابتدائية الأمام الذهبي | Imam Al-Dhahabi Elementary School | Primary |  | Qassim | Buraidah | 26.38943242748317, 43.9242179 | KFM2020660187367 | 10041772222 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1085 | ابتدائية علي بن ابي طالب | Ali bin Abi Talib Elementary School | Primary |  | Qassim | Buraidah | 26.356783738746635, 43.89440538650834 | KFM2120660238430 | 10041780091 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1086 | ابتدائية عمر بن سليم | Omar bin Salim Elementary School | Primary |  | Qassim | Buraidah | 26.378958557498862, 43.92255399258881 | KFM2020660204721 | 10041855254 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1087 | العلاء بن زياد | Al-Ala bin Ziyad School |  |  | Qassim | Buraidah | 26.394986307396927, 43.9145904981472 | KFM2020660204667 | 10041795540 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1088 | القاضي بن ابي يعلى | Al-Qadi bin Abi Ya'la School |  |  | Qassim | Buraidah | 26.3919197699761, 43.88946678836114 | KFM2020660187359 | 10041694903 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1089 | عوق عقلي الحسين بن علي | Al-Hussein bin Ali School (Mental Disability) |  |  | Qassim | Buraidah | 26.355327403063765, 43.933707341021844 | KFM2120660274338 | 10041848984 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1090 | خالد بن دينار | Khalid bin Dinar School |  |  | Qassim | Buraidah | 26.380000355591978, 43.859246284655555 | KFM2120660301424 | 10041911827 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1091 | ابي داؤود | Abi Dawood School |  |  | Qassim | Buraidah | 26.3481290983487, 43.937466565630345 | KFM2020660187414 | 10041840485 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1092 | ابتدائية ضراس | Dharas Elementary School | Primary |  | Qassim | Buraidah | 26.319929015576975, 43.88647257672227 | KFM2120660248117 | 10041808890 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1093 | الأمين | Al-Amin School |  |  | Qassim | Buraidah | 26.40674516303153, 43.91426422698332 | KFM2120660238459 | 10041865617 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1094 | مالك بن عامر | Malik bin Amer School |  |  | Qassim | Buraidah | 26.362518200662844, 43.928413371163884 | KFM2020660194801 | 10041849201 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1095 | العبودي | Al-Aboudi School |  |  | Qassim | Buraidah | 26.386674531969643, 43.924104330688905 | KFM2020660187238 | 10041784878 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1096 | الأدريسي | Al-Idrisi School |  |  | Qassim | Buraidah | 26.365128147135497, 43.862554417197266 | KFM2120660266856 | 10083305992 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1097 | الأمير عبدالاله بن عبدالعزيز | Prince Abdul-Ilah bin Abdul-Aziz School |  |  | Qassim | Buraidah | 26.36313913433603, 43.92815821349166 | KFM2020660194802 | 10041848957 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1098 | متوسطة مجمع صالح بن علي العثيم | Saleh bin Ali Al-Uthaim Intermediate School | Intermediate |  | Qassim | Buraidah | 26.42753633784184, 43.88341486931109 | MMF2420601017209 | 10106559267 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1099 | ابتدائية الإمام ابي حنيفة | Imam Abu Hanifa Elementary School | Primary |  | Qassim | Buraidah | 26.340335677183976, 44.026047017139156 | KFM2120660265821 | 10041180741 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1100 | ابتدائية الهدية | Al-Huda Elementary School | Primary |  | Qassim | Buraidah | 26.399250382648333, 44.05753607854146 | KFM2120660284107 | 10041648061 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1101 | ابتدائية أبوبكر الصديق - عوق عقلي | Abu Bakr Al-Siddiq Elementary School - Intellectual Disability | Primary |  | Qassim | Buraidah | 26.309087525409335, 44.04616383068891 | KFM2020660194267 | 10041275101 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1102 | ابتدائية خباب بن الأرت | Khabbab Ibn Al-Aratt Elementary School | Primary |  | Qassim | Buraidah | 26.30523594208417, 44.02529593700494 | KFM2120660300986 | 10041737519 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1103 | ابتدائية فلسطين | Palestine Elementary School | Primary |  | Qassim | Buraidah | 26.370042311184683, 43.99909298280275 | KFM2120660303892 | 10083812831 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1104 | ثانوية الامير فيصل بن فهد - مسارات | Prince Faisal Bin Fahd Secondary School - Special Needs | Secondary |  | Qassim | Buraidah | 26.338518363318304, 44.017421313727205 | KFM2120660282791 | 10041853563 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1105 | ثانوية بريدة - عوق عقلي | Buraidah Secondary School - Intellectual Disability | Secondary |  | Qassim | Buraidah | 26.327724955372318, 43.98563082379981 | KFM2120660301899 | 10041228479 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1106 | متوسطة ابن قدامة | Ibn Qudamah Intermediate School | Intermediate |  | Qassim | Buraidah | 26.320412430379776, 43.995247572873424 | KFM2120660273103 | 10041228595 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1107 | متوسطة الاحنف بن قيس | Al-Ahnaf Bin Qais Intermediate School | Intermediate |  | Qassim | Buraidah | 26.33369121767994, 44.00049476109128 | KFM2120660236019 | 10041231803 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1108 | متوسطة الشيخ عبدالعزيز بن باز | Sheikh Abdulaziz Bin Baz Intermediate School | Intermediate |  | Qassim | Buraidah | 26.31159357248084, 44.052365102482334 | KFM2120660248041 | 10041532271 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1109 | ابتدائية سهل بن الربيع | Sahl Bin Al-Rabee Elementary School | Primary |  | Qassim | Buraidah | 26.368527876587144, 43.974010173016666 | KFM2020660194780 | 10041711906 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1110 | متوسطة الامام محمد بن سعود | Imam Muhammad Bin Saud Intermediate School | Intermediate |  | Qassim | Buraidah | 26.37048572333879, 43.96851391349165 | KFM2020660194771 | 10041660075 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1111 | ابتدائية ابن ماجة | Ibn Majah Elementary School | Primary |  | Qassim | Buraidah | 26.38493605980373, 43.97027698094996 | KFM2020660205354 | 10041824623 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1112 | ابتدائية الآمدي | Al-Amidi Elementary School | Primary |  | Qassim | Buraidah | 26.387036454407905, 43.9889119 | KFM2120660244797 | 10041830569 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1113 | مجمع الخليج التعليمي القسم المتوسط | Al-Khaleej Educational Complex - Intermediate Section | Intermediate |  | Qassim | Buraidah | 26.307803573023445, 43.968642471685975 | KFM2120660274301 | 10041684685 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1114 | ابتدائية العجيبة | Al-Ajeeba Elementary School | Primary |  | Qassim | Buraidah | 26.328497839727987, 43.96678259688814 | KFM2020660194527 | 10041472478 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1115 | ابتدائية رواق | Rawaq Elementary School | Primary |  | Qassim | Buraidah | 26.276879105318084, 44.004020687902276 | SMR2220661019175 | 10041305925 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1116 | ابتدائية الشيخ محمد بن عثيمين لتحفيظ القرآن الكريم | Sheikh Muhammad bin Uthaimin Elementary School for Quran Memorization | Primary |  | Qassim | Buraidah | 26.34135447774397, 43.960972808526996 | KFM2020660194297 | 10041717409 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1117 | مركز الشيخ محمد بن ابراهيم للتعليم المستمر | Sheikh Muhammad bin Ibrahim Center for Continuing Education |  |  | Qassim | Buraidah | 26.29202506351482, 43.99553417412409 | KFM2120660274539 | 10040976522 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1118 | متوسطة ابن كثير | Ibn Kathir Intermediate School | Intermediate |  | Qassim | Buraidah | 26.314341838996057, 43.97866863729147 | KFM2020660194483 | 10041377719 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1119 | عوق عقلي - ابتدائية معهد التربية الفكرية شمال | Intellectual Disability - Elementary School of the Institute of Intellectual Education North | Primary |  | Qassim | Buraidah | 26.366295367905543, 43.94053079999999 | KFM2020660187232 | 10041492962 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1120 | ابتدائية ابن عقيل | Ibn Aqeel Elementary School | Primary |  | Qassim | Buraidah | 26.36138155013897, 43.937517342327766 | KFM2120660265790 | 10041900190 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1121 | ثانوية مجمع الأمير سلطان - مسارات | Prince Sultan Complex Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.363098069053965, 43.94367154232776 | KFM2020660194807 | 10041348056 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1122 | مجمع الأمير سلطان - القسم متوسطة | Prince Sultan Complex - Intermediate Section | Intermediate |  | Qassim | Buraidah | 26.362168417862076, 43.94296027116389 | KFM2020660194808 | 10041347809 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1123 | ثانوية الأقصى - مسارات | Al-Aqsa Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.37361051866034, 43.93423041534445 | KFM2020660019933 | 10041580608 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1124 | ابتدائية المعرفة في بريدة | Al-Ma'rifah Elementary School in Buraidah | Primary |  | Qassim | Buraidah | 26.40595720805846, 43.93031854232778 | KFM2020660194355 | 10085138141 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1125 | تحفيظ ابتدائية الشيخ عبد الرحمن بن عبدالله بن فريان | Sheikh Abdul Rahman bin Abdullah bin Faryan Elementary School for Quran Memorization | Primary |  | Qassim | Buraidah | 26.35949371978003, 43.95122697116389 | KFM2020660187271 | 10041773201 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1126 | ثانوية عمرو بن العاص - مسارات | Amr bin Al-Aas Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.37976563273092, 43.950047963491656 | SMR2320661035056 | 10041344647 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1127 | ابتدائية الفتح الرائدة في بريدة | Al-Fath Al-Ra'idah Elementary School in Buraidah | Primary |  | Qassim | Buraidah | 26.362326396275712, 43.95387671163886 | KFM2020660194687 | 10041277016 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1128 | ابتدائية الإمام السيوطي | Imam Al-Suyuti Elementary School | Primary |  | Qassim | Buraidah | 26.413045012824316, 43.918196515344455 | KFM2020660194600 | 10082971978 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1129 | متوسطة قتادة بن النعمان | Qatadah bin Al-Nu'man Intermediate School | Intermediate |  | Qassim | Buraidah | 26.39860646184259, 43.92647101349167 | KFM2120660268565 | 10041960429 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1130 | متوسطة ابن عبدالبر | Ibn Abdul-Barr Intermediate School | Intermediate |  | Qassim | Buraidah | 26.398558411530253, 43.92661048836115 | KFM2020660204545 | 10041634914 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1131 | ابتدائية أحد | Uhud Elementary School | Primary |  | Qassim | Buraidah | 26.323220459418938, 43.963271084655545 | KFM2020660194530 | 10041312993 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1132 | ثمامة بن عدي | Thumamah ibn Adi School |  |  | Qassim | Buraidah | 26.297590755370496, 43.945617500378816 | SMR2220661013332 | 10041338908 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1133 | الطفيل بن عمرو | Al-Tufayl ibn Amr School |  |  | Qassim | Buraidah | 26.380922700109544, 43.85885952698333 | KFM2120660301426 | 10041839199 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1134 | ثانوية الرازي - مسارات | Al-Razi Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.312232657871945, 44.049376849280115 | KFM2020660194306 | 10041501622 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1135 | متوسطة الامام الترمذي | Imam Al-Tirmidhi Intermediate School | Intermediate |  | Qassim | Buraidah | 26.331365740900385, 44.02226357168597 | KFM2120660250145 | 10041806948 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1136 | ثانوية النجاشي - مسارات | Al-Najashi Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.364834225742662, 43.95055415767222 | KFM2020660204541 | 10041285081 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1137 | مدرسة أميمة بن الخطاب للطفولة المكبرة ببريدة - بنات | Umaymah ibn Al-Khattab Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.352541705828425, 43.93546585581944 | SMR2220661003582 | 10104659998 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1138 | مجمع الخليج التعليمي - القسم الثانوي ببريدة - بنين | Al-Khaleej Educational Complex - Secondary Section in Buraydah - Boys | Secondary | Boys | Qassim | Buraidah | 26.30910586259207, 43.968390356341516 | KFM2120660274296 | 10041684569 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1139 | مدرسة سلمى بنت صخر للطفولة المبكرة ببريدة - بنات | Salma ibn Sakhr Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.364882034800335, 43.95386168465554 | KFM2020660194809 | 10041347925 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1140 | الابتدائية السابعة والتسعون ببريدة - بنات | Ninety-Seventh Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.327812418703093, 44.01522104893033 | KFM2020660195607 | 10041898289 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1141 | الثانوية السادسة عشر ببريدة - بنات | Sixteenth Secondary School in Buraydah - Girls | Secondary | Girls | Qassim | Buraidah | 26.369313750033438, 43.96481985396663 | KFM2020660204860 | 10041535934 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1142 | الابتدائية السبعون ببريدة - بنات | Seventieth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.336315052437982, 43.99215230109516 | KFM2120660303667 | 10098869591 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1143 | متوسطة الميلداء ببريدة - بنات | Al-Milda Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.31645050560227, 43.78534588465554 | KFM2020660204679 | 10041773328 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1144 | المتوسطة السادسة عشرة ببريدة - بنات | Sixteenth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.345199175696244, 43.98885132698332 | KFM2020660194929 | 10041799496 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1145 | الابتدائية السادسة والستون ببريدة - بنات | Sixty-Sixth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.354056025751344, 44.05134590936107 | KFM2020660194303 | 10041637710 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1146 | مدرسة الشماس للطفولة المبكرة ببريدة - بنات | Al-Shamas Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.329057417034154, 43.961431928836106 | KFM2120660265199 | 10088484671 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1147 | الثانوية الثامنة ببريدة - بنات | Eighth Secondary School in Buraydah - Girls | Secondary | Girls | Qassim | Buraidah | 26.372956106047504, 43.944630750225585 | KFM2120660274343 | 10041996001 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1148 | المتوسطة السابعة العشرون ببريدة - بنات | 27th Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.34799261191683, 43.93919372541639 | KFM2120660274335 | 10041996065 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1149 | المتوسطة الحادية عشر بمحافظة بريدة - بنات | 11th Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.332925295071004, 43.997307772873405 | KFM2120660236021 | 10041181864 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1150 | الابتدائية الخامسة عشر ببريدة - بنات | 15th Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.367798254983068, 43.95116555581943 | KFM2020660194827 | 10041225092 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1151 | المتوسطة الثالثة ببريدة - بنات | 3rd Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.407754332718472, 43.931189084655536 | KFM2020660194592 | 10041989614 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1152 | مدرسة أمامة بنت حمزة للطفولة المبكرة ببريدة - بنات | Umamah Bint Hamzah Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.28709495130798, 43.99391834589009 | KFM2120660238629 | 10082622091 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1153 | الثانوية الثامنة والعشرون - مسارات - بنات | 28th Secondary School - Tracks - Girls | Secondary | Girls | Qassim | Buraidah | 26.325852254611064, 43.96214831349165 | KFM2120660247227 | 10041568372 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1154 | مدرسة حسناء بنت معاوية للطفولة المبكرة ببريدة - بنات | Hasna Bint Muawiyah Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.31251608179027, 43.9684069802846 | KFM2020660204858 | 10041406445 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1155 | المتوسطة التاسعة ببريدة - بنات | 9th Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.287326162249233, 43.993840642849854 | KFM2120660238626 | 10082616773 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1156 | مدرسة رقية بنت عمر بن الخطاب للطفولة المبكرة ببريدة - بنات | Ruqayyah Bint Umar Ibn Al-Khattab Early Childhood School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.320502031242786, 43.960034788361135 | KFM2020660196042 | 10041403461 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1157 | الثانوية السابعة والعشرون ببريدة - مسارات - بنات | 27th Secondary School in Buraydah - Tracks - Girls | Secondary | Girls | Qassim | Buraidah | 26.309048815217224, 44.04020573068891 | KFM2020660194383 | 10090557873‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1158 | مدرسة المتنبي الثانوية | Al-Mutanabbi Secondary School | Secondary |  | Qassim | Buraidah | 26.39046529480199, 43.965816142276786 | KFM2120660235942 | 10041810520 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1159 | المدرسة الابتدائية السادسة والخمسون | 56th Elementary School | Primary |  | Qassim | Buraidah | 26.319217421252738, 44.04450267365488 | KFM2020660195604 | 10041498920 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1160 | المدرسة الابتدائية الحادية والثلاثون | 31st Elementary School | Primary |  | Qassim | Buraidah | 26.3084281394196, 44.03986656308734 | KFM2020660196167 | 10090561651 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1161 | المتوسطة الثانية والخمسون ببريدة - بنات | 52nd Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.331229950756892, 44.05837297916552 | SMR2420661039343 | 10041559088 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1162 | روضة زينب بنت محمد صلى الله عليه وسلم ببريدة - بنات | Zainab Bint Muhammad Kindergarten in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.380026933531184, 43.91397443543868 | KFM2020660204692 | 10088606246 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1163 | ابتدائية محمد بن سيرين | Muhammad Ibn Sirin Elementary School | Primary |  | Qassim | Buraidah | 26.31785624058549, 44.04114466821593 | KFM2120660248043 | 10089311333 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1164 | ثانوية الوطن - مسارات | Al-Watan Secondary School - Tracks | Secondary |  | Qassim | Buraidah | 26.30274680977106, 44.0175897451034 | KFM2120660304270 | 10101830521 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1165 | سناء السلمية الطفولة المبكرة | Sanaa Al-Salmi Early Childhood | Primary |  | Qassim | Buraidah | 26.270286461704664, 43.99027734407149 | KFM2020660194794 | 10041772948‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1166 | ابتدائية أبي بن كعب الأنصاري لتحفيظ القرآن الكريم | Ubayy ibn Ka'b al-Ansari Elementary School for Quran Memorization | Primary |  | Qassim | Buraidah | 26.330230761522508, 44.010021460072316 | KFM2120660287945 | 10041846729 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1167 | الثانوية الاولى ببريدة - مقررات - بنات | First Secondary School in Buraydah - Curriculum - Girls |  | Girls | Qassim | Buraidah | 26.335699416553183, 43.99177432691168 | KFM2120660303663 | 10041308936‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1168 | ياقوت الحموي | Yaqut al-Hamawi |  |  | Qassim | Buraidah | 26.310286352210124, 43.94257004166242 | KFM2120660273068 | 10041750154‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1169 | متوسطة ابن خلدون | Ibn Khaldun Intermediate School | Intermediate |  | Qassim | Buraidah | 26.3169865751678, 43.95802462374882 | KFM2020660211718 | 10041181471‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1170 | مدرسة المنصورية | Al-Mansuriyah School |  |  | Qassim | Buraidah | 26.310202643805948, 43.942044355819434 | KFM2020660195285 | 10041750280‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1171 | ابتدائية ربيعة بن كعب | Rabia ibn Ka'b Elementary School | Primary |  | Qassim | Buraidah | 26.329293794958925, 43.95442932854958 | KFM2020660195360 | 10041840126‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1172 | مجمع القيروان التعليمي ببريدة -القسم المتوسط- بنين | Al-Qayrawan Educational Complex in Buraydah - Intermediate Section - Boys | Intermediate | Boys | Qassim | Buraidah | 26.396006689050985, 43.93224591774332 | KFM2020660187335 | 10041470339 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1173 | الثانوية الخامسة ببريدة - بنات | Fifth Secondary School in Buraydah - Girls | Secondary | Girls | Qassim | Buraidah | 26.373321967814764, 43.977363442327764 | SMR2420661039454 | 10041964357 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1174 | الثانوية الثالثة والعشرون ببريدة -بنات | Twenty-Third Secondary School in Buraydah - Girls | Secondary | Girls | Qassim | Buraidah | 26.387652441583597, 43.935140915344455 | SMR2420661040092 | 10041789972‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1175 | مدرسة حليمة السعدية لتحفيظ القرآن الكريم - بنات | Halima al-Sa'diyya School for Quran Memorization - Girls |  | Girls | Qassim | Buraidah | 26.38119645340258, 43.92634608465554 | KFM2020660187460 | 10041511567 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1176 | المتوسطة التاسعة والاربعون ببريدة - بنات | Forty-Ninth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.39120173164096, 43.95456343886928 | KFM2020660198549 | 10041862366‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1177 | الثانوية الثالثة والثلاثون ببريدة - مقررات - بنات | Thirty-Third Secondary School in Buraydah - Curriculum - Girls | Secondary | Girls | Qassim | Buraidah | 26.346858039286957, 43.965770933349816 | KFM2020660204867 | 10041905937‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1178 | المتوسطة الثانية عشر ببريدة - بنات | Twelfth Intermediate School in Buraydah - Girls | Intermediate | Girls | Qassim | Buraidah | 26.379229287133114, 43.97073625795757 | KFM2120660287896 | 10103728508‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1179 | الابتدائية الثالثة والعشرون ببريدة - بنات | Twenty-Third Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.327304351958116, 43.955545157672226 | KFM2020660204675 | 10041920343 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1180 | الابتدائية السادسة والاربعون ببريدة -بنات | Forty-Sixth Elementary School in Buraydah - Girls | Primary | Girls | Qassim | Buraidah | 26.36971017442387, 43.93595169814721 | KFM2020660204747 | 10041225047‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1181 | ابتدائية الحسن البصري | Al-Hasan al-Basri Elementary School | Primary |  | Qassim | Buraidah | 26.35822820886655, 43.97341198650834 | SMR2220661019889 | 10041901938‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1182 | ابتدائية الزبير بن العوام | Al-Zubayr ibn al-Awam Elementary School | Primary |  | Qassim | Buraidah | 26.34881134109138, 43.990224973016666 | KFM2020660205312 | 10041181597‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1183 | ابتدائية الشيخ صالح الخريصي | Sheikh Saleh al-Khuraisi Elementary School | Primary |  | Qassim | Buraidah | 26.341584711040777, 43.97735656931109 | KFM2120660235930 | 10041712135‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1184 | عوق سمعي ابتدائية معهد الامل للصم | Al-Amal Institute for the Deaf Elementary School (Hearing Impairment) | Primary |  | Qassim | Buraidah | 26.352575272597374, 43.96518324102187 | KFM2020660205334 | 10041988724 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1185 | ابتدائية الشيخ صالح العمري | Sheikh Saleh al-Amri Elementary School | Primary |  | Qassim | Buraidah | 26.389509899065413, 43.93115424287386 | KFM2020660187301 | 10041810403‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1186 | متوسطة علي الحصين | Ali al-Husayn Intermediate School | Intermediate |  | Qassim | Buraidah | 26.389404180022495, 43.93113278520163 | KFM2020660187303 | 10041810271‪ |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1187 | عبدالملك بن مروان | Abdulmalik bin Marwan |  |  | Qassim | Buraidah | 26.371093484260633, 43.90132838465555 | SMR2220661012378 | 10041778899 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1188 | ثانوية الريان مقررات | Al-Rayyan Secondary School (Curriculum) | Secondary |  | Qassim | Buraidah | 26.4073285178253, 43.91474572698332 | KFM2120660238462 | 10041865742 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1189 | ثانوية مجمع صالح بن علي العثيم | Saleh bin Ali Al-Othaim Complex Secondary School | Secondary |  | Qassim | Buraidah | 26.427907814385815, 43.88312484047497 | SMR24206610339400 | 10106559258 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1190 | مدرسة الأمير فيصل بن مشعل بن سعود الثانوية - مسارات | Prince Faisal bin Mishaal bin Saud Secondary School (Pathways) | Secondary |  | Qassim | Buraidah | 26.374387290053946, 43.92410432142493 | SMR2220661012006 | 10104426010 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1191 | ابتدائية سهيل بن عمرو | Suhayl bin Amr Elementary School | Primary |  | Qassim | Buraidah | 26.32406152299356, 44.04229607116389 | KFM2120660301070 | 10082602974 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1192 | ثانوية ابن رشد - مسارات | Ibn Rushd Secondary School (Pathways) | Secondary |  | Qassim | Buraidah | 26.349443439979897, 43.990259469858024 | KFM2020660205314 | 10041511816 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1193 | ثانوية أبي أيوب الأنصاري ببريدة - مسارات | Abu Ayyub Al-Ansari Secondary School in Buraidah (Pathways) | Secondary |  | Qassim | Buraidah | 26.337589024094505, 43.97685203068891 | KFM2020660204809 | 10041262363 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1194 | ابتدائية طارق بن زياد | Tariq bin Ziyad Elementary School | Primary |  | Qassim | Buraidah | 26.334850176655724, 43.96485239999999 | KFM2020660204570 | 10041515673 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1195 | ثانوية القيروان - مسارات | Al-Qayrawan Secondary School (Pathways) | Secondary |  | Qassim | Buraidah | 26.3964142337164, 43.931974925130525 | KFM2020660193849 | 10082579811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1196 | الابتدائية الخامسة لتحفيظ القرآن الكريم - بنات | Fifth Elementary School for Quran Memorization (Girls) | Primary | Girls | Qassim | Buraidah | 26.381190614313844, 43.92680661377689 | KFM2020660187459 | 10041511683 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1197 | المدرسة العشرون الثانوية | Twentieth Secondary School | Secondary |  | Qassim | Buraidah | 26.352575272597374, 43.96518324102187 | KFM2120660272645 | 10041622323 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1198 | الابتدائية الخمسون - بنات | Fiftieth Elementary School (Girls) | Primary | Girls | Qassim | Buraidah | 26.38110612278998, 43.92789818650834 | KFM2020660204723 | 10041622403 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1199 | مدرسة شهداء الوطن الابتدائية | Martyrs of the Nation Elementary School | Primary |  | Qassim | Buraidah | 26.41076768146228, 43.91398131534446 | KFM2020660194150 | 10093225367 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-QAS1200 | المدرسة الابتدائية رقم 100 - للبنات | Elementary School No. 100 (Girls) | Primary | Girls | Qassim | Buraidah | 26.410815726691098, 43.91398131534446 | KFM2020660194149 | 10093222543 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
[29 empty] | 0 | 0 | 0 | 0
[11 empty] | Total | Completed | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 0
[12 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on L4: 4/2/2025
Note on M4: 4/2/2025

## Jeddah Schools -1
|  | Report Date | 2026-04-29
Project | Schools Information | [11 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordinates |  | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Jeddah-1 | SS-ZAM-JAD1001 | الثامنة لتحفيظ القران الكريم المتوسطة بنات | 8th Intermediate School for Quran Memorization | Intermediate | Girls | Jeddah | Jeddah |  | 21.42535287076525, 39.278084739411824 | ALH2020807325594 | 10053648903 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | Primary | Boys | Not Started
| SS-ZAM-JAD1002 | الثامنة والسبعون بعد المائة الابتدائية بنات | 178th Elementary School (Girls) | Primary | Girls | Jeddah | Jeddah |  | 21.50666285474217, 39.24466037301576 | ECC2020807599181 | 10053592737 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | Intermediate | Girls | In Progress
| SS-ZAM-JAD1003 | الرابعة والستون المتوسطة بنات | 64th Intermediate Girls' School | Intermediate | Girls | Jeddah | Jeddah |  | 21.63949018299976, 39.140628800270605 | HLY2020627003699 | 10053133242 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | Secondary | NA | Completed
| SS-ZAM-JAD1004 | الثانوية الرابعة والخمسون بنات | 54th Secondary Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.560089212346835, 39.216858949936515 | HLY2020627003833 | 10053317849 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed | NA |  | NA
| SS-ZAM-JAD1005 | الابتدائية الثانية بعد المائتان بنات | 202nd Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.575828359614718, 39.24155684766391 | HLY2020627005693 | 10053132648 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1006 | التاسعة والاربعون الثانوية بنات | 49th Girls' Secondary School | Secondary | Girls | Jeddah | Jeddah |  | 21.424692343605173, 39.27841114376472 | HLY2020627005694 | 10053132085 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1007 | اسيد بن حضير الابتدائية بنين | Asid ibn Hudair Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.59827031573613, 39.18806790858684 | HLY2020627018456 | 10053213067 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1008 | الثانوية الثالثة بنات | 3rd Secondary School (Girls) | Secondary | Girls | Jeddah | Jeddah |  | 21.506730438830758, 39.267978582286595 | HLY2020627019358 | 10053710115 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1009 | ابي بن كعب الابتدائية | Ubayy bin Ka'b Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.552693196921954, 39.157394761012895 | HLY2020627020235 | 10053646856 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1010 | التاسعة والثلاثون بعد المائة الابتدائية | 139th Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.59813535331344, 39.11702554075731 | HLY2020627020500 | 10020640885 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1011 | الخامسة والستون الثانوية بنات | 65th Secondary Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.610250939085905, 39.12354300570797 | HLY2020627020519 | 10020641078 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1012 | الخامسة والستون المتوسطة بنات | 65th Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.424176483076934, 39.27844348932514 | HLY2020627020520 | 10020640983 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1013 | الاربعون الثانوية بنات | 40th Girls' Secondary School | Secondary | Girls | Jeddah | Jeddah |  | 21.560459515369512, 39.147618895071325 | HLY2020627020697 | 10053390061 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1014 | السادسة والاربعون بعد المائة الابتدائية بنات | 146th Elementary School for Girls | Primary | Girls | Jeddah | Jeddah |  | 21.425598094908654, 39.28756164579717 | HLY2020627020699 | 10053389848 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1015 | الرابعة والثلاثون بنات | Thirty-Fourth Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.56160967337708, 39.145662390086855 | HLY2020627020747 | 10053135597 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1016 | الحديثة المتوسطة | Al-Haditha Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.506651479300377, 39.24514885103089 | HLY2020627022754 | 10053530823 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1017 | الثامنة والستون الثانوية بنات | 68th Secondary Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.554474208285825, 39.21952647077909 | HLY2020627022915 | 10053201951 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1018 | الخامسة عشر لتحفيظ القران الابتدائية بنات | 15th Girls' Elementary Quran Memorization School | Primary | Girls | Jeddah | Jeddah |  | 21.551943574748478, 39.21086544255789 | HLY2020627023144 | 10053208272 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1019 | الواحدة والستون بعد المائة الابتدائية بنات | 161st Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.57614633534001, 39.24156184736687 | HLY2020627023454 | 10053206330 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1020 | السبعون الابتدائية بنات | 70th Elementary School (Girls) | Primary | Girls | Jeddah | Jeddah |  | 21.596419110676834, 39.25610796097727 | HLY2020627023500 | 10053408925 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1021 | صقر قريش الابتدائية بنين | Saqr Quraish Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.53872835991483, 39.19319748936972 | HLY2020627023540 | 10053714769 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1022 | الثانية والخمسون الثانوية بنات | 52nd Secondary Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.604490452417313, 39.26328462349587 | HLY2020627024119 | 10053467846 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1023 | فلسطين الثانوية-مقررات بنين | Palestine Secondary School - Boys' Curriculum | Secondary | Girls | Jeddah | Jeddah |  | 21.644928728462652, 39.13176400510993 | HLY2020627024611 | 10053237541 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1024 | ابن راشد الابتدائية بنين | bn Rashid Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.598250321400386, 39.171144876335056 | HLY2020627024616 | 10053531437 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1025 | الثانية والثمانون بعد المائة الابتدائية بنات | 182nd Elementary School for Girls | Primary | Girls | Jeddah | Jeddah |  | 21.579054572619256, 39.22027006122693 | HLY2020627024920 | 10053651382 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1026 | الرابعة والثمانون المتوسطة بنات | 84th Girls' Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.530798443917128, 39.2146532457651 | HLY2020627025034 | 10053651776 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1027 | السادسة والعشرون بعد المائة الابتدائية بنات | 126th Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.59736080586172, 39.237756373578954 | HLY2020627025232 | 10053131954 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Revisit | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1028 | عبدالرحمن الداخل الثانوية مقررات بنين | Abdul Rahman Al-Dakhil Secondary School (Boys' Curriculum) | Secondary | Girls | Jeddah | Jeddah |  | 21.516185556949527, 39.22516633559665 | HLY2020627025514 | 10053625481 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1029 | ابي بكر الصديق الابتدائية بنين | Abi Bakr Al-Siddiq Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.56509753018709, 39.16606646682261 | HLY2020627025790 | 10053652129 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1030 | النموذجية السابعة الابتدائية بنين | Seventh Model Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.428442451873273, 39.28020401780569 | HLY2020627035525 | 10053138051 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1031 | الرياض الابتدائية بنين | Riyadh Advanced Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.581818584403763, 39.23331146167482 | HLY2020627042137 | 10053394285 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1032 | المسعودي المتوسطة | Al-Masoudi Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.57822532095659, 39.15032248442079 | HLY2020627043074 | 10053288184 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1033 | الابتدائية الواحد والسبعون بعد المائة بنات | 171st Elementary School (Girls) | Primary | Girls | Jeddah | Jeddah |  | 21.583695016181007, 39.244525851918105 | HLY2020627044687 | 10053648215 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1034 | النموذجية السادسة الابتدائية بنين | 6th Model Elementary Boys' School | Primary | Girls | Jeddah | Jeddah |  | 21.576850928293894, 39.21158004501332 | HLY2020627049760 | 10053210682 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1035 | الثامنة عشر المتوسطة بنات | 18th Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.552393645312552, 39.21123885425462 | HLY2020627053586 | 10053238208 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1036 | الثمانون الابتدائية بنات | 80th Elementary Girls' School | Primary | Girls | Jeddah | Jeddah |  | 21.578725691679708, 39.146940033538236 | HLY2020627053686 | 10053258935 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1037 | التاسعة والسبعون الابتدائية بنات | 79th Elementary School for Girls | Primary | Girls | Jeddah | Jeddah |  | 21.569738430096425, 39.2140688 | HLY2020627054741 | 10053131257 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1038 | خالد بن الوليد الثانوية بنين | Khalid bin Al-Walid Secondary School for Boys | Secondary | Girls | Jeddah | Jeddah |  | 21.589089137932593, 39.135584366094264 | HLY2020627054743 | 10053319941 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1039 | محمد بن علي بن ابي طالب المتوسطة بنين | Muhammad ibn Ali ibn Abi Talib Intermediate School for Boys | Intermediate | Girls | Jeddah | Jeddah |  | 21.57784515440266, 39.1880696601529 | HLY2020627054745 | 10053262811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1040 | الاولى الابتدائية بنات | First Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.59247761531529, 39.19938347468122 | HLY2020627055402 | 10053200800 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1041 | الثالثة والثلاثون الابتدائية بنات | The 33rd Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.50748273681918, 39.26785847011936 | HLY2020627056008 | 10053385231 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1042 | الثالثة والثلاثون المتوسطة بنات | 33rd Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.424518614883844, 39.285675053727836 | HLY2020627056071 | 10053321313 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1043 | الخيف الابتدائية بنين | Al-Khaif Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.51633576627835, 39.170787840928355 | HLY2020627056156 | 10053505212 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1044 | عمير بن سعد الابتدائية بنين | Omair bin Saad Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.50675690244847, 39.24391424840258 | HLY2020627056341 | 10053214000 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1045 | مجمع الامير سلطان الثانوي-مقررات بنين | Prince Sultan Secondary School Complex - Boys' Curriculum | Secondary | Girls | Jeddah | Jeddah |  | 21.552418284480353, 39.157725210058395 | HLY2020627056744 | 10053173641 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1046 | الثالثة عشر الثانوية بنات | 13th Secondary School - Girls | Secondary | Girls | Jeddah | Jeddah |  | 21.592686718852868, 39.20027808268621 | HLY2020627056753 | 10053706195 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1047 | الثالثة بعد المائة المتوسطة بنات | 103rd Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.58209908480871, 39.23422689994772 | HLY2020627057212 | 10053390320 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1048 | الخامسة لتحفيظ القران الابتدائية بنات | 5th Girls' Primary School for Quran Memorization | Primary | Girls | Jeddah | Jeddah |  | 21.559744080970894, 39.21626448754173 | HLY2020627057450 | 10053711954 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1049 | الثانية عشر لتحفيظ القران الكريم الابتدائية بنات | Twelfth Elementary School for Quran Memorization | Primary | Girls | Jeddah | Jeddah |  | 21.586613773711424, 39.19188826300827 | HLY2020627057766 | 10053709400 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1050 | ام القرى الثانوية مقررات بنين | Umm Al-Qura Secondary School - Boys' Curriculum | Secondary | Girls | Jeddah | Jeddah |  | 21.57267613688156, 39.17392370884049 | HLY2020627057783 | 10053626773 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1051 | ابي سفيان الابتدائية بنين | Abi Sufyan Elementary School (Boys) | Primary | Girls | Jeddah | Jeddah |  | 21.4237677801856, 39.278629222508236 | HLY2020627057792 | 10053625088 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1052 | مجمع الامير سلطان الابتدائية بنين | Prince Sultan Elementary School Complex for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.575938344867264, 39.210816170673404 | HLY2020627057914 | 10053170854 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1053 | الثلاثون الابتدائية بنات | 30th Elementary Girls' School | Primary | Girls | Jeddah | Jeddah |  | 21.598359081371928, 39.23731305214666 | HLY2020627058868 | 10053113553 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1054 | الثالثة والستون المتوسطة بنات | 63rd Intermediate Girls' School | Intermediate | Girls | Jeddah | Jeddah |  | 21.583702342372998, 39.24543665186221 | HLY2020627058870 | 10053113713 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1055 | الثامنة والخمسون بعد المائة الابتدائية بنات | 158th Elementary School for Girls | Primary | Girls | Jeddah | Jeddah |  | 21.58129417104225, 39.233745404973774 | HLY2020627058877 | 10053350370 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1056 | التاسعة بعد المائة الثانوية بنات | 109th Secondary School for Girls | Secondary | Girls | Jeddah | Jeddah |  | 21.610719099611423, 39.12284809669406 | HLY2020627058878 | 10053350638 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1057 | التاسعة والتسعون المتوسطة بنات | 99th Intermediate Girls' School | Intermediate | Girls | Jeddah | Jeddah |  | 21.610638800179284, 39.124005369057784 | HLY2020627058884 | 10053212570 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1058 | الاحنف بن قيس الثانوية - مقررات بنين | Al-Ahnaf Bin Qais Secondary School - Boys' Curriculum | Secondary | Girls | Jeddah | Jeddah |  | 21.57926583323074, 39.2212262153603 | HLY2020627058931 | 10053350647 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1059 | الامام فيصل بن تركي المتوسطة بنين | Imam Faisal bin Turki Intermediate School for Boys | Intermediate | Girls | Jeddah | Jeddah |  | 21.515010858662222, 39.235030812667354 | HLY2020627059108 | 10053527819 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1060 | الثامنة والعشرون بعد المائة الابتدائية بنات | 128th Girls' Primary School | Primary | Boys | Jeddah | Jeddah |  | 21.554844222705608, 39.17707908768633 | HLY2020627059240 | 10053691978 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1061 | الثلاثون المتوسطة بنات | 30th Intermediate Girls' School | Intermediate | Girls | Jeddah | Jeddah |  | 21.538716270296433, 39.213873523588674 | HLY2020627059601 | 10053712639 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1062 | الثانية والثلاثون الثانوية بنات | 32nd Secondary Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.59847822649542, 39.18502182720388 | HLY2020627059604 | 10053236544 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1063 | الخامسة لتحفيظ القران المتوسطة بنات | Fifth Quran Memorization Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.559850975732928, 39.21748854729422 | HLY2020627059605 | 10053712129 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1064 | السابعة والعشرون الثانوية بنات | 27th Secondary School for Girls | Secondary | Girls | Jeddah | Jeddah |  | 21.58867279273942, 39.17830986889433 | HLY2020627059914 | 10053709858 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1065 | ابي الدرداء الابتدائية بنين | Abi Al-Darda Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.43045864825561, 39.274510088359605 | HLY2020627060063 | 10053113212 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1066 | مجمع الامير سلطان المتوسطة بنين | Prince Sultan Intermediate School Complex for Boys | Intermediate | Girls | Jeddah | Jeddah |  | 21.58770205671012, 39.20199061209167 | HLY2020627060556 | 10053172429 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1067 | الامام ورش المتوسطة لتحفيظ القرآن | Imam Warsh Intermediate Quran Memorization School | Intermediate | Girls | Jeddah | Jeddah |  | 21.597666442217275, 39.23782345768177 | HLY2020627061825 | 10053714099 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1068 | مجمع السلامة المتوسط | Al-Salamah Intermediate Complex | Intermediate | Girls | Jeddah | Jeddah |  | 21.54703069209348, 39.188135320162026 | HLY2020627061964 | 10053712700 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1069 | مجمع السلامة الثانوي بنين | Al-Salamah Secondary Complex for Boys | Secondary | Girls | Jeddah | Jeddah |  | 21.597370054040525, 39.117001151647116 | HLY2020627061965 | 10053712531 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1070 | الملك فهد المتوسطة بنين | King Fahd Intermediate School for Boys | Intermediate | Girls | Jeddah | Jeddah |  | 21.55216240946272, 39.15717366745189 | HLY2020627062491 | 10053529635 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1071 | الثانية والثلاثون المتوسطة بنات | 32nd Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.51555408222381, 39.225244320562524 | HLY2020627063018 | 10053647764 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1072 | قريش الثانوية-مقررات بنين | Quraish Secondary School - Boys' Curriculum | Secondary | Girls | Jeddah | Jeddah |  | 21.599047756856475, 39.18465872883595 | HLY2020627063176 | 10053108311 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1073 | ابتدائية تحفيظ القران العاشرة | Quran memorization Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.57533926314164, 39.211107306031664 | HLY2020627063272 | 10053765599 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1074 | الطفولة المبكرة بإبتدائية النموذجية الرابعة | Early Childhood at the Fourth Model Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.57546155371973, 39.18781684642394 | HLY2020627064656 | 10085371923 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1075 | عمر بن الخطاب الابتدائية بنين | Omar Ibn Al-Khattab Elementary School - Boys | Primary | Girls | Jeddah | Jeddah |  | 21.561329379618204, 39.14561462370335 | HLY2020627064974 | 10053180977 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1076 | النموذجية الثانية الابتدائية بنين | Second Model Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.591757035019086, 39.2474438985829 | HLY2020627065020 | 10053625883 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1077 | معهد الأمل الاول الابتدائية بنات | Al-Amal Institute for Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.598800012572855, 39.18415431278309 | HLY2020627065500 | 10053316181 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1078 | الواحدة والثلاثون المتوسطة بنات | 31st Intermediate School - Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.59570915034245, 39.25583706623214 | HLY2020627065742 | 10053316064 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1079 | ابن الجزري لتحفيظ القرآن الابتدائية بنين | Ibn Al-Jazari Elementary School for Quran Memorization | Primary | Boys | Jeddah | Jeddah |  | 21.53281298027523, 39.21363395582021 | HLY2020627065769 | 10053259979 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1080 | السابعة والخمسون الابتدائية بنات | Fifty-Seventh Elementary School for Girls | Primary | Boys | Jeddah | Jeddah |  | 21.513684855143254, 39.18402318351992 | HLY2020627065819 | 10053531849 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1081 | الثانوية السادسة بعد المائة بنات | 106th Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.499197425944175, 39.26948246507881 | KFM2120655005201 | 10105075840 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1082 | الابتدائية الثامنة والستون بعد المائة بنات | 168th Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.55393612264518, 39.18141402388402 | KFM2120655005300 | 10105075831 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1083 | الامير تركي بن عبدالعزيز المتوسطة بنين | Prince Turki Bin Abdulaziz Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.82751731788642, 39.21346817417674 | MMF2420601011977 | 10053263327 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1084 | ثانويه الخمره الاولى | Al-Khumra First Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.524116092114564, 39.17528550803432 | MMF2420601021801 | 10106082025 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1085 | طيبة الابتدائية بنات | Tayyiba Elementary School for Girls | Primary | Boys | Jeddah | Jeddah |  | 21.532400224510617, 39.21395009843525 | MMF2420601023044 | 10053452093 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Pending | Pending | Pending | Completed |  | 0 | 0 | 11 | In Progress
| SS-ZAM-JAD1086 | مدرسة شداد بن أوس | Shaddad ibn Aws School | Secondary | Boys | Jeddah | Jeddah |  | 21.398659603157, 39.2744145 | SMR2220621002446 | 10104396752 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Pending | Pending | Completed | Completed |  | 0 | 0 | 12 | In Progress
| SS-ZAM-JAD1087 | مدرسة الليث بن سعد المتوسطة بنين | Al-Layth ibn Saad Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.4710438764672, 39.21895021415652 | SMR2220621010146 | 10105356359 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1088 | ب سعد بن الربيع للبنين بحي المروة | Saad ibn Rabi’ School for Boys in Al-Marwa District | Primary | Boys | Jeddah | Jeddah |  | 21.467440417385177, 39.272687540167915 | SMR2220621010163 | 10105376478 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1089 | مدرسة بدر الابتدائية بنين | Badr Elementary School for Boys | Primary | Boys | Jeddah | Jeddah |  | 21.58926754768365, 39.24574558962175 | SMR2220621010276 | 10105348867 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Pending | Pending | Completed | Completed |  | 0 | 0 | 12 | In Progress
| SS-ZAM-JAD1090 | مدرسة ابي تمام الابتدائية | Abi Tamam Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.605282042172412, 39.14958100023514 | SMR2220621010314 | 10105349640 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1091 | الابتدائية الثانية للطفولة المبكرة لتحفيظ القران | Second Elementary School for Early Childhood (Tuhaf) |  | Boys | Jeddah | Jeddah |  | 21.428386358414524, 39.28731534712628 | SMR2420621021062 | 10053573188 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1092 | السابعة والعشرون الابتدائية بنات | Twenty-seventh Elementary School for Girls | Primary | Boys | Jeddah | Jeddah |  | 21.55826791300435, 39.22046431821793 | SXE2120627088089 | 10053237274 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1093 | التسعون الابتدائية بنات | Ninetyth Elementary School for Girls | Primary | Boys | Jeddah | Jeddah |  | 21.578137757099903, 39.22652110024884 | SXE2120627088124 | 10053264988 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1094 | الرابعة عشر تحفيظ القران الابتدائية بنات | 14th Quran Memorization Elementary Girls' School | Primary | Boys | Jeddah | Jeddah |  | 21.441179382266267, 39.252734736879084 | SXE2120627088128 | 10053757891 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1095 | الامير سعود بن عبدالمحسن الابتدائية بنين | Prince Saud bin Abdulmohsen Elementary School for Boys | Primary | Boys | Jeddah | Jeddah |  | 21.495091622234536, 39.2855537 | SXE2120627088131 | 10053345816 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1096 | عثمان بن عفان الثانوية-مقررات بنين | Uthman Bin Affan Secondary School (Boys) | Secondary | Boys | Jeddah | Jeddah |  | 21.57780440089447, 39.20288046322709 | SXE2120627090133 | 10053178567 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1097 | ابن خلدون الثانوية-مقررات بنين | Ibn Khaldoun Secondary School (Boys' Curriculum) | Secondary | Boys | Jeddah | Jeddah |  | 21.573374223745446, 39.22762493001228 | SXE2120627090183 | 10053760421 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1098 | الابتدائية التاسعة والثمانون بنات | Eighty-ninth Elementary School for Girls | Primary | Boys | Jeddah | Jeddah |  | 21.331148965177068, 39.24391911869605 | SXE2120627099420 | 10053345852 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1099 | الحادية والتسعون الابتدائية بنات | 91st Girls' Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.81716431267627, 39.21078972675981 | SXE2120627099456 | 10053713251 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1100 | الثامنة والسبعون الثانوية بنات | 78th Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.548957873615176, 39.22143821349212 | SXE2120627099825 | 10053713206 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1101 | السابعة بعد المائة الابتدائية بنات | 107th Elementary School for Girls | Primary | Boys | Jeddah | Jeddah |  | 21.56481702276333, 39.20456 | SXE2120627099828 | 10053713055 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1102 | رضوى الثانوية-مقررات بنين | Radwa Secondary School (Curriculum-Based) for Boys | Secondary | Boys | Jeddah | Jeddah |  | 21.476660231897128, 39.18572451673874 | SXE2120627099928 | 10053178487 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1103 | السابعة والثلاثون المتوسطة بنات | 37th Intermediate School for Girls | Intermediate | Boys | Jeddah | Jeddah |  | 21.62689897156436, 39.157584909794515 | SXE2120627099930 | 10053588411 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1104 | عمر بن الخطاب الثانوية-مقررات بنين | Omar Bin Al-Khattab Secondary School - Boys' Curriculum | Secondary | Girls | Jeddah | Jeddah |  | 21.554051853579235, 39.21916547930759 | SXE2120627099934 | 10053131060 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1105 | السابعة والاربعون الثانوية بنات | 47th Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.494827057891964, 39.286141104186065 | SXE2120627099935 | 10053473281 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1106 | عبدالله بن مسعود الابتدائية بنين | Abdullah Ibn Masoud Elementary School for Boys | Primary | Boys | Jeddah | Jeddah |  | 21.601954359450563, 39.152957231131 | SXE2120627099941 | 10101190727 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1107 | الخامسة والثمانون الثانوية بنات | 85th Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.60183628129855, 39.15317998650788 | SXE2120627100980 | 10053199521 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1108 | معهد النور الابتدائية بنات | Al-Nour Elementary Institute - Girls | Primary | Boys | Jeddah | Jeddah |  | 21.477480429380808, 39.232655989577026 | SXE2120627101051 | 10053757757 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1109 | المروة المتوسطة بنين | Al-Marwa Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.558734939599987, 39.15970886727821 | SXE2120627101055 | 10053706408 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1110 | ابن حبان الثانوية-مقررات بنين | Ibn Hibban Secondary School (Boys' Curriculum) | Secondary | Boys | Jeddah | Jeddah |  | 21.547982852552792, 39.18246826976779 | SXE2120627101072 | 10053571998 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1111 | المتوسطة التاسعة والثمانون بنات | 89th Intermediate School - Girls | Intermediate | Boys | Jeddah | Jeddah |  | 21.571427397306202, 39.217567156440104 | SXE2120627101077 | 10053134277 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1112 | الخامسة والثمانون بعد المائة الابتدائية بنات | 185th Elementary School (Girls) | Primary | Boys | Jeddah | Jeddah |  | 21.570722969920087, 39.213663005701484 | SXE2120627101103 | 10053134508 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1113 | اسد بن الفرات المتوسطة بنين | Asad Ibn Al-Furat Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.580860599190785, 39.17091864127639 | SXE2120627101158 | 10083126409 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1114 | الاقصى المبارك المتوسطة بنين | Al-Aqsa Al-Mubarak Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.8415356257404, 39.22800999109642 | SXE2120627101187 | 10053346635 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1115 | الخمسون المتوسطة بنات | 50th Girls' Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.507613567545658, 39.18542985578544 | SXE2120627101218 | 10053714132 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1116 | الواحدة والاربعون الثانوية بنات | 41st Girls' Secondary School | Secondary | Girls | Jeddah | Jeddah |  | 21.55119624398151, 39.16893636328163 | SXE2120627102028 | 10053409360 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1117 | الابتدائية السابعة والثمانون بنات | 87th Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.61739791793998, 39.16428859314325 | SXE2120627102030 | 10053409092 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1118 | السادسة والستون بعد المائة الابتدائية بنات | 166th Girls' Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.475453652675125, 39.236879475461485 | SXE2120627102034 | 10053593897 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1119 | التاسعة لتحفيظ القران الكريم المتوسطة بنات | 9th Intermediate School for Quran Memorization for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.53197446308883, 39.215631581533046 | SXE2120627102035 | 10053209734 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1120 | عقبة بن نافع الابتدائية بنين | Uqba ibn Nafi' Primary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.454031561358818, 39.25550318834326 | SXE2120627102107 | 10020647198 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1121 | شيبة بن عثمان الابتدائية بنين | Shaybah ibn Uthman Elementary School for Boys | Primary | Girls | Jeddah | Jeddah |  | 21.551997230227965, 39.21086389237624 | SXE2120627102116 | 10053694826 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1122 | الزهراوي الثانوية-مقررات بنين | Al-Zahrawi Secondary School (Boys' Curriculum) | Secondary | Boys | Jeddah | Jeddah |  | 21.527007880443076, 39.19122741349212 | SXE2120627102122 | 10053261224 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1123 | ابن منظور الثانوية مقررات بنين | Ibn Manzur Secondary School (Boys) | Secondary | Girls | Jeddah | Jeddah |  | 21.576093643996348, 39.21167100742992 | SXE2120627102141 | 10053183342 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1124 | الامير سلطان بن عبدالعزيز المتوسطة | Prince Sultan bin Abdulaziz Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.55156308758046, 39.178607153968485 | SXE2120627102142 | 10053405398 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1125 | معهد التربية الفكرية الابتدائي 1 -بنات | Institute for Intellectual Education (Elementary) 1 - Girls | Primary | Girls | Jeddah | Jeddah |  | 21.50822973956678, 39.16499153888841 | SXE2120627102151 | 10053173758 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1126 | الخامسة والاربعون بعد المائة الابتدائية بنات | 145th Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.522345253272817, 39.18616494256415 | SXE2120627102155 | 10053707281 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1127 | الخامسة والتسعون المتوسطة بنات | 95th Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.50699612787914, 39.180286631744046 | SXE2120627102156 | 10053706856 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1128 | السابعة والعشرون بعد المائة المتوسطة بنات | 127th Intermediate School for Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.52171050674328, 39.1861381694695 | SXE2120627102158 | 10053409664 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1129 | الاولى المتوسطة بنات | First Intermediate School - Girls | Intermediate | Girls | Jeddah | Jeddah |  | 21.475628811125947, 39.23703677941398 | SXE2120627103572 | 10053446283 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1130 | الثامنة والثلاثون المتوسطة بنات | 38th Intermediate Girls' School | Intermediate | Boys | Jeddah | Jeddah |  | 21.52112672220621, 39.23652494564203 | SXE2120627103661 | 10084210955 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1131 | الامير سعود الفيصل المتوسطة | Prince Saud Al-Faisal Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.47697894612232, 39.217631098445345 | SXE2120627103751 | 10053290020 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1132 | عثمان بن عفان الابتدائية بنين | Uthman Bin Affan Elementary School for Boys | Primary | Boys | Jeddah | Jeddah |  | 21.579941898475493, 39.1913018 | SXE2120627104075 | 10053197311 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1133 | السابعة والعشرون بعد المائة الابتدائية بنات | 127th Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.453434662029906, 39.275449467030114 | SXE2120627104321 | 10084219370 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1134 | ابي الاسود الدؤلي المتوسطة بنين | Abi Al-Aswad Al-Du'ali Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.51935735331918, 39.23363689206304 | SXE2120627104322 | 10053148881 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1135 | الابتدائية السبعون بعد المائة بنات | 170th Elementary School - Girls | Primary | Boys | Jeddah | Jeddah |  | 21.53396828811066, 39.18392834030096 | SXE2120627104416 | 10053445123 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1136 | السابعة والسبعون المتوسطة بنات | 77th Girls' Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.543660127477438, 39.20175314232808 | SXE2120627104420 | 10093887792 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1137 | متوسطة ابن كثير بنين | Ibn Kathir Intermediate School - Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.473267684997047, 39.26524826464643 | SXE2120627104438 | 10102758271 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1138 | عرفات الثانوية مقررات بنين | Arafat Secondary School (Curriculum-Based) for Boys | Secondary | Boys | Jeddah | Jeddah |  | 21.57953370122804, 39.24568508797068 | SXE2120627500429 | 10105036270 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1139 | مدرسة ابي عقيل الاولى بنين | Abi Aqil First School for Boys | Primary | Boys | Jeddah | Jeddah |  | 21.610054305365363, 39.18702961950006 | SXE2120627501741 | 10105343987 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Pending | Pending | Completed | Completed |  | 0 | 0 | 12 | In Progress
| SS-ZAM-JAD1140 | علي بن ابى طالب الثانوية-مقررات | Ali Bin Abi Talib Secondary School (Curriculum-Based) | Secondary | Boys | Jeddah | Jeddah |  | 21.57622551504254, 39.21702003601312 | SXE2120627098695 | 10053349708 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1141 | الحطيم الثانوية | Al-Hateem Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.60269660260736, 39.15132046034886 | HLY2020627022262 | 10053242873 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1142 | الثانوية الستون بنات | 60th Secondary Girls' School | Secondary | Girls | Jeddah | Jeddah |  | 21.574259703562298, 39.193101628835954 | HLY2020627004512 | 10053650652 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1143 | الخامسة والثلاثون الابتدائية بنات | 35th Elementary Girls' School | Primary | Boys | Jeddah | Jeddah |  | 21.541320097569635, 39.16354303002492 | HLY2020627003709 | 10053445080 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1144 | السادسة والستون المتوسطة بنات | 66th Intermediate Girls' School | Intermediate | Boys | Jeddah | Jeddah |  | 21.634410314443016, 39.17663561569765 | SEX2120627101154 | 10053645760 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1145 | الثانية و التسعون الابتدائية بنات | 92nd Elementary Girls' School | Primary | Boys | Jeddah | Jeddah |  | 21.555074292855814, 39.166800437455414 | HLY2020627003706 | 10053393813 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1146 | الثالثة لتحفيظ القران الكريم الابتدائية | Third Elementary School for Quran Memorization | Primary | Boys | Jeddah | Jeddah |  | 21.473805128202216, 39.22692760926124 | SXE2120627088163 | 10053132334 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1147 | المدرسة التاسعة ( ٩ ) الابتدائية | 9th Elementary school | Primary | Boys | Jeddah | Jeddah |  | 21.634684537548626, 39.14209586526706 | SXE2120627102164 | 10053649910 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1148 | حكيم بن حزام الابتدائية بنين | Hakim Ibn Hizam Elementary School - Boys | Primary | Boys | Jeddah | Jeddah |  | 21.563745922083953, 39.14781542883595 | HLY2020627002914 | 10053133028 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1149 | عروة بن الزبير الابتدائية | Urwa Ibn Al-Zubayr Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.551784177485207, 39.211747915500084 | HLY2020627021660 | 10053760153 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1150 | المائة بنات | The Hundred Girls | Secondary | Girls | Jeddah | Jeddah |  | 21.595855452530365, 39.256564471573775 | HLY2020627023470 | 10053409682 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1151 | الثانوية الاولى بنات | First Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.582618691948248, 39.21976297249924 | SXE2120627102104 | 10053350594 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1152 | ابن ماجه الابتدائية | Ibn Majah Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.57768704121791, 39.22129584781803 | HLY2020627025455 | 10053196171 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1153 | أحمد بن حنبل الثانوي | Ahmad Ibn Hanbal Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.563838663385866, 39.1793888746726 | SXE2120627103600 | 10053145851 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1154 | مدرسة بن حزم الثانوية | Ibn Hazm Secondary School | Secondary | Girls | Jeddah | Jeddah |  | 21.422971952607917, 39.27852202487179 | SXE2120627099199 | 10102798268 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1155 | إبتدائية الرغامة الأولى | Al-Raghamah First Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.454232867049313, 39.25612788465615 | HLY2020627022261 | 10053471482 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1156 | الابتدائية الثالثة والاربعون بعد المائة | One Hundred and Forty-Third Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.454416012547714, 39.25567360000001 | SMR2320621017807 | 10053237078 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1157 | ثانوية النهروان | Al-Nahrawan Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.52646476324077, 39.190995682761226 | SXE2120627093573 | 10020628405 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1158 | المدرسة الرابعة والستون الثانوية | The Sixty-Fourth Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.5216501297836, 39.227374812384284 | HLY2020627021930 | 10053181348 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Revisit | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1159 | المتوسطة العشرون بعد المئة | 120th Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.52119824732299, 39.22732202472673 | HLY2020627021910 | 10053236375 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1160 | جدة الثانوية | Jeddah Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.511716924005103, 39.23659262173581 | HLY2020627055577 | 10053204596 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending | Pending | Pending | Completed | Completed |  | 0 | 0 | 12 | In Progress
| SS-ZAM-JAD1161 | النموذجية الخامسة الابتدائية | Fifth Model Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.55875403045294, 39.22017004232808 | SEC Room Closed | SEC Room Closed |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1162 | الامام الذهبي المتوسطة بنين | Imam Al-Dhahabi Intermediate School for Boys | Intermediate | Boys | Jeddah | Jeddah |  | 21.575939444153438, 39.24625367521 | SXE2120627102007 | 10053630300 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1163 | طليطلة الثانوية | Toledo Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.591246872662563, 39.14623797301576 | HLY2020627021986 | 10053574050 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1164 | قطبة بن عامر الابتدائية | Qutbah Bin Amer Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.59111718431127, 39.14619505767192 | HLY2020627021604 | 10103014371 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1165 | الحسن بن سفيان الأبتدائية | Al-Hassan Bin Sufyan Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.589368994944323, 39.14686766164389 | SXE2120627104325 | 10053694254 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1166 | محمد بن إدريس الثانوية | Muhammad Bin Idris Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.603640303640095, 39.16530764640993 | HLY2020627024531 | 10053631049 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1167 | بدر الثانوية مقررات بنين | Badr Boys' Secondary School (Curriculum-Based) | Secondary | Boys | Jeddah | Jeddah |  | 21.518254721018224, 39.15862515767192 | HLY2020627052877 | 10053573901 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1168 | الرابعة عشر الثانوية بنات | 14th Secondary School (Girls) | Secondary | Girls | Jeddah | Jeddah |  | 21.518089478040967, 39.15802170000001 | SXE2120627088122 | 10053315183 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1169 | الثامنة والخمسون ابتدائية | The 58th Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.465605454265063, 39.2436848433831 | HLY2020627053681 | 10053236956 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1170 | متوسطة تحفيظ القران السابعة | 7th Quran Memorization Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.570497820028738, 39.217730942448426 | HLY2020627021927 | 10053181811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1171 | الابتدائية الثالثة عشر لتحفيظ القران | 13th Quran Memorization Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.551759771743022, 39.16638489816067 | HLY2020627021977 | 10053236581 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Revisit | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1172 | المتوسطة السابعة والخمسون | 57th Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.61176719065258, 39.19421745382795 | HLY2020627021978 | 10053236811 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1173 | الثامنة والثلاثون ثانوية | 38th Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.54000933439341, 39.18135743967631 | HLY2020627020223 | 10053591972 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1174 | الطفولة المبكرة بابتدائية التضامن الإسل | Early Childhood at Al-Tadhamun Islamic Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.425272620675944, 39.2890216920969 | SMR2220621010101 | 10053214369 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1175 | المدرسة الرابعة الثانوية | Fourth Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.57876319569612, 39.169486437576666 | HLY2020627057726 | 10053349154 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Revisit | Completed |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1176 | المدرسة الثامنة المتوسطة | Eighth Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.55158086546082, 39.168804207326886 | HLY2020627065121 | 10053348406 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1177 | مدرسة مدائن الفهد الثانوية | Madain Al-Fahd Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.581919374363636, 39.15306845141472 | SXE2120627101016 | 10053632206 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1178 | مجمع الثغر الابتدائية | Al-Thaghr Elementary Complex | Primary | Boys | Jeddah | Jeddah |  | 21.6000211915587, 39.189071136301635 | HLY2020627056309 | 10053346985 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1179 | مدرسة ابي عبيده عامر بن الجراح | Abi Ubaidah Amer Ibn Al-Jarrah School | Primary | Boys | Jeddah | Jeddah |  | 21.585089947107875, 39.232636192861634 | SMR2220621002678 | 10105305716 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1180 | الخامسه عشر لرياض الاطفال | Fifteenth Kindergarten |  | Boys | Jeddah | Jeddah |  | 21.429400987135242, 39.285767813492114 |  |  |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1181 | متوسطة الامير بندر | Prince Bandar Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.514899114839746, 39.17926590975094 | SXE2120627104437 | 10053590877 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1182 | ابتدائية الامير بندر | Prince Bandar Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.58835340881647, 39.13480334976551 | SXE2120627104432 | 10053591159 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1183 | مدرسة ابن البيطار | Ibn Al-Baytar School | Secondary | Girls | Jeddah | Jeddah |  | 21.57755147266627, 39.20477165979842 | HLY2020627007066 | 10053446621 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1184 | الثانوية الثالثة بعد المائة | 103 high school | Secondary | Boys | Jeddah | Jeddah |  | 21.56458940070891, 39.16595854882215 | HLY2020627020119 | 10053236141 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1185 | التسعون الثانويه | Ninetyth Secondary School | Secondary | Girls | Jeddah | Jeddah |  | 21.494904290723497, 39.28613990507081 | SXE2120627101999 | 10053209968 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1186 | السادسه والثلاثون المتوسطه | Thirty-Sixth Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.425051013018738, 39.28848817077504 | HLY2020627023235 | 10053209000 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1187 | المغيره بن شعبه الابتدائيه | Al-Mughirah Ibn Shu'bah Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.598135889937097, 39.18752239349395 | HLY2020627030397 | 10053315129 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1188 | مدرسة عكاظ المتوسطه | Ukaz Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.517170554048484, 39.190172554635446 | HLY2020627021293 | 10053625687 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Pending |  | 0 | 0 | 14 | In Progress
| SS-ZAM-JAD1189 | عروة بن مسعود الابتدائيه | Urwah Ibn Mas'ud Elementary School | Primary | Girls | Jeddah | Jeddah |  | 21.596086524311307, 39.25567975767192 | HLY2020627020221 | 10053574363 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1190 | السادسه والثمانون للطفوله المبكره | Eighty-Sixth Early Childhood School |  | Boys | Jeddah | Jeddah |  | 21.421222576977264, 39.29244030026853 | SMR2220621002427 | 10104229871 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1191 | الخامسه بعد المائة ثانويه | One Hundred-Fifth Secondary School | Secondary | Girls | Jeddah | Jeddah |  | 21.57933430518946, 39.149471115690304 | SMR2220621002440 | 10104229861 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1192 | التاسعه عشر بعد المائه المتوسطه | One Hundred-Nineteenth Intermediate School | Intermediate | Girls | Jeddah | Jeddah |  | 21.56991065881775, 39.214470065616105 | SMR2220621000622 | 10104229852 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1193 | المتوسطة السابعة عشر | Seventeenth Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.56418585678875, 39.18949561534383 | HLY2020627056722 | 10053257221 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1194 | الرابعه والتسعون بعد المائه الابتدائيه | 194th Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.464439677689292, 39.227246056629596 | HLY2020627020207 | 10053625749 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1195 | الامين الابتدائيه | Al-Amin Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.579518968339055, 39.16899245767192 | HLY2020627020192 | 10088486710 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1196 | الرابعه والاربعون بعد المائه | 144th Elementary School | Primary | Boys | Jeddah | Jeddah |  | 21.60724852219717, 39.2623139680518 | SMR2420628013471 | 30127749659 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1197 | مدرسة صقلية الثانوية | Sicily Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.42732146157479, 39.28313618326669 | HLY2020627020161 | 10053506471 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1198 | الثالثة والخمسون الثانوية بنات | The 53rd Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.451832618113915, 39.20608261027721 | HLY2020627065040 | 10053586794 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1199 | السادسة والثمانون الثانوية بنات | 86th Girls' Secondary School | Secondary | Boys | Jeddah | Jeddah |  | 21.506318885192712, 39.248977407094344 | SXE2120627099364 | 10053692241 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 0 | 0 | 15 | Completed
| SS-ZAM-JAD1200 | الابتدائية الخامسة والسبعون بنات | Fourth Intermediate School | Intermediate | Boys | Jeddah | Jeddah |  | 21.545168108709742, 39.221067730936916 | HLY2020627022974 | 10053351045 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Revisit | Completed |  | 0 | 0 | 14 | In Progress
Total | [29 empty] | 0 | 0 | 0 | 0
[12 empty] | Total | Completed | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 195 | 195 | 195 | 189 | 197 | 0
[13 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on M4: 4/2/2025
Note on N4: 4/2/2025

## Makkah Schools -1
|  | Report Date | 2026-05-06
Project | Schools Information | [12 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordinates |  | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Makkah-1 | SS-ZAM-MAK1001 | مدرسة أبو بكر الرازي الابتدائية | Abu Bakr Al-Razi Elementary School | Primary | Boys | Makkah | Makkah | 21.4306 | 39.7961 | 21.43057,39.79615 | HLY2020627012233 | 10053778111 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress | Primary | Boys | Not Started
| SS-ZAM-MAK1002 | الابتدائية الثلاثون بعد المائة بنات | 130th Girls' Elementary School | Primary | Girls | Makkah | Makkah | 21.4152 | 39.7788 | 21.41524,39.7788 | SXE2020627004349 | 10053753373 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress | Intermediate | Girls | In Progress
| SS-ZAM-MAK1003 | سودة بنت زمعة المتوسطة بنات | Sawda Bint Zam'a Girls' Intermediate School | Intermediate | Girls | Makkah | Makkah | 21.4497 | 39.7674 | 21.44974,39.7674 | HLY2020627038127 | 10085435314 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress | Secondary | NA | Completed
| SS-ZAM-MAK1004 | الحسن البصري للطفولة المبكرة | Al-Hasan Al-Basri Early Childhood School | Early Child Hood | Boys | Makkah | Makkah | 21.422 | 39.7754 | 21.422015,39.775438 | SXE2020627059790 | 10083318355 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress | Early Child Hood |  | NA
| SS-ZAM-MAK1005 | المتوسطة الثانية بنات | Second Girls' Intermediate School | Intermediate | Girls | Makkah | Makkah | 21.4471 | 39.8042 | 21.447054,39.804183 | SMR2320621012794 | 10053330681 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress | Kinder Garten
| SS-ZAM-MAK1006 | الابتدائية السابعة و الثلاثون بنات | 37th Girls' Elementary School | Primary | Girls | Makkah | Makkah | 21.3761 | 39.7642 | 21.376062,39.764208 | SXE2020627005731 | 10053274572 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress | NA
| SS-ZAM-MAK1007 | `المدرسة الثانوية للبنات رقم 35 | 35th Girls' Secondary School | Secondary | Girls | Makkah | Makkah | 21.4554 | 39.7628 | 21.45539,39.76283 | 8401004 |  |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1008 | ابن كثير المتوسطة بنين | Ibn Kathir Boys' Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.4465 | 39.8694 | 21.446533,39.869363 | HLY2020627001788 | 10053601818 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1009 | معن بن عدي الابتدائية بنين | Ma'n Bin Adi Boys' Elementary School | Primary | Boys | Makkah | Makkah | 21.3821 | 39.8177 | 21.3821,39.81765 | HLY2020627012174 | 10053338956 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1010 | المتوسطة الثانية و الخمسون بنات | 52nd Girls' Intermediate School | Intermediate | Girls | Makkah | Makkah | 21.4344 | 39.8129 | 21.434409,39.81288 | SXE2020627006095 | 10053282144 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1011 | الثانوية السادسة عشر بنات | 16th Girls' Secondary School | Secondary | Girls | Makkah | Makkah | 21.4235 | 39.7731 | 21.42352,39.77313 | SXE2020627059786 | 10053535688 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1012 | الشيخ محمد السبيل للطفولة المبكرة | Sheikh Muhammad Al-Sabil Early Childhood School | Early Child Hood | Girls | Makkah | Makkah | 21.4385 | 39.7968 | 21.438536,39.796808 | HLY2020627036585 | 10053491485 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1013 | زينب بنت جحش الابتدائية بنات | Zainab Bint Jahsh Girls' Elementary School | Primary | Girls | Makkah | Makkah | 21.4499 | 39.7679 | 21.44991,39.76786 | HLY2020627038128 | 10085432751 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1014 | مدرسة عثمان بن عفان الثانوية -بنين | Uthman Bin Affan Boys' Secondary School | Secondary | Boys | Makkah | Makkah | 21.4317 | 39.8527 | 21.43165,39.85268 | HLY2020627010720 | 10053275032 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1015 | عمرو بن سالم الخزاعي الابتدائية بنين | Amr bin Salem Al-Khuza'i Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.457 | 39.8473 | 21.45698,39.84731 | HLY2020627001681 | 10053659504 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1016 | موسى بن نصير المتوسطة بنين | Musa bin Nusair Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4464 | 39.8497 | 21.44645,39.84969 | HLY2020627037229 | 10053192495 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1017 | الثالثة والخمسون الابتدائية بنات | Fifty-Third Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4764 | 39.7888 | 21.4764321,39.7887852 | HLY2020627009660 | 10053661128 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1018 | الثانوية الستون بنات | Sixtieth Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4274 | 39.7841 | 21.42741,39.78415 | SXE2020627057613 | 10053378101 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1019 | ثانوية الحكم بن هاشم بنين | Al-Hakam bin Hashim Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.3864 | 39.835 | 21.38637,39.83497 | SXE2020627059982 | 10053778013 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1020 | الروضة الثالثة والعشرون | Twenty-Third Kindergarten | Kinder Garten | Girls | Makkah | Makkah | 21.4831 | 39.784 | 21.48315,39.78404 | HLY2020627009611 | 10098728921 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1021 | ثانوية عمرة بنت عبدالرحمن بنات | Umrah bint Abdul Rahman Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4841 | 39.784 | 21.4840601,39.7840409 | HLY2020627009612 | 10098732497 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1022 | ثانوية طلحة بن عبيد الله | Talhah bin Ubaidullah Secondary School | Secondary | Boys | Makkah | Makkah | 21.4151 | 39.8658 | 21.415098,39.865812 | SXE2020627006173 | 10053776888 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1023 | اسية بنت مزاحم الابتدائية | Asiyah bint Muzahim Elementary School | Primary | Girls | Makkah | Makkah | 21.414 | 39.8044 | 21.41399,39.80444 | HLY2020627036432 | 10053233991 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1024 | مجمع الاميرة نورة التعليمي قسم الابتدائي | Princess Noura Educational Complex - Elementary Section | Primary | Girls | Makkah | Makkah | 21.4756 | 39.9267 | 21.4756441,39.9266868 | SXE2020627003663 | 10102728316 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1025 | مجمع الاميرة نورة التعليمي قسم المتوسط | Princess Noura Educational Complex - Intermediate Section | Intermediate | Girls | Makkah | Makkah | 21.4756 | 39.9267 | 21.4756441,39.9266868 | SXE2020627003552 | 10102728307 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1026 | مجمع الاميرة نورة التعليمي قسم الثانوي | Princess Noura Educational Complex - Secondary Section | Secondary | Girls | Makkah | Makkah | 21.4756 | 39.9267 | 21.4756441,39.9266868 | SXE2020627003659 | 10102728291 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1027 | عامر بن ربيعة الابتدائية بنين | Amer bin Rabi'ah Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4041 | 39.708 | 21.40408,39.70797 | HLY2020627038561 | 10053597500 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1028 | ابن الجوزي الابتدائية بنين | Ibn Al-Jawzi Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4763 | 39.7872 | 21.476318,39.7872074 | HLY2020627009656 | 10053660873 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1029 | أمامة بنت العاص المتوسطة بمكة المكرمة | Umamah bint Al-Aas Intermediate School in Makkah Al-Mukarramah | Intermediate | Girls | Makkah | Makkah | 21.4011 | 39.7983 | 21.40111,39.79828 | HLY2020627036383 | 10096882762 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1030 | الابتدائية السابعة لتحفيظ القران | Seventh Elementary School for Quran Memorization | Primary | Girls | Makkah | Makkah | 21.4415 | 39.7852 | 21.4415,39.78515 | HLY2020627055277 | 10053193652 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1031 | متوسطة الزاهر -بنين | Al-Zahir Intermediate School - Boys | Intermediate | Boys | Makkah | Makkah | 21.4424 | 39.7913 | 21.442393,39.791304 | HLY2020627001516 | 10053162502 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1032 | دار السلام الابتدائية بنين | Dar Al-Salam Primary School - Boys | Primary | Boys | Makkah | Makkah | 21.3908 | 39.8052 | 21.39076,39.80517 | SXE2020627059829 | 10053703003 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1033 | فاطمة الزهراء الثانوية بنات | Fatima Al-Zahra Secondary School - Girls | Secondary | Girls | Makkah | Makkah | 21.4494 | 39.7676 | 21.44942,39.76757 | HLY2020627038129 | 10085433356 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1034 | الروضة الخامسه -بنات | Fifth Kindergarten - Girls | Kinder Garten | Girls | Makkah | Makkah | 21.4163 | 39.8579 | 21.41631,39.85789 | HLY2020627011472 | 10053664120 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1035 | الثامنة عشرة المتوسطة بنات | Eighteenth Intermediate School - Girls | Intermediate | Girls | Makkah | Makkah | 21.3883 | 39.8106 | 21.38835,39.81061 | HLY2020627002235 | 10053335300 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1036 | الثانوية الحادية و الثلاثون بنات | Thirty-First Secondary School - Girls | Secondary | Girls | Makkah | Makkah | 21.4022 | 39.8189 | 21.40222,39.8189 | SXE2020627061437 | 10053542941 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1037 | بشر بن البراء المتوسطة | Bishr Ibn Al-Bara' Intermediate School | Intermediate | Girls | Makkah | Makkah | 21.4365 | 39.7595 | 21.436502,39.759543 | HLY2020627038635 | 10053377515 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1038 | متوسطة عتاب بن اسيد -بنين | Atab Ibn Asid Intermediate School - Boys | Intermediate | Boys | Makkah | Makkah | 21.408 | 39.7942 | 21.408,39.79422 | SXE2020627058443 | 10053596137 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1039 | مدرسة الحرمين للطفولة المبكرة | Al-Haramain Early Childhood School | Early Child Hood | Girls | Makkah | Makkah | 21.414 | 39.8608 | 21.41397,39.86079 | SXE2020627070241 | 10053775245 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1040 | الحادية و الثلاثون المتوسطة بنات | Thirty-First Intermediate School - Girls | Intermediate | Girls | Makkah | Makkah | 21.423 | 39.8028 | 21.423017,39.802849 | HLY2020627001001 | 10053429569 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1041 | مدرسة جعفر بن ابي طالب المتوسطة بنين | Jaafar bin Abi Talib Middle School for Boys | Intermediate | Boys | Makkah | Makkah |  |  | , | HLY2020627053955 | 10053542913 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1042 | الملك فيصل الثانوية بنين | King Faisal Secondary School for Boys | Secondary | Girls | Makkah | Makkah | 21.4345 | 39.8128 | 21.434507,39.812811 | SXE2020627005625 | 10053280373 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1043 | الثانوية الخامسة والاربعون بنات | Forty-Fifth Secondary School - Girls | Secondary | Girls | Makkah | Makkah | 21.4877 | 39.9337 | 21.487656,39.933653 | SXE2020627073163 | 10053338802 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1044 | ثانوية خديجة بنت خويلد بنات | Khadija Bint Khuwaylid Secondary School - Girls | Secondary | Girls | Makkah | Makkah | 21.3827 | 39.8316 | 21.38273,39.83158 | SXE2020627059978 | 10084523038 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1045 | ثانوية بثينة بنت النعمان | Buthaina Bint Al-Nu'man Secondary School | Secondary | Girls | Makkah | Makkah | 21.4013 | 39.7986 | 21.40125,39.79863 | HLY2020627036384 | 10096890209 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1046 | وكيع بن الجراح المتوسطة بنين | Waki' Ibn Al-Jarrah Intermediate School - Boys | Intermediate | Boys | Makkah | Makkah | 21.464 | 39.8642 | 21.46395,39.86423 | HLY2020627001685 | 10053720050 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1047 | المتوسطة الثانية و الستون بنات | Sixty-Second Intermediate School - Girls | Intermediate | Girls | Makkah | Makkah | 21.4098 | 39.7762 | 21.409761,39.776184 | SXE2020627004345 | 10053798482 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1048 | الامام البخاري الابتدائية بنات | Imam Al-Bukhari Primary School - Girls | Primary | Girls | Makkah | Makkah | 21.4441 | 39.8119 | 21.44408,39.81191 | SXE2020627072953 | 10053600445 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1049 | عباد بن بشر المتوسطة بنين | Abbad Ibn Bishr Intermediate School - Boys | Primary | Boys | Makkah | Makkah | 21.4076 | 39.7041 | 21.40761,39.70408 | HLY2020627038565 | 10053599489 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1050 | الرابعة والعشرون الثانوية بنات | Twenty-Fourth Secondary School - Girls | Secondary | Girls | Makkah | Makkah | 21.4616 | 39.8085 | 21.461586,39.808518 | HLY2020627001308 | 10053492901 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1051 | ابتدائية منى بنين | Mona Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4145 | 39.8602 | 21.41455,39.86022 | SXE2020627057689 | 10053776707 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1052 | مدرسة أنس بن مالك المتوسطة بنين | Anas Bin Malik Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4292 | 39.7876 | 21.429246,39.787589 | SXE2020627056691 | 10053332513 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1053 | المتوسطة الحادية و الخمسون بنات | Fifty-First Intermediate School for Girls | Intermediate | Girls | Makkah | Makkah | 21.4211 | 39.7727 | 21.421117,39.772685 | SXE2020627059785 | 10053536166 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1054 | البراء بن مالك للطفولة المبكرة | Al-Bara' Bin Malik Early Childhood School | Early Child Hood | Girls | Makkah | Makkah | 21.4141 | 39.7754 | 21.41411,39.775415 | SXE2020627004346 | 10053795758 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1055 | ابي عبيدة عامر بن الجراح المتوسطة بنين | Abi Ubaidah Amer Bin Al-Jarrah Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.3961 | 39.782 | 21.39612,39.78205 | SXE2020627059809 | 10053267621 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1056 | المتوسطة السابعة عشر بنات | Seventeenth Intermediate School for Girls | Intermediate | Girls | Makkah | Makkah | 21.414 | 39.8037 | 21.41399,39.80368 | SXE2020627060222 | 10053233319 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1057 | الشيخ عبدالله الخليفي الثانوية بنين | Sheikh Abdullah Al-Khalifi Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.3701 | 39.7999 | 21.37015,39.799877 | HLY2020627029560 | 10053271113 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1058 | الابتدائية الحادية و الثلاثون بعد المئة بنات | One Hundred and Thirty-First Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4052 | 39.7802 | 21.405157,39.780186 | SXE2020627058449 | 10053800956 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1059 | الابتدائية الثانية عشرة لتحفيظ القرآن | Twelfth Elementary School for Quran Memorization | Primary | Girls | Makkah | Makkah | 21.3841 | 39.8358 | 21.38411,39.83577 | SXE2020627056427 | 10053224141 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1060 | الابتدائية الخامسة و التسعون بنات | Ninety-Fifth Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.3659 | 39.7741 | 21.3659483,39.7740758 | HLY2020627001937 | 10053459245 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1061 | المتوسطة السابعة والخمسون | Fifty-Seventh Intermediate School | Intermediate | Girls | Makkah | Makkah | 21.3656 | 39.774 | 21.3655863960644,39.7739751988916 | HLY2020627057725 | 10053459503 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1062 | عمر المختار الابتدائية بنين | Omar Al-Mukhtar Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.3955 | 39.7883 | 21.39546,39.78829 | HLY2020627038575 | 10053524700 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1063 | الرابعة الابتدائية بنات | Fourth Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.3888 | 39.8102 | 21.38882,39.81017 | SXE2020627058873 | 10053335097 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1064 | المتوسطة السابعة و السبعون بنات | Seventy-Seventh Intermediate School for Girls | Intermediate | Girls | Makkah | Makkah | 21.4011 | 39.7009 | 21.40109,39.70087 | HLY2020627036449 | 10053602477 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1065 | متوسطة فاطمة بنت اسد بنت | Fatima Bint Asad Intermediate School for Girls | Intermediate | Girls | Makkah | Makkah | 21.4517 | 39.8388 | 21.45168,39.83881 | HLY2020627036499 | 10053541362 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1066 | الابتدائية السادسة و العشرون بعد المائة بنات | One Hundred and Twenty-Sixth Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4231 | 39.773 | 21.42312,39.77303 | HLY2020627038392 | 10053535946 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1067 | العباس بن عبدالمطلب الابتدائية بنين | Al-Abbas ibn Abd al-Muttalib Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4249 | 39.8062 | 21.424862,39.806191 | HLY2020627012268 | 10053284461 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1068 | عتبة بن غزوان للطفولة المبكرة | Utbah ibn Ghazwan Early Childhood Center | Early Child Hood | NA | Makkah | Makkah | 21.38 | 39.7831 | 21.38,39.7831 | SXE2020627059718 | 10053339990 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1069 | نعيم بن مسعود الابتدائية - بنين | Na'im ibn Mas'ud Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.3846 | 39.8676 | 21.384635,39.867571 | SXE2020627006130 | 10053656398 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1070 | ابي الدرداء الابتدائية بنين | Abi al-Darda' Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4015 | 39.7931 | 21.40154,39.79312 | HLY2020627038645 | 10053778247 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1071 | مركز ام المؤمنين خديجه بنت خويلد للتوحد - بنات | Umm al-Mu'minin Khadijah bint Khuwaylid Center for Autism for Girls | NA | Girls | Makkah | Makkah | 21.4166 | 39.8575 | 21.41662,39.85748 | HLY2020627038952 | 10053663866 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1072 | ابن القيم للطفولة المبكرة | Ibn al-Qayyim Early Childhood Center | Early Child Hood | NA | Makkah | Makkah | 21.3935 | 39.8795 | 21.393474,39.879489 | HLY2020627038092 | 10053655944 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1073 | متوسطة ابن رجب بنين | Ibn Rajab Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4034 | 39.8679 | 21.40339,39.86792 | SXE2020627059108 | 10090192262 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1074 | مدرسة اليرموك المتوسطة بنين | Al-Yarmouk Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.3949 | 39.7884 | 21.39485,39.78838 | HLY2020627038574 | 10053524961 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1075 | ثانوية الامير سعود الفيصل | Prince Saud al-Faisal Secondary School | Secondary | Boys | Makkah | Makkah | 21.4476 | 39.8579 | 21.447644,39.857853 | HLY2020627038013 | 10053384761 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1076 | الثانوية الثالثة والثلاثون للبنات | The Thirty-Third Girls' High School | Primary | Boys | Makkah | Makkah | 21.4588 | 39.9675 | 21.4588026809986,39.9674845503276 | HLY2020627036277 | 10053219187 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1077 | مدرسة بلاط الشهداء المتوسطة | Balat al-Shuhada' Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.3847 | 39.867 | 21.384722,39.867035 | SXE2020627006129 | 10053656665 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1078 | الابتدائية الخامسة والثلاثون | The 35th Elementary School | Primary | Girls | Makkah | Makkah | 21.4232 | 39.8036 | 21.4232169,39.803581 | SXE2020627003781 | 10053429031 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1079 | المتوسطة الثامنة بنات | The 8th Intermediate School for Girls | Intermediate | Girls | Makkah | Makkah | 21.4163 | 39.8572 | 21.41633,39.85723 | HLY2020627038955 | 10053662690 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1080 | الابتدائية الثامنة و الاربعون بعد المئة بنات | The 148th Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.3992 | 39.7041 | 21.39925,39.70411 | HLY2020627012437 | 10053660391 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1081 | متوسطة القاضي عياض بنين | Al-Qadi Iyad Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4489 | 39.8392 | 21.448869,39.839192 | HLY2020627002459 | 10053429273 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1082 | متوسطة الزبير بن العوام بنين | Al-Zubair Ibn Al-Awam Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4399 | 39.8398 | 21.43988,39.83978 | HLY2020627002155 | 10101467556 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1083 | متوسطة عبدالله بن انيس بنين | Abdullah Ibn Anis Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4313 | 39.7887 | 21.43135,39.78874 | HLY2020627037726 | 10053330223 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1084 | القعقاع بم عمرو المتوسطة بنين | Al-Qaqa' Ibn Amr Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4493 | 39.8613 | 21.449327,39.861332 | HLY2020627010734 | 10053329410 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1085 | الابتدائية السادسة و الثلاثون بنات | 36th Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4054 | 39.8766 | 21.405442,39.876572 | HLY2020627001223 | 10053543714 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1086 | محمد بن عبدالوهاب للطفولة المبكرة بنات | Muhammad Ibn Abdul Wahhab Early Childhood Center for Girls | Early Child Hood | Girls | Makkah | Makkah | 21.446 | 39.8691 | 21.445952,39.869079 | HLY2020627001787 | 10053602575 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1087 | الثانوية السادسة والعشرون بنات | 26th Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4346 | 39.7969 | 21.43461,39.79687 | HLY2020627037213 | 10053777482 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1088 | الابتدائية الحادية والاربعون | 41st Elementary School | Primary | Girls | Makkah | Makkah | 21.4143 | 39.8038 | 21.41429,39.80382 | SXE2020627060220 | 10053233471 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1089 | التاسعة و الخمسون الابتدائية بنات | 59th Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4161 | 39.8574 | 21.41607,39.85741 | HLY2020627038860 | 10053662199 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1090 | ذات الصواري الثانوية بنين | Dhat Al-Sawari Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.4429 | 39.8457 | 21.442899,39.845734 | SXE2020627003128 | 10053332504 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1091 | الثانوية الرابعة بنات | 4th Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4459 | 39.8045 | 21.44595,39.80448 | SMR2220621003583 | 10053331427 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1092 | ثانوية العز بن عبد السلام بنين | Al-Izz Ibn Abdul Salam Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.4897 | 39.9306 | 21.48974,39.930562 | HLY2020627010749 | 10053274518 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1093 | متوسطة الارقم بن ابي الارقم -بنين | Al-Arqam Ibn Abi Al-Arqam Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4132 | 39.8617 | 21.41317,39.86169 | HLY2020627057607 | 30065950045 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1094 | الابتدائية الستون بنات | 60th Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4461 | 39.8555 | 21.44612,39.855503 | HLY2020627001235 | 10053382542 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1095 | معهد التربية الفكرية | Institute of Intellectual Education | NA | Boys | Makkah | Makkah | 21.4333 | 39.7864 | 21.43331,39.78644 | SXE2020627056666 | 10053328299 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1096 | ثانوية معاذ بن جبل -بنين | Mu'adh Ibn Jabal Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.3954 | 39.7822 | 21.3954,39.78217 | SXE2020627059811 | 10053267943 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1097 | مدرسة عذبةبنت سعد الإبتدائية للبنات | Adhba Bint Saad Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4006 | 39.7984 | 21.400639,39.7983643 | HLY2020627038015 | 10096891261 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1098 | المدرسة المتوسطة الرابعة والستون بنات | 64th Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.4583 | 39.967 | 21.4582698219524,39.9670365466268 | HLY2020627036276 | 10053218958 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1099 | جبل النور للطفولة المبكرة | Jabal Al-Nour Early Childhood Center | Early Child Hood | Boys | Makkah | Makkah | 21.4519 | 39.8583 | 21.45187,39.85832 | HLY2020627010654 | 10053489601 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1100 | ابي محجن الثقفي المتوسطة بنين | Abi Mihjan Al-Thaqafi Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.3825 | 39.8207 | 21.38248,39.82065 | SXE2020627058736 | 10053342224 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1101 | تحفيظ القران الثالثه بنات | 3rd Quran Memorization Center for Girls | NA | Girls | Makkah | Makkah | 21.4152 | 39.7784 | 21.41523,39.77835 | SXE2020627058457 | 10053753874 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1102 | الابتدائية التاسعه والاربعون -بنات | 49th Elementary School - Girls | Primary | Girls | Makkah | Makkah | 21.389 | 39.7899 | 21.38904,39.78994 | KFM2120655005655 | 10105126027 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1103 | المدرسة المائة والثلاثة والثلاثون الابتدائية | The 133rd Elementary School | Primary | Girls | Makkah | Makkah | 21.4585 | 39.9676 | 21.4585089074289,39.9675691362663 | SXE2020627003000 | 10053461360 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1104 | جبير بن مطعم الابتدائية | Jubair Bin Mut'im Elementary School | Primary | Boys | Makkah | Makkah | 21.3999 | 39.8024 | 21.39986,39.80239 | HLY2020627036382 | 10095439522 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1105 | الابتدائية الثانية و الثلاثون بعد المئة بنات | 132nd Elementary School - Girls | Primary | Girls | Makkah | Makkah | 21.4721 | 39.9252 | 21.472083,39.925239 | SXE2020627003598 | 10053578792 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1106 | المتوسطة الثامنة والاربعون بنات | 48th Intermediate School - Girls | Intermediate | Girls | Makkah | Makkah | 21.4721 | 39.9252 | 21.472083,39.925239 | SXE2020627003597 | 10053578541 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1107 | مدرسة الامير عبدالمجيد الثانوية بنين | Prince Abdulmajid Secondary School - Boys | Secondary | Boys | Makkah | Makkah | 21.4295 | 39.7869 | 21.42948,39.786915 | SXE2020627056693 | 10053333299 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1108 | المتوسطة الرابعة عشر بنات | 14th Intermediate School - Girls | Intermediate | Girls | Makkah | Makkah | 21.4409 | 39.7856 | 21.44087,39.78556 | HLY2020627037292 | 10053194696 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1109 | ابن تيمية الابتدائية | Ibn Taymiyyah Elementary School | Primary | Boys | Makkah | Makkah | 21.4171 | 39.7932 | 21.41706,39.79318 | HLY2020627036003 | 10053777025 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1110 | عطاء بن ابي رباح الابتدائية | Ata Bin Abi Rabah Elementary School | Primary | Boys | Makkah | Makkah | 21.4057 | 39.7772 | 21.405728,39.777203 | SXE2020627004350 | 10053798938 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1111 | المتوسطة الثانية والثلاثون بنات | 32nd Intermediate School - Girls | Intermediate | Girls | Makkah | Makkah | 21.4525 | 39.8591 | 21.452485,39.859059 | HLY2020627044056 | 10053488846 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1112 | الفتح المتوسطة بنين | Al-Fath Intermediate School - Boys | Intermediate | Boys | Makkah | Makkah | 21.3905 | 39.8047 | 21.390513,39.804714 | SXE2020627059828 | 10053702768 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1113 | ابتدائية الرحمانية بنين | Al-Rahmaniyah Elementary School - Boys | Primary | Boys | Makkah | Makkah | 21.3876 | 39.8352 | 21.387614,39.835248 | SXE2020627060742 | 10053776968 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1114 | ابتدائية معاذة العدوية بنات | Mu'adhah Al-Adawiyah Elementary School - Girls | Primary | Girls | Makkah | Makkah | 21.4398 | 39.8433 | 21.43984,39.84327 | HLY2020627001522 | 10053661816 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1115 | متوسطة عمر بن الخطاب -بنين | Omar Bin Al-Khattab Intermediate School - Boys | Intermediate | Boys | Makkah | Makkah | 21.4382 | 39.805 | 21.438244,39.804965 | HLY2020627038424 | 10053604892 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1116 | ثانوية جعفر الصادق -بنين | Ja'far Al-Sadiq Secondary School - Boys | Secondary | Boys | Makkah | Makkah | 21.4017 | 39.7925 | 21.40172,39.79252 | HLY2020627038644 | 10053778176 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1117 | الثالثة عشر الابتدائية لتحفيظ القران بنات | Thirteenth Elementary School for Quran Memorization (Girls) | Primary | Girls | Makkah | Makkah | 21.4459 | 39.8558 | 21.445875,39.855752 | HLY2020627010651 | 10053382776 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1118 | الابتدائية الاربعون بنات | Fortieth Elementary School (Girls) | Primary | Girls | Makkah | Makkah | 21.3838 | 39.836 | 21.38379,39.83597 | SXE2020627056425 | 10053223706 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1119 | ثانوية أبي زيد الانصاري | Abu Zaid Al-Ansari Secondary School | Secondary | Boys | Makkah | Makkah | 21.4752 | 39.8411 | 21.47516,39.84106 | SXE2020627003064 | 10053721487 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1120 | ثانوية مكة - بنين | Makkah Secondary School (Boys) | Secondary | Boys | Makkah | Makkah | 21.4466 | 39.8083 | 21.44662,39.80835 | SXE2020627056886 | 10053538429 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1121 | الابتدائية السادسة لتحفيظ القران الكريم | Sixth Elementary School for Quran Memorization | Primary | Girls | Makkah | Makkah | 21.4597 | 39.8438 | 21.459707,39.843755 | HLY2020627001326 | 10053163653 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1122 | المتوسطة الاربعون بنات | Fortieth Intermediate School (Girls) | Intermediate | Girls | Makkah | Makkah | 21.4273 | 39.7844 | 21.42728,39.78435 | SXE2020627057614 | 10053377918 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1123 | قتادة بن النعمان الابتدائية بنين | Qatadah Ibn Al-Nu'man Elementary School (Boys) | Primary | Boys | Makkah | Makkah | 21.4491 | 39.8618 | 21.449092,39.86179 | HLY2020627010731 | 10053329170 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1124 | عمورية الابتدائية بنين | Amouriyah Elementary School (Boys) | Primary | Boys | Makkah | Makkah | 21.403 | 39.786 | 21.40304,39.78596 | HLY2020627038642 | 10053716576 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1125 | متوسطة اليمامة | Al-Yamamah Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.4834 | 39.7959 | 21.483420020707,39.7958955772841 | HLY2020627011893 | 10053715990 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1126 | الخامسة والاربعون الابتدائية بنات | Forty-Fifth Elementary School (Girls) | Primary | Girls | Makkah | Makkah | 21.4455 | 39.8043 | 21.445487,39.804341 | HLY2020627037563 | 10053330911 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1127 | مدرسة الهجرة المتوسطة | Al-Hijrah Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.3869 | 39.8358 | 21.38691,39.8358 | HLY2020627002244 | 10053777741 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1128 | الامام السخاوي الثانوية بنين | Imam Al-Sakhawi Secondary School (Boys) | Secondary | Boys | Makkah | Makkah | 21.426 | 39.7871 | 21.42597,39.787141 | HLY2020627011997 | 10053493111 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1129 | معهد النور للمكفوفين | Al-Noor Institute for the Blind | NA | Boys | Makkah | Makkah | 21.4356 | 39.76 | 21.43559,39.75995 | SXE2020627059788 | 10053377749 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1130 | الابتدائية السادسة والاربعون | Forty-Sixth Elementary School | Primary | Girls | Makkah | Makkah | 21.4463 | 39.8043 | 21.44631,39.80432 | HLY2020627001923 | 10053486144 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1131 | الثانوية السادسة والاربعون بنات | Forty-Sixth Secondary School (Girls) | Secondary | Girls | Makkah | Makkah | 21.3865 | 39.8765 | 21.386472,39.876507 | SXE2020627006211 | 10053429200 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1132 | متوسطة عثمان بن طلحة بنين | Uthman Ibn Talhah Intermediate School (Boys) | Intermediate | Boys | Makkah | Makkah | 21.4041 | 39.8182 | 21.404074,39.818232 | HLY2020627001804 | 10053541747 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1133 | المتوسطة الثالثة و الستون بنات | Sixth Intermediate School (Girls) | Intermediate | Girls | Makkah | Makkah | 21.3755 | 39.7641 | 21.375538,39.764138 | SXE2020627005736 | 10053335032 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1134 | الروضة السادسة | Sixth Kindergarten | Kinder Garten | Girls | Makkah | Makkah | 21.4134 | 39.8038 | 21.41339,39.80383 | HLY2020627036431 | 10053234245 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1135 | مدرسة حنظله بن عامر للطفولة المبكره | Hanzala Ibn Amer Early Childhood School | Early Child Hood | Boys | Makkah | Makkah | 21.3673 | 39.7956 | 21.36727,39.79556 | HLY2020627013002 | 10053273495 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1136 | مدرسة عبدالرحمن الغافقي للطفولة المبكرة | Abdul Rahman Al-Ghafiqi Early Childhood School | Early Child Hood | Boys | Makkah | Makkah | 21.3761 | 39.7773 | 21.37606,39.77727 | SXE2020627059812 | 10102875554 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1137 | متوسطة العاصمة النموذجية -بنين | Al-Asimah Model Intermediate School (Boys) | Intermediate | Boys | Makkah | Makkah | 21.4152 | 39.865 | 21.415238,39.86502 | HLY2020627038257 | 10053776627 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1138 | ثانوية زبيدة بنت حعفر-بنات | Zubaydah Bint Ja'far Secondary School (Girls) | Secondary | Girls | Makkah | Makkah | 21.4372 | 39.8376 | 21.43725,39.83763 | HLY2020627001096 | 10053489781 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1139 | الابتدائية الواحد و الخمسون بنات | Fifty-oneth Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.3894 | 39.881 | 21.38937,39.881045 | HLY2020627001891 | 10053384421 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1140 | القدس الثانوية بنين | Al-Quds Secondary School for Boys | Primary | Boys | Makkah | Makkah | 21.4412 | 39.7938 | 21.441242,39.793815 | HLY2020627001838 | 10053382702 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1141 | ام عماره الابتدائية -بنات | Umm Amara Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.418 | 39.8563 | 21.418,39.85632 | HLY2020627038873 | 10088073818 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1142 | حسان بن ثابت -بنين | Hassan Bin Thabit Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4351 | 39.8049 | 21.435053,39.804866 | HLY2020627036583 | 10053658276 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1143 | عين جالوت الثانوية بنين | Ain Jalut Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.401 | 39.7826 | 21.401,39.78255 | SXE2020627004352 | 10053747492 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1144 | الثانوية السابعة بنات | Seventh Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.3897 | 39.8815 | 21.389712,39.881534 | SXE2020627071312 | 10053384181 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1145 | متوسطة عبدالله خياط بنين | Abdullah Khayyat Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.411 | 39.7796 | 21.410977,39.779572 | SXE2020627003400 | 10053796746 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1146 | الثانوية الرابعة عشر بنات | Fourteenth Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4059 | 39.8768 | 21.405929,39.876799 | SXE2020627058345 | 10053542691 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1147 | الثانوية الثامنة و العشرون بنات | Twenty-eighth Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4017 | 39.8698 | 21.401749,39.869849 | HLY2020627013017 | 10053232581 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1148 | الملك عبدالله الثانوية بنين | King Abdullah Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.4828 | 39.7959 | 21.48277,39.79585 | HLY2020627011895 | 10053715775 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1149 | عكرمة بن عمرو بن هشام الثانوية بنين | Ikrimah Bin Amr Bin Hisham Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.4784 | 39.8435 | 21.478422,39.843501 | HLY2020627001327 | 10053192898 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1150 | المدرسة السادسة والتسعون الابتدائية بنات | Ninety-sixth Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.3853 | 39.872 | 21.38526,39.87201 | HLY2020627055228 | 10053490728 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1151 | تحفيظ القران الاولى المتوسطة والثانوي بنات | First Intermediate and Secondary School for Girls (Quran Memorization) | Secondary | Girls | Makkah | Makkah | 21.4471 | 39.8053 | 21.44710444,39.80532079 | SXE2020627060790 | 10053487277 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1152 | البلد الامين المتوسطة للموهوبين | Al-Balad Al-Amin Intermediate School for Gifted Students | Intermediate | Boys | Makkah | Makkah | 21.4333 | 39.7729 | 21.43328,39.77286 | HLY2020627029682 | 10091625978 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1153 | الثانوية التاسعة والثلاثون بنات | Thirty-ninth Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.3667 | 39.7971 | 21.3667,39.79707 | HLY2020627000877 | 10053272273 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1154 | الابتدائية الخامسة و الثلاثون بعد المئة بنات | One hundred and thirty-fifth Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.3667 | 39.7971 | 21.3667,39.79707 | HLY2020627000879 | 10053272513 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1155 | المغيرة بن شعبة الابتدائية بنين | Al-Mughirah Bin Shu'bah Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4446 | 39.7661 | 21.444555,39.766073 | SXE2020627056399 | 10053775700 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1156 | مدرسة سعد بن معاذ الابتدائية بنين | Saad Bin Mu'adh Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.4223 | 39.7693 | 21.4222603,39.7692556 | HLY2020627009658 | 10053378236 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1157 | ابتدائية حبيبة بنت عمرو | Habibah Bint Amr Elementary School | Primary | Girls | Makkah | Makkah | 21.3839 | 39.808 | 21.3838956,39.8079786 | SXE2020627058880 | 10102405441 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1158 | المدرسة التاسعة والثلاثون ( 39 ) المتوسطة بمكة | The 39th Intermediate School in Makkah | Intermediate | Girls | Makkah | Makkah | 21.4646 | 39.9376 | 21.4645942091197,39.9376204429693 | HLY2020627012218 | 10053752886 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1159 | روضة النرجس مكة | Al-Narjis Kindergarten, Makkah | Early Child Hood | Girls | Makkah | Makkah | 21.4639 | 39.9371 | 21.4639240623986,39.9370592466964 | SXE2020627069749 | 10053699395 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1160 | الابتدائية السادسة والثمانون للبنات | The 86th Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.4637 | 39.9375 | 21.4637197872232,39.9374910551946 | SXE2020627069748 | 10053700066 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started |  |  | 3 | 0 | 11 | In Progress
| SS-ZAM-MAK1161 | ابتدائية حمزة بن عبدالمطلب بنين | Hamza bin Abdul Muttalib Primary School for Boys | Primary | Girls | Makkah | Makkah | 21.402 | 39.816 | 21.4019725770643,39.8160219306406 | HLY2020627010226 | 10053581411 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1162 | الثانوية التاسعة و العشرون بنات | The 29th Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4642 | 39.938 | 21.4642265141921,39.9380140859387 | SXE2020627069750 | 10053699813 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1163 | الثانوية التاسعة والأربعون | The 49th Secondary School | Secondary | Girls | Makkah | Makkah | 21.4053 | 39.7809 | 21.4053141833742,39.7808516144048 | SXE2020627059810 | 10053801391 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1164 | مدرسة العمرة | Al-Umrah School | Secondary | Boys | Makkah | Makkah | 21.4727 | 39.7903 | 21.4727362467644,39.7903163779539 | HLY2020627012447 | 10053664621 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1165 | مدرسة الأمير ماجد بن عبد العزيز المتوسطة | Prince Majid bin Abdul Aziz Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.3583 | 39.883 | 21.3582526618892,39.8829583859377 | SXE2020627005317 SXE2020627005320 SXE2020627005433 SXE2020627005423 | 10053163359 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1166 | مدرسة ابن هشام الابتدائية | Ibn Hisham Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.5685 | 39.7789 | 21.5684789160763,39.7789070294404 | SXE2020627006152 | 10053376376 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1167 | مدرسة زمزم الابتدائيةبنين | Zamzam Elementary School for Boys | Primary | Boys | Makkah | Makkah | 21.5701 | 39.7767 | 21.5701154622357,39.7766894461914 | HLY2020627012248 | 10096961525 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started |  |  | 3 | 0 | 11 | In Progress
| SS-ZAM-MAK1168 | الابتدائية العاشرة للطفولة المبكرة | The 10th Elementary School for Early Childhood | Primary | Girls | Makkah | Makkah | 21.4529 | 39.8635 | 21.4529468317903,39.8634517493322 | HLY2020627059665 | 10102901341 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1169 | المدرسة الثامنة والعشرون بنات | The 28th Girls' School | Intermediate | Girls | Makkah | Makkah | 21.569 | 39.7797 | 21.5690154478152,39.779677958038 | HLY2020627010715 | 10053537744 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 3 | 0 | 11 | In Progress
| SS-ZAM-MAK1170 | مدرسة ابتدائية ابن عامر للطفولة المبكرة بنين | Ibn Amer Elementary School for Early Childhood for Boys | Primary | Boys | Makkah | Makkah | 21.3572 | 39.8774 | 21.3571966771625,39.8773854551713 | SXE2020627071972 | 10053162567 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1171 | المدرسة السادسة والثلاثون الثانوية بنات | The 36th Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.5568 | 39.7692 | 21.5567828904576,39.7692332571384 | HLY2020627001309 | 10053657303 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1172 | الابتدائية التاسعة بعد المائة للبنات | The 109th Elementary School for Girls | Primary | Girls | Makkah | Makkah | 21.5683 | 39.7792 | 21.5683165900514,39.7792463249895 | HLY2020627010691 | 10053537495 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1173 | مدرسة ام سعد بن معاذ الابتدائيه | Umm Saad bin Muadh Elementary School | Primary | Boys | Makkah | Makkah | 21.4553 | 39.7632 | 21.4553205300277,39.7631693874527 | SXE2020627003094 | 10053190697 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1174 | المدرسة الإبتدائية الثامنة والتسعون | The 98th Elementary School | Primary | Girls | Makkah | Makkah | 21.5573 | 39.7685 | 21.5572668399853,39.7685107149465 | HLY2020627001264 | 10053657789 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1175 | الروضة الثانية عشر | Twelfth Kindergarten | Kinder Garten | Girls | Makkah | Makkah | 21.5574 | 39.769 | 21.5573914424621,39.7689985835601 | HLY2020627001306 | 10053658338 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1176 | مدرسة عروة بن الزبير الابتدائية | Urwah ibn al-Zubayr Elementary School | Primary | Girls | Makkah | Makkah | 21.5579 | 39.7711 | 21.5579215605234,39.7711080464866 | HLY2020627012279 | 10053656585 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1177 | المدرسة المتوسطة الثامنة والثلاثون بنات | Thirty-Eighth Intermediate School for Girls | Intermediate | Girls | Makkah | Makkah | 21.4527 | 39.8638 | 21.4527101180762,39.8638202122687 | HLY2020627055241 | 10102901331 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1178 | مدرسة أبي بن كعب المتوسطة | Ubayy ibn Ka'b Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.5577 | 39.7708 | 21.557650593622,39.7708081300555 | HLY2020627012284 | 10053656825 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1179 | مدرسة زيد بن الخطاب المتوسطة بنين | Zayd ibn al-Khattab Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.5696 | 39.7768 | 21.5696202140511,39.7767957192969 | HLY2020627012247 | 10096966209 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started |  |  | 3 | 0 | 11 | In Progress
| SS-ZAM-MAK1180 | المدرسة الثلاثون الثانوية بمكة | Thirtieth Secondary School in Mecca | Secondary | Girls | Makkah | Makkah | 21.3836 | 39.835 | 21.3836292878118,39.8350454804277 | SXE2020627056426 | 10053223911 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1181 | الثانوية الحادية والاربعون للبنات | Forty-First Secondary School for Girls | Secondary | Girls | Makkah | Makkah | 21.4682 | 39.9404 | 21.4681532310385,39.940365711729 | HLY2020627010910 | 10053702946 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1182 | مجمع معهدالأمل للبنات الصم | Al-Amal Institute Complex for Deaf Girls | NA | Girls | Makkah | Makkah | 21.4467 | 39.8041 | 21.4467292793975,39.8040842823718 | HLY2020627055294 | 10053329699 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started |  |  | 3 | 0 | 11 | In Progress
| SS-ZAM-MAK1183 | الابتدائية السابعة بعد المائة بمكة المكرمة | One Hundred-Seventh Elementary School in Mecca | Primary | Girls | Makkah | Makkah | 21.4685 | 39.9401 | 21.4685497315665,39.9400997826101 | SXE2020627071455 | 10053702712 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1184 | مدرسة الليث بن سعد المتوسطة بنين | Al-Layth ibn Sa'd Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.5427 | 39.7944 | 21.5427115893451,39.7943535168138 | SXE2020627006193 | 10087535417 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1185 | البيروني الابتدائية | Al-Biruni Elementary School | Primary | Boys | Makkah | Makkah | 21.4655 | 39.9428 | 21.4655024975193,39.9428027217203 | SXE2020627071456 | 10053745040 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1186 | المدرسة الثامنة الابتدائية وروضة المودة | Eighth Elementary School and Al-Mawaddah Kindergarten | Primary | Girls | Makkah | Makkah | 21.4651 | 39.9622 | 21.4651432580084,39.9621664490176 | SXE2020627071264 | 10053337618 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1187 | مدرسة صفية بنت عبدالمطلب طفولة مبكرة | Safiyyah ibn Abd al-Muttalib Early Childhood School | Early Child Hood | Girls | Makkah | Makkah | 21.5333 | 39.7866 | 21.5332986551792,39.786555069998 | SMR2220621004029 | 10105319711 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started |  |  | 3 | 0 | 11 | In Progress
| SS-ZAM-MAK1188 | ثانوية أبي أيوب الأنصاري بنين | Abu Ayyub al-Ansari Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.4658 | 39.9398 | 21.4658197977812,39.9398293205349 | SXE2020627071452 | 10053704806 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Completed | Completed | Not Started | Not Started | Not Started |  |  | 5 | 0 | 9 | In Progress
| SS-ZAM-MAK1189 | مدرسة الجاحظ الثانوية بنين | Al-Jahiz Secondary School for Boys | Secondary | Boys | Makkah | Makkah | 21.4632 | 39.9668 | 21.4632038204688,39.966822545535 | SXE2020627073166 | 10053339597 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1190 | المتوسطة الرابعة والأربعون | Forty-Fourth Intermediate School | Intermediate | Girls | Makkah | Makkah | 21.5327 | 39.7859 | 21.5327291004203,39.7859362183338 | SXE2020627006150 | 10053328781 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1191 | المدرسة الثانوية السابعة والعشرون بنات | Twenty-seventh Girls' Secondary School | Secondary | Girls | Makkah | Makkah | 21.4526 | 39.8591 | 21.4526449036434,39.8591292739075 | HLY2020627037206 | 10053488309 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1192 | مدرسة زيد الخير الابتدائية | Zaid Al-Khair Elementary School | Primary | Boys | Makkah | Makkah | 21.5026 | 39.9594 | 21.5026373678935,39.9594270730291 | SXE2020627070537 | 10094270483 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1193 | مدرسة يزيد بن رومان المتوسطة الراشدية | Yazeed Bin Ruman Al-Rashidiyah Intermediate School | Intermediate | Boys | Makkah | Makkah | 21.4683 | 39.9553 | 21.4683047646825,39.9553301519238 | SXE2020627069716 | 10103447042 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1194 | مدرسة أبي سعيد الخدري الابتدائية | Abu Saeed Al-Khudri Elementary School | Primary | Boys | Makkah | Makkah | 21.5293 | 39.7953 | 21.5292675850717,39.7952512323768 | HLY2020627036118 | 10053191611 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1195 | مدرسة عكاظ الابتدائية | Okaz Elementary School | Primary | Boys | Makkah | Makkah | 21.4885 | 39.9608 | 21.4885407379955,39.9608478268466 | SXE2020627070539 | 10053123934 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed | Completed | Completed | Completed | Not Started |  |  | 2 | 0 | 12 | In Progress
| SS-ZAM-MAK1196 | مدرسة عبدالملك بن مروان المتوسطة بنين | Abdulmalik Bin Marwan Intermediate School for Boys | Intermediate | Boys | Makkah | Makkah | 21.4676 | 39.9555 | 21.4675777969855,39.9554949833331 | SXE2020627069715 | 10053403080 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1197 | الابتدائية السادسة والعشرون للبنات مكه | Twenty-sixth Girls' Elementary School, Makkah | Primary | Girls | Makkah | Makkah | 21.4492 | 39.8101 | 21.4491584589796,39.8100708406226 | HLY2020627037464 | 10053155268 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1198 | المدرسة المتوسطة السابعة والأربعون ( بنات ) | Forty-seventh Intermediate School (Girls) | Intermediate | Girls | Makkah | Makkah | 21.5569 | 39.7687 | 21.5568604,39.7686609062644 | HLY2020627001307 | 10053657537 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
| SS-ZAM-MAK1199 | المدرسة الثانوية الثانية | Second Secondary School | Secondary | Girls | Makkah | Makkah | 21.417 | 39.8569 | 21.4169573761298,39.8568588854291 | HLY2020627038951 | 10053663187 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | 0 | 0 | 14 | In Progress
| SS-ZAM-MAK1200 | المدرسة التاسعة عشرة الثانوية بنات | Nineteenth Girls' Secondary School | Secondary | Girls | Makkah | Makkah | 21.5684 | 39.7798 | 21.5684347303888,39.7797517706823 | HLY2020627012249 | 10053537243 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | Completed |  |  | 1 | 0 | 13 | In Progress
[13 empty] | Total | Completed | 200 | 200 | 200 | 200 | 200 | 200 | 199 | 198 | 190 | 200 | 200 | 193 | 170 | 182 |  |  | 0 | 0 | 0 | 182.1333
[14 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 10 | 0 | 0 | 7 | 30 | 18
Note on N4: 4/2/2025
Note on O4: 4/2/2025

## Al Jouf Schools -1
|  | Report Date | 2026-05-10
Project | Project | Schools Information | [12 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
|  | School ID | School Name (Arabic) | School Name (English) | School Level | School Gender (Boys / Girls) | Region | City | School Coordinates |  | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Al Jouf-1 | Al Jouf Schools Project | SS-ZAM-JOUF1001 | الابتدائية الاولى بالطوير | The first elementary school in Al-Tuwair | Primary | Girls | Al Jouf | Al Jouf | 29.9141 | 40.1988 | 29.9141234861226,40.1987630579318 | KFM2020660075677 | 30110288636 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress | Primary | Boys | Not Started
|  | SS-ZAM-JOUF1002 | مدرسة النهضة | Al Nahda School | Primary | Boys | Al Jouf | Al Jouf | 29.9643 | 40.2194 | 29.9642695133926,40.2194066592426 | KFM2120660238801 | 10005997011 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress | Intermediate | Girls | In Progress
|  | SS-ZAM-JOUF1003 | مدرسة العباس بن عبدالمطلب | Al-Abbas ibn Abdul Muttalib School | Primary | Boys | Al Jouf | Al Jouf | 29.9165 | 40.1968 | 29.9165409402206,40.1968428978733 | KFM2020660179535 | 10005982724 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress | Secondary | NA | Completed
|  | SS-ZAM-JOUF1004 | مدرسة مصعب بن عمير | Musab bin Umair School | Primary | Boys | Al Jouf | Al Jouf | 29.8895 | 40.2145 | 29.8894760683633,40.2144653246139 | KFM2020660179650 | 10005899402 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress | KinderGarten |  | NA
|  | SS-ZAM-JOUF1005 | مدرسة حسان بن ثابت | Hassan ibn Thabit School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8754 | 40.223 | 29.8754450605914,40.2230282924485 | KFM2020660179540 | 10086914371 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress | Early Childhood
|  | SS-ZAM-JOUF1006 | ابتدائية قارا بنين | Qara Boys Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.8646 | 40.2196 | 29.8646373003157,40.2196165874439 | KFM2020660179674 | 10005967432 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | NA
|  | SS-ZAM-JOUF1007 | مدرسة الرفيعة | Al-Rafi'a School | Intermediate | Boys | Al Jouf | Al Jouf | 30.0664 | 40.3213 | 30.0663632049601,40.3213212097802 | KFM2120660261712 | 10005987909 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1008 | مدرسة هديب | Hadib School | Primary | Boys | Al Jouf | Al Jouf | 30.0634 | 40.3918 | 30.0634315235089,40.3918053112577 | KFM2120660238756 | 10005998377 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1009 | مدرسة الخندق | Al-Khandaq School | Intermediate | Boys | Al Jouf | Al Jouf | 30.3634 | 40.4224 | 30.3633841657012,40.422415537146 | KFM2120660238866 | 10005998439 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1010 | مدرسة قارا الأولى الابتدائية والطفولة المبكرة للبنات" | First Primary and Early Childhood of Qara | Primary | Girls | Al Jouf | Al Jouf | 29.8882 | 40.223 | 29.8882018670891,40.2230098843916 | KFM2020660179680 | 10005964628 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1011 | متوسطة خوعاء بنين | Khawaa Intermediate School for Boys | Intermediate | Boys | Al Jouf | Al Jouf | 29.7989 | 40.4427 | 29.7989481398237,40.4427148065863 | KFM2120660239654 | 10005951746 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1012 | الابتدائية السادسة والطفولة المبكرة بسكاكا (بنات) | Sixth Primary and Early Childhood School in Sakaka (Girls) | Primary | Girls | Al Jouf | Al Jouf | 29.9742 | 40.1927 | 29.974225223484,40.192669145252 | KFM2020660179658 | 10005999294 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1013 | مدرسة ابن تيمية لتحفيظ القرآن | Ibn Taymiyyah School for Quran Memorization | Primary | Boys | Al Jouf | Al Jouf | 30.1217 | 40.3891 | 30.121711968654,40.3890571902676 | KFM2120660239685 | 10005998116 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1014 | ابتدائية أم المؤمنين سودة بنت زمعة والطفولة المبكرة بقارا (بنات) | Umm Al-Mu’mineen Sawda bint Zam’a Primary and Early Childhood School in Qara (Girls) | Intermediate | Girls | Al Jouf | Al Jouf | 29.8803 | 40.2279 | 29.880306,40.227894 | KFM2020660179441 | 10083050857 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1015 | مدرسة الابتدايه الخامسه بنات | Fifth Primary School for Girls | Primary | Girls | Al Jouf | Al Jouf | 29.978 | 40.2126 | 29.978022, 40.212609 | KFM2020660075177 | 10005995428 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 3 | In Progress
|  | SS-ZAM-JOUF1016 | المدرسة المتوسطة الأولى بزلوم (بنات) | First Intermediate School in Zalum (Girls) | Intermediate | Girls | Al Jouf | Al Jouf | 30.1704 | 40.2888 | 30.17037,40.288807 | KFM2120660239622 | 10005994153 |  | 2026-04-11 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1017 | الروضة الأولى بزُلوم | First Kindergarten in Zalum | KinderGarten | Girls | Al Jouf | Al Jouf | 30.1657 | 40.3047 | 30.165747,40.304684 | KFM2120660261656 | 10093592007 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1018 | الإبتدائية الثانية والمتوسطة الأولى والثانوية الأولى لتحفيظ القران الكريم بدومة الجندل | The second primary school, the first middle school, and the first secondary school,For memorizing the Holy Quran in Doumat Al-Jandal | Primary | Girls | Al Jouf | Al Jouf | 29.8018 | 39.8568 | 29.80184,39.856838 | SMR2420661036810 | 10096518193 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1019 | مدرسة السادسة | Sixth Grade School (dhuma) | Early Childhood | Girls | Al Jouf | Al Jouf | 29.8124 | 39.8553 | 29.812437,39.855274 | KFM2020660185628 | 10006005669 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1020 | مدرسة الثالثة والعشرون | Twenty-third school | Secondary | Girls | Al Jouf | Al Jouf | 29.9786 | 40.2563 | 29.9785825290929,40.2563119984886 | KFM2020660179607 | 10005996031 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1021 | ابتدائية الطوير | Al-Tuwair Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.9139 | 40.1991 | 29.9139461591511,40.1991256020181 | KFM2020660182971 | 10005967129 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1022 | ابتدائية الوادي والبحيرات (بنات) | Al-Wadi and Al-Buhayrat Primary School (Girls) | Primary | Boys | Al Jouf | Al Jouf | 29.8327 | 39.8691 | 29.832731,39.86911 | KFM2020660182960 | 10006005856 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1023 | مدرسة الأولى بزلوم | First School in Bazloum | Intermediate | Girls | Al Jouf | Al Jouf | 30.1701 | 40.298 | 30.1700517120588,40.2979839216705 | KFM2120660240734 | 10005968556 |  | 2026-04-15 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1024 | الروضة الثانية بصوير | The second kindergarten in Suwayr | KinderGarten | Girls | Al Jouf | Al Jouf | 30.1288 | 40.3815 | 30.1287829798635,40.3814671629348 | KFM2120660239653 | 10005993488 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1025 | الابتدائية الثانية طفولة المبكرة | Second Primary Early Childhood | Early Childhood | Girls | Al Jouf | Al Jouf | 29.936 | 40.1954 | 29.9359953231781,40.195372638177 | KFM2120660239645 | 10005993460 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1026 | المتوسطة الأولى بصوير | The first intermediate school in Souir | Intermediate | Girls | Al Jouf | Al Jouf | 30.1184 | 40.3917 | 30.1184022173737,40.3917197523688 | KFM2120660239688 | 10005989510 |  | 2026-04-28 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1027 | الثانوية الاولى بصوير | The first secondary school in Souir | Secondary | Girls | Al Jouf | Al Jouf | 30.1334 | 40.3764 | 30.1333973030419,40.3764418958397 | KFM2120660239687 | 10005989538 |  | 2026-04-22 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1028 | المتوسطة الثالثة بسكاكا | Third Intermediate School in Sakaka | Intermediate | Girls | Al Jouf | Al Jouf | 29.9346 | 40.2013 | 29.9346215263527,40.2013483163728 | KFM2020660179687 | 10005989322 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1029 | الابتدائية الحادية والعشرون | Twenty-first primary school | Primary | Girls | Al Jouf | Al Jouf | 29.9497 | 40.2036 | 29.9496569845465,40.2035864607148 | KFM2020660179655 | 10005961798 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1030 | الابتدائية السادسة | Sixth Elementary School (QARA) | Primary | Girls | Al Jouf | Al Jouf | 29.9758 | 40.1929 | 29.9757722313146,40.1928533624132 | KFM2020660179642 | 10005998626 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1031 | سعد بن أبي وقاص الابتدائية | Saad bin Abi Waqqas Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.8912 | 40.2262 | 29.8911545758384,40.2261526095688 | KFM2020660179656 | 10005986723 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1032 | الابتدائية العشرون والطفولة المبكرة بسكاكا | The twentieth primary and early childhood school in Sakaka | Primary | Girls | Al Jouf | Al Jouf | 29.9619 | 40.211 | 29.9618866278234,40.2110171912494 | SMR2420661036806 | 10005996443 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1033 | المتوسطة الثانية باللقائط | The second intermediate school in Al-Laqayt | Intermediate | Girls | Al Jouf | Al Jouf | 29.9783 | 40.2395 | 29.9783368380698,40.2394675936275 | KFM2020660179608 | 10102399970 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1034 | الثانوية التاسعة بسكاكا | Ninth Secondary School in Sakaka | Secondary | Girls | Al Jouf | Al Jouf | 29.9781 | 40.2128 | 29.9781244406967,40.2127576895182 | KFM2020660075181 | 10005995446 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1035 | المتوسطة بهديب | Intermediate School in Bahdeeb | Secondary | Girls | Al Jouf | Al Jouf | 30.0617 | 40.4038 | 30.0616964694218,40.4038316757768 | KFM2120660238870 | 10005994055 |  | 2026-04-08 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1036 | الثانوية الثانية بصوير | Secondary School II in Souir | Secondary | Girls | Al Jouf | Al Jouf | 30.1294 | 40.3842 | 30.1293716824293,40.3841865600344 | KFM2120660239662 | 10005993147 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1037 | ابتدائية الثانيه و الثانويه الاولئ بالسكاكا | Second Primary and First Secondary School in Sakaka | Primary | Girls | Al Jouf | Al Jouf | 29.8032 | 40.4409 | 29.933891, 40.194796 | KFM2020660154924 | 10005989037 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1038 | المتوسطة الاولى بالرفيعة للبنات | The first intermediate school in Al-Rafi'a for girls | Intermediate | Girls | Al Jouf | Al Jouf | 30.0616 | 40.3215 | 30.0616250309494,40.3215421782807 | KFM2120660261706 | 10005992032 |  | 2026-04-11 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1039 | الابتدائية التاسعة والطفولة مبكرة | Ninth Primary and Early Childhood | Primary | Girls | Al Jouf | Al Jouf | 29.9291 | 40.1813 | 29.9290521071954,40.1812883902853 | KFM2120660235808 | 10005993067 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1040 | الثانوية الرابعة للبنات بسكاكا | The Fourth Secondary School for Girls in Sakaka | Secondary | Girls | Al Jouf | Al Jouf | 29.9014 | 40.2069 | 29.9014096918099,40.2069283243169 | KFM2120660243979 | 10005938575 |  | 2026-05-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1041 | الابتدائية الرابعة بسكاكا | The Fourth Elementary School in Sakaka | Primary | Girls | Al Jouf | Al Jouf | 29.9621 | 40.2082 | 29.9621262148975,40.2082397169139 | KFM2120660239631 | 10101200968 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1042 | الابتدائية الثالثة للبنات بسكاكا | The Third Elementary School for Girls in Sakaka | Intermediate | Girls | Al Jouf | Al Jouf | 29.9879 | 40.1971 | 29.9879422672338,40.1971181002963 | KFM2120660243980 | 10005961448 |  | 2026-04-16 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1043 | مدرسة تحفيظ القرآن الكريم فلسطين | Holy Quran Memorization School Palestine | Primary | Girls | Al Jouf | Al Jouf | 29.9903 | 40.2104 | 29.99033076994,40.2104343470852 | KFM2020660179399 | 10005966829 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1044 | مدرسة أشبيلية | Seville School | Intermediate | Boys | Al Jouf | Al Jouf | 29.9471 | 40.1999 | 29.9471112137758,40.1999078452078 | KFM2020660179689 | 10005966060 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1045 | مدرسة الأمير فهد بن بدر | Prince Fahd bin Badr School | Intermediate | Boys | Al Jouf | Al Jouf | 29.9346 | 40.1908 | 29.9346307045551,40.1907723973297 | KFM2020660179682 | 10005960834 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1046 | مدرسة الإمام مسلم | Imam Muslim School | Intermediate | Boys | Al Jouf | Al Jouf | 29.9399 | 40.2019 | 29.9398877340145,40.2018942010297 | KFM2020660179516 | 10005993227 |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
|  | SS-ZAM-JOUF1047 | مدرسة أبي أيوب الأنصاري | Abu Ayyub al-Ansari School | Primary | Boys | Al Jouf | Al Jouf | 29.9975 | 40.2587 | 29.9975095682448,40.258712764237 | KFM2020660184671 | 10095262744 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1048 | مدرسة هشام بن عبدالملك | Hisham bin Abdul Malik School | NA | Boys | Al Jouf | Al Jouf | 29.9281 | 40.1997 | 29.9281462493802,40.1996832679518 | KFM2020660182943 | 10005987346 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1049 | مدرسة بدر | Badr School | NA | Boys | Al Jouf | Al Jouf | 29.9738 | 40.1834 | 29.9737661426959,40.183374149709 | KFM2020660179582 | 10005996668 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1050 | مدرسة غرناطة | Granada School | NA | Boys | Al Jouf | Al Jouf | 29.9645 | 40.2058 | 29.9645079391734,40.2058480475997 | KFM2120660235780 | 10005985691 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1051 | مدرسة عبدالرحمن السديري | Abdulrahman Al-Sudairy School | NA | Boys | Al Jouf | Al Jouf | 29.9506 | 40.204 | 29.9506264964268,40.2040144476002 | KFM2120660238863 | 10005969188 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1052 | مدرسة الشيخ فيصل | Sheikh Faisal School | NA | Boys | Al Jouf | Al Jouf | 29.9418 | 40.2034 | 29.9418474066486,40.2033671587009 | KFM2120660235814 | 10005960914 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1053 | مدرسة سراقة بن مالك | Suraqa bin Malik School | NA | Boys | Al Jouf | Al Jouf | 29.9964 | 40.2564 | 29.9963862922224,40.2563835629409 | KFM2020660184672 | 10094125670 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1054 | مدرسة ثانوية نهاوند | Nahavand High School | Secondary | Boys | Al Jouf | Al Jouf | 29.8789 | 40.2211 | 29.8789432247977,40.2211184629465 | KFM2120660243131 | 10005938501 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1055 | المتوسطة الحادية عشر بسكاكا | Eleventh Intermediate School in Sakaka | Intermediate | Girls | Al Jouf | Al Jouf | 29.9826 | 40.1901 | 29.982569,40.190121 | KFM2120660243975 | 10084877330 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1056 | الابتدائية الاولى للطفولة المبكرة بسكاكا | The First Elementary School for Early Childhood in Sakaka | Primary | Girls | Al Jouf | Al Jouf | 29.9681 | 40.2002 | 29.968111,40.200233 | KFM2020660179408 | 10005995741 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1057 | الابتدائية الرابعة عشر و المتوسطة الثالثة عشر بسكاكا | The fourteenth primary school and the thirteenth intermediate school in Sakaka | Primary | Girls | Al Jouf | Al Jouf | 29.925 | 40.197 | 29.9249827,40.1969733 | KFM2020660182944 | 10005988058 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1058 | المتوسطة الاولى والثانوية السابعة | First Intermediate and Seventh Secondary School | Intermediate | Girls | Al Jouf | Al Jouf | 29.9144 | 40.1987 | 29.9144198,40.1986556 | KFM2020660182975 | 10005993512 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1059 | مدرسة السديرية | Al-Sudairiah School | Primary | Girls | Al Jouf | Al Jouf | 29.9521 | 40.1932 | 29.9521375272905,40.1931714543466 | KFM2020660076506 | 10005969849 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1060 | مدرسة صلاح الدين | Salah al-Din School | Intermediate | Boys | Al Jouf | Al Jouf | 29.9816 | 40.2118 | 29.9815543249356,40.2118077899274 | KFM2120660243075 | 10005970447 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1061 | مدرسة الشهداء | Martyrs School | Primary | Boys | Al Jouf | Al Jouf | 29.9733 | 40.2453 | 29.9732888661065,40.2452602949354 | KFM2020660179621 | 10005997001 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1062 | مدرسة عمار بن ياسر | Ammar ibn Yasir School | Primary | Boys | Al Jouf | Al Jouf | 29.986 | 40.2204 | 29.9860498373739,40.2204439531487 | KFM2020660179398 | 10005987829 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1063 | مدرسة صقر قريش | Saqr Quraish School | Primary | Boys | Al Jouf | Al Jouf | 29.9925 | 40.2017 | 29.992533102325,40.2016866512984 | KFM2020660179421 | 10005999187 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1064 | ابتدائية معاذ بن جبل | Muadh ibn Jabal Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.8146 | 39.8503 | 29.8146183211117,39.85025191843 | KFM2020660152238 | 10006004017 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1065 | ابتدائية الملك فهد سكاكا | King Fahd Elementary School, Sakaka | Primary | Boys | Al Jouf | Al Jouf | 29.9563 | 40.2033 | 29.956251637201,40.2032792587003 | SMR2420661037087 | 10005969811 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1066 | ابتدائية عبدالرحمن بن عوف | Abdul Rahman bin Auf Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.9542 | 40.212 | 29.9541908770074,40.2119511917786 | KFM2120660261708 | 10018941891 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1067 | ابتدائية المأمون | Al-Mamoun Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.9464 | 40.2068 | 29.9463989360251,40.2068127126721 | KFM2020660184756 | 10005969830 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1068 | ثانوية اليرموك | Yarmouk Secondary School | Secondary | Boys | Al Jouf | Al Jouf | 29.9849 | 40.2443 | 29.9848899722359,40.2442557858499 | KFM2020660179630 | 10005989233 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1069 | مدرسة الثانوية الأولى بدومة الجندل | The First Secondary School in Doumat Al-Jandal | Secondary | Girls | Al Jouf | Al Jouf | 29.8096 | 39.8683 | 29.8095657809901,39.8683392566426 | KFM2020660185748 | 10006004161 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1070 | مدرسة التاسعة عشر طفولة مبكرة | Nineteenth Early Childhood School | Early Childhood | Girls | Al Jouf | Al Jouf | 29.9971 | 40.2068 | 29.997112,40.206829 | KFM2020660179430 | 10084592797 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1071 | مدرسة الأولى بقارا | First School in Qara | Primary | Girls | Al Jouf | Al Jouf | 29.8966 | 40.2186 | 29.8966162620251,40.218583422248 | KFM2020660179675 | 10005964593 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1072 | مدرسة الثالثة بقارا | Third School in Qara | Primary | Girls | Al Jouf | Al Jouf | 29.8782 | 40.2134 | 29.8781611539218,40.2134335811022 | KFM2020660179641 | 10005970465 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1073 | مدرسة ابتدائية ثانوية في قارة | Secondary Elementary School in Qara | Primary | Girls | Al Jouf | Al Jouf | 29.8648 | 40.2236 | 29.8647641779916,40.2236474327081 | KFM2020660179531 | 10083053367 |  | 2026-04-19 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1074 | مدرسة الخامسة بقارا | Fifth School in Qara | Primary | Girls | Al Jouf | Al Jouf | 29.8821 | 40.2357 | 29.8821054762545,40.2357495593655 | KFM2020660179619 | 10005996891 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1075 | مدرسة الطفوله المبكره الاولي باللقائط | Al-Laqayt Early Childhood School | Early Childhood | Girls | Al Jouf | Al Jouf | 29.9851 | 40.2432 | 29.9850981890971,40.2431904875346 | KFM2020660179485 | 10005992014 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1076 | مدرسة الطفوله المبكره الثانية باللقائط | Al-Laqayt Second Early Childhood School | Early Childhood | Girls | Al Jouf | Al Jouf | 29.9934 | 40.2321 | 29.9933925518232,40.2320838016434 | KFM2020660184680 | 10005992328 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1077 | الثانوية العاشرة بسكاكا بنات | The Tenth Secondary School in Sakaka (Girls) | Secondary | Girls | Al Jouf | Al Jouf | 29.945 | 40.1971 | 29.944967,40.197102 | KFM2020660179685 | 10005993183 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1078 | مدرسة الثانية عشرة | Twelfth grade school | Primary | Girls | Al Jouf | Al Jouf | 29.9972 | 40.2202 | 29.9971735596952,40.2202283407594 | KFM2120660244001 | 10088974449 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1079 | مدرسة الخامسة والعشرون | Twenty-Fifth School | Primary | Girls | Al Jouf | Al Jouf | 29.9479 | 40.2106 | 29.9479053382052,40.2106442507579 | KFM2120660238783 | 10005993844 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1080 | مدرسة الروضة الرابعة | Fourth Kindergarten School | Primary | Girls | Al Jouf | Al Jouf | 29.9339 | 40.2015 | 29.9339435583701,40.2014563280156 | KFM2120660235813 | 10005989396 |  | 2026-05-04 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1081 | الابتدائية السابعة عشر | Seventeenth Elementary School | Primary | Girls | Al Jouf | Al Jouf | 29.9344 | 40.196 | 29.9344314387455,40.1959871814443 | KFM2120660235807 | 10019035262 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1082 | مدرسة الابتدائية الخامسة عشر | 15th Elementary School | Primary | Girls | Al Jouf | Al Jouf | 29.9488 | 40.2769 | 29.9487967876474,40.2768993683529 | KFM2020660182946 | 10005989369 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1083 | مدرسة المتوسطة الرابعة | Fourth Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 31.3263 | 37.3287 | 31.3262528784571,37.3286888790201 | SMR2220661010477 | 10084462729 |  | 2026-05-07 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1084 | المدرسة الابتدائية الرابعة للطفولة المبكرة بدومة الجندل | The Fourth Elementary School for Early Childhood in Dumat al-Jandal | Primary | Girls | Al Jouf | Al Jouf | 29.8198 | 39.8563 | 29.819754,39.856339 | SMR2420668002100 | 10105089792 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1085 | المدرسة المتوسطة الرابعة بدومة الجندل | Fourth Intermediate School in Dumat Al-Jandal | Intermediate | Girls | Al Jouf | Al Jouf | 29.8086 | 39.8467 | 29.80855,39.846706 | KFM2020660184803 | 10006004330 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1086 | الابتدائية الأولى بدومة الجندل | First Primary School in Dumat Al-Jandal | Primary | Girls | Al Jouf | Al Jouf | 29.8069 | 39.8702 | 29.806881,39.870239 | KFM2020660182940 | 10005985440 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1087 | مدرسة عمر بن عبدالعزيز | Omar bin Abdulaziz School | Intermediate | Boys | Al Jouf | Al Jouf | 29.9898 | 40.2437 | 29.9898052534519,40.2436676052697 | KFM2020660179636 | 10005987220 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1088 | مدرسة الاندلس | Andalus School | Primary | Boys | Al Jouf | Al Jouf | 29.9165 | 40.1946 | 29.9164633789131,40.1945777711612 | KFM2020660182973 | 10005938486 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1089 | مدرسة عبادة بن الصامت | Ubadah ibn al-Samit School | Primary | Boys | Al Jouf | Al Jouf | 29.9032 | 40.203 | 29.9032265701304,40.2029543341096 | KFM2020660179443 | 10091300551 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1090 | ابتدائية الأضارع بنين | Al-Adhraa Elementary School for Boys | Primary | Boys | Al Jouf | Al Jouf | 29.8283 | 39.5734 | 29.828272,39.573425 | KFM2020660182997 | 10006006030 |  | 2026-04-19 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1091 | مدرسة الشيخ ابن باز | Sheikh Ibn Baz School | Secondary | Boys | Al Jouf | Al Jouf | 29.8283 | 39.5734 | 29.828272,39.573425 | KFM2020660182902 | 10006003781 |  | 2026-04-21 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1092 | مدرسة الروضة الأولى | First Kindergarten School | KinderGarten | Girls | Al Jouf | Al Jouf | 30.5056 | 38.2165 | 30.505611,38.2164992 | KFM2020660179407 | 30132937711 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1093 | مدرسة الثانوية الثانية (Qara) | Secondary School II (Qara) | Secondary | Girls | Al Jouf | Al Jouf | 29.8908 | 40.2182 | 29.8907751,40.2182325 | kfm2020660177678 | 30015076901 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1094 | متوسطة الأضارع | Medium-sized | Intermediate | Boys | Al Jouf | Al Jouf | 29.8321 | 39.5716 | 29.832069,39.571625 | KFM2120660236896 | 10005988998 |  | 2026-04-19 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1095 | مدرسة ثانوية الرديفة | Al-Radifah Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 29.8026 | 39.6892 | 29.802591,39.689228 | KFM2020660182987 | 10097801796 |  | 2026-04-21 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1096 | ابتدائية الطفوله المبكره بالأضارع | Early Childhood Elementary School in Al-Adhra' | Early Childhood | Girls | Al Jouf | Al Jouf | 29.8321 | 39.5721 | 29.832115,39.572067 | KFM2020660184740 | 10006005991 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1097 | ابتدائية الأضارع بنات | Al-Adhraa Girls Elementary School | Primary | Girls | Al Jouf | Al Jouf | 29.8321 | 39.5721 | 29.832115,39.572067 | KFM2020660182901 | 10097745491 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1098 | الروضة الحكومية بالدريفة | Government Kindergarten in Al-Duraifa | Primary | Girls | Al Jouf | Al Jouf | 29.8027 | 39.6897 | 29.80266,39.689747 | KFM2020660182990 | 10006004518 |  | 2026-04-22 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1099 | متوسطة دومة الجندل | Dumat Al-Jandal Intermediate School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8101 | 39.857 | 29.810053,39.857006 | KFM2020660184792 | 10005985360 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1100 | مدرسة الأمير نايف بن عبد العزيز | Prince Nayef bin Abdulaziz School | Secondary | Boys | Al Jouf | Al Jouf | 29.81 | 39.8569 | 29.810047,39.85685 | KFM2120660238808 | 10006005524 |  | 2026-04-22 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1101 | مدرسة عثمان بن عفان | Othman ibn Affan School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8158 | 39.859 | 29.815826,39.859005 | KFM2020660184800 | 10086683943 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1102 | مدرسة سعيد بن زيد | Saeed bin Zaid School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8141 | 39.8438 | 29.814095,39.843781 | KFM2020660184796 | 10005974132 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1103 | مدرسة موسى بن نصير | Musa ibn Nusayr School | Primary | Boys | Al Jouf | Al Jouf | 29.7982 | 39.8764 | 29.798225,39.876385 | KFM2020660182050 | 10006005041 |  | 2026-04-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1104 | مدرسة الملك سعود بن عبد العزيز | King Saud bin Abdulaziz School | Secondary | Boys | Al Jouf | Al Jouf | 29.8069 | 39.8547 | 29.806879,39.854713 | KFM2020660182053 | 10005985403 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1105 | مدرسة عمرو بن العاص | Amr ibn al-Aas School | Primary | Boys | Al Jouf | Al Jouf | 29.8278 | 39.8782 | 29.8278055,39.8782286 | SMR2420668002104 | 10006004984 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1106 | مدرسة عبد الله بن عمر | Abdullah bin Omar School | Primary | Boys | Al Jouf | Al Jouf | 29.817 | 39.856 | 29.817039,39.855995 | SMR2420668002076 | 10005985225 |  | 2026-04-14 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1107 | مدرسة الأمام الشاطبي | Imam Al-Shatibi School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8132 | 39.8533 | 29.813166,39.853306 | SMR2420661037092 | 10085532846 |  | 2026-04-26 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1108 | مدرسة الثالثة | Third School (DHUMA) | Primary | Girls | Al Jouf | Al Jouf | 29.8086 | 39.8467 | 29.80855,39.846706 | KFM2020660184801 | 10006004349 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1109 | المتوسطة الثالثة و الثانوية الثانية بدومة الجندل | The third intermediate school and the second secondary school in Doumat Al-Jandal | Intermediate | Girls | Al Jouf | Al Jouf | 29.7956 | 39.8744 | 29.795567,39.874416 | KFM2120660238820 | 10095708040 |  | 2026-04-15 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1110 | مدرسة ابتدائية ابن خلدون | Ibn Khaldoun Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.9503 | 40.1974 | 29.950285,40.197376 | KFM2020660182948 | 10005969821 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1111 | المدرسه المتوسطه السابعه و الثانويه السادسه | Seventh Intermediate and Sixth Secondary School | Intermediate | Girls | Al Jouf | Al Jouf | 29.9341 | 40.1944 | 29.9341191656329, 40.1943880770686 | KFM2020660154925 | 10005986732 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 3 | In Progress
|  | SS-ZAM-JOUF1112 | مدرسة الاولى بزلوم | First School in Zaloum | Secondary | Girls | Al Jouf | Al Jouf | 30.1675 | 40.3006 | 30.1675029033775,40.3005770535439 | KFM2120660261655 | 10005996757 |  | 2026-04-14 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1113 | مدرسة سعد بن عبادة | Saad bin Ubadah School | Primary | Girls | Al Jouf | Al Jouf | 29.8885 | 39.3072 | 29.88855,39.307232 | KFM2020660182011 | 10006007494 |  | 2026-05-02 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1114 | مدرسة عذفاء (BOYS) | Adhfaa School (BOYS) | Primary | Boys | Al Jouf | Al Jouf | 29.251 | 41.4427 | 29.250998584967,41.4427071485333 | KFM2120660243954 | 10005961072 |  | 2026-04-04 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1115 | مدرسة الابتدائية الأولى | First Elementary School (THABARJAL) | Primary | Girls | Al Jouf | Al Jouf | 30.5003 | 38.2238 | 30.500349,38.223778 | KFM2120660242487 | 10006001534 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1116 | مدرسة الابتدائية السادسة | Sixth Elementary School (thabarjal) | Primary | Girls | Al Jouf | Al Jouf | 29.8838 | 40.2151 | 29.8838071851153,40.2151358505083 | KFM2120660242488 | 10006043928 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1117 | مدرسة عذفاء الابتدائية | Adhfaa Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.2471 | 41.445 | 29.2470788016569,41.4450162113748 | AEC2020830306498 | 10092968724 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1118 | مدرسة الأمير فهد بن جلوي | Prince Fahd bin Jalawi School | Intermediate | Boys | Al Jouf | Al Jouf | 29.9473 | 40.1826 | 29.9473005713569,40.1826378782861 | KFM2120660239630 | 10101207092 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1119 | Iلمتطوسطه و الثانويه الوادي والبحيرات (بنات) | Al-Wadi and Al-Buhayrat Intermediate and Secondary School (Girls) | Intermediate | Girls | Al Jouf | Al Jouf | 29.8328 | 39.8694 | SMR2420668002093 | 10006004859 |  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 0 | 0 | In Progress | Not Started
|  | SS-ZAM-JOUF1120 | مدرسة ب العشرون بالقريات | Twenty-year-old school in Al-Qurayyat | Primary | Girls | Al Jouf | Al Jouf | 31.3247 | 37.3536 | 31.3247075065219,37.3536136472949 | KFM2020660182826 | 10006011316 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1121 | مدرسة الثانوية العاشرة | Tenth Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 31.3382 | 37.3244 | 31.3381899567072,37.3244413858032 | KFM2020660182846 | 10005977107 |  | 2026-04-15 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1122 | مدرسة الثانوية التاسعة | Ninth Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 31.3449 | 37.3466 | 31.344873061164,37.3465568046776 | Kfm2020660182758 | 10005979433 |  | 2026-04-30 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1123 | مدرسة المتوسطة السابعة | Seventh Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 31.3424 | 37.3481 | 31.3423539992988,37.3480779386375 | Kfm2020660182760 | 10005979255 |  | 2026-05-03 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1124 | مدرسة الابتدائية السادسة بالقريات | Al-Qurayyat Sixth Primary School | Primary | Girls | Al Jouf | Al Jouf | 31.3421 | 37.3394 | 31.3421081580301,37.3394052742777 | KFM2020660182757 | 10006009480 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1125 | مدرسة الابتدائية الرابعة بالقريات | Fourth Primary School in Al-Qurayyat | Primary | Girls | Al Jouf | Al Jouf | 31.3376 | 37.324 | 31.3376028924908,37.3239965885799 | KFM2020760221344 | 10018876101 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1126 | مدرسة المتوسطة الثامنة | 8th Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 31.3182 | 37.3474 | 31.3181958164311,37.3474119104394 | KFM2020660182860 | 10005977582 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1127 | مدرسة ابتدائية ابو موسى الأشعري | Abu Musa Al-Ash'ari Elementary School | intermediate | Boys | Al Jouf | Al Jouf | 31.2975 | 37.3372 | 31.2974896673903,37.337196841654 | Kfm2020660182710 | 10005979891 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1128 | مدرسة الابتدائية الخامسة بالقريات | Fifth Elementary School in Al-Qurayyat | Primary | Girls | Al Jouf | Al Jouf | 31.331 | 37.356 | 31.3310272520545,37.3560423017034 | KFM2020660182796 | 10005979166 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1129 | مدرسة ابتدائية علي بن ابي طالب | Ali bin Abi Talib Elementary School | Primary | Boys | Al Jouf | Al Jouf | 31.3279 | 37.3773 | 31.327858964721,37.3772992023712 | Kfm2020660180787 | 10005978211 |  | 2026-04-27 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1130 | مدرسة الثانوية الرابعة عشر | Fourteenth Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 31.3266 | 37.329 | 31.3265755067587,37.3290459956254 | Kfm2020660182900 | 10006043721 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1131 | مدرسة المتوسطة الثانية عشر | Twelfth Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 31.3381 | 37.325 | 31.3380587455722,37.3249830570332 | Kfm2020660182787 | 10005977116 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1132 | مدرسة المتوسطة السابعة عشر | Seventeenth Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 31.3061 | 37.3455 | 31.3060675070408,37.3454622337363 | Kfm2020660180645 | 10006043104 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1133 | الابتدائية الثامنة عشر | Eighteenth Primary School | Intermediate | Girls | Al Jouf | Al Jouf | 31.326 | 37.3294 | 31.3259788606386,37.3293862637503 | Kfm2020660182897 | 10006009819 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1134 | ثانوية الانصار بالنبك | Al-Ansar Secondary School in Al-Nabk | Secondary | Boys | Al Jouf | Al Jouf | 30.294 | 38.7016 | 30.29398,38.701572 | KFM2120660242441 | 10006028609 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1135 | الابتدائية الثانية | Second Primary School (Thabarjal) | Primary | Girls | Al Jouf | Al Jouf | 30.4989 | 38.2135 | 30.4988501131817,38.2134742964029 | KFM2020660158502 | 10006026730 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1136 | المتوسطة الخامسة | Fifth Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 30.4996 | 38.2106 | 30.499578,38.210567 | KFM2020660158636 | 10006027361 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1137 | الابتدائية الثانية للتحفيظ في طبرجل | The second primary school for memorization in Tabarjal | Primary | Girls | Al Jouf | Al Jouf | 30.4984 | 38.2134 | 30.498439,38.2134341 | KFM2120660242506 | 10087907601 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1138 | مدرسة ابن بطوطة | Ibn Battuta School | Primary | Boys | Al Jouf | Al Jouf | 30.4969 | 38.2037 | 30.4969225907132,38.2036528837116 | KFM2120660242428 | 10006042199 |  | 2026-05-07 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1139 | مدرسة أبي سعيد الخدري | Abu Saeed Al-Khudri School | Primary | Boys | Al Jouf | Al Jouf | 30.4979 | 38.2033 | 30.4978652581413,38.2032633771842 | KFM2120660242434 | 10006042180 |  | 2026-05-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1140 | مدرسة الامام البخاري | Imam Bukhari School | Primary | Boys | Al Jouf | Al Jouf | 30.4761 | 38.2126 | 30.4760545853415,38.2125684973605 | KFM2120660237850 | 10006043866 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1141 | مدرسة جعفر الطيار | Jaafar Al-Tayyar School | Primary | Boys | Al Jouf | Al Jouf | 30.5002 | 38.1946 | 30.5002397205731,38.1946098941248 | KFM2120660242483 | 10006027343 |  | 2026-05-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1142 | مدرسة الثانوية الرابعة | Fourth Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 30.4972 | 38.2019 | 30.4972236132065,38.2019311465938 | SMR2220661014774 | 10104196822 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1143 | متوسطة الملك عبد الله بن عبدالعزيز | King Abdullah bin Abdulaziz Intermediate School | Intermediate | Boys | Al Jouf | Al Jouf | 30.487 | 38.2556 | 30.4870414907069,38.2555634883431 | KFM2120660243846 | 10006011460 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1144 | مدرسة قتيبة بن مسلم | Qutayba ibn Muslim School | Secondary | Boys | Al Jouf | Al Jouf | 30.487 | 38.2556 | 30.4869958431849,38.2555848467021 | KFM2120660237937 | 10086056701 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1145 | مدرسة حمزة بن عبد المطلب | Hamza ibn Abdul Muttalib School | Primary | Boys | Al Jouf | Al Jouf | 30.5037 | 38.2214 | 30.5037099858784,38.221368524478 | KFM2120660243783 | 10093190001 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1146 | مدرسة خالد بن الوليد | Khalid ibn al-Walid School | Primary | Boys | Al Jouf | Al Jouf | 30.487 | 38.2556 | 30.4870414907069,38.2555634883431 | KFM2120660243777 | 10006026776 |  | 2026-05-07 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1147 | مدرسة زيد بن ثابت | Zaid bin Thabit School | Primary | Boys | Al Jouf | Al Jouf | 30.487 | 38.2556 | 30.4869958431849,38.2555848467021 | KFM2120660242563 | 10006042635 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1148 | مدرسة علي بن أبي طالب | Ali ibn Abi Talib School | Primary | Boys | Al Jouf | Al Jouf | 30.5037 | 38.2214 | 30.5037099858784,38.221368524478 | KFM2120660237911 | 10084703681 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1149 | ابتدائية النباج للبنات | Al-Nabaj Elementary School for Girls | Primary | Boys | Al Jouf | Al Jouf | 30.4338 | 38.4009 | 30.4337635,38.4009182 | KFM2120660242543 | 10006011147 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1150 | مدرسة الابتدائية السابعة | Seventh Elementary School | Primary | Girls | Al Jouf | Al Jouf | 30.4739 | 38.2345 | 30.4738955211299,38.2345448199455 | KFM2120660242517 | 10006042214 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1151 | مدرسة الابتدائية الثالثة | Third Primary School | Primary | Girls | Al Jouf | Al Jouf | 30.4923 | 38.253 | 30.4922649679137,38.2529874846669 | KFM2120660243849 | 10006043392 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1152 | ابتدائية ميقوع للبنين | Miqou' Elementary School for Boys | Primary | Boys | Al Jouf | Al Jouf | 29.8166 | 38.9156 | 29.816629,38.915646 | SMR2220661010332 | 10005973322 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1153 | متوسطة معاوية بن أبي سفيان | Muawiyah bin Abi Sufyan Intermediate School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8144 | 38.9125 | 29.814423,38.912457 | KFM2020660182916 | 10006006085 |  | 2026-05-06 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1154 | مدرسة اصفان بنات | Asfan Girls School | Primary | Girls | Al Jouf | Al Jouf | 29.6672 | 39.6671 | 29.667194,39.667053 | KFM2120660245535 | 10006004447 |  | 2026-04-26 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1155 | مدرسة ابتدائيه الثانيه سكاكا | Second Primary School in Sakakka | Primary | Girls | Al Jouf | Al Jouf | 29.9889 | 40.2085 | 29.9889243898008, 40.2084716373593 | KFM2020660179637 | 10005968636 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1156 | ابتدائية رُفيدة الأنصارية للطفولة المبكرة بدومة الجندل للبنات | Rufaidah Al-Ansariyah Early Childhood Primary School | Primary | Girls | Al Jouf | Al Jouf | 29.8054 | 39.8613 | 29.805441,39.861313 | KFM2020660184769 | 10005984729 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1157 | مدرسة الشقيق | Al Shaqiq Secondary School – Girls | Secondary | Girls | Al Jouf | Al Jouf | 29.301 | 39.9162 | 29.300968,39.916157 | KFM2120660236882 | 10006003922 |  | 2026-05-06 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1158 | متوسطة الفياض | Al-Fayyadh Intermediate School | Intermediate | Boys | Al Jouf | Al Jouf | 30.5937 | 38.1077 | 30.593657,38.107697 | KFM2120660243852 | 10006027245 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1159 | مدرسة بلال بن رباح | Bilal bin Rabah School | Primary | Boys | Al Jouf | Al Jouf | 30.5931 | 38.1079 | 30.5930684,38.1079287 | KFM2020660158520 | 10006042045 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1160 | ابتدائية الفياض | Al-Fayyadh Elementary School | Primary | Boys | Al Jouf | Al Jouf | 30.591 | 38.1073 | 30.590986,38.107262 | SMR2220661014737 | 10100288882 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1161 | مدرسة اصفان بنين | Asfan Boys School | Secondary | Boys | Al Jouf | Al Jouf | 29.667 | 39.6718 | 29.666988,39.671791 | KFM2120660243922 | 10006006989 |  | 2026-04-27 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1162 | مدرسة الابتدائية الأولى بحدرج | Hadraj First Primary School | Primary | Girls | Al Jouf | Al Jouf | 30.5203 | 38.2033 | 30.520271,38.203251 | KFM2120660237793 | 10006042018 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1163 | مدرسة ابتدائية أم المؤمنين زينب | Umm Al-Mu'minin Zainab Elementary School | Primary | Girls | Al Jouf | Al Jouf | 30.5211 | 38.2043 | 30.5211227,38.2043411 | KFM2120660237790 | 10006011998 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1164 | المتوسطة الثالثة بطبرجل | The Third Intermediate School in Tabarjal | Intermediate | Girls | Al Jouf | Al Jouf | 30.4901 | 38.2533 | 30.490133,38.253315 | KFM2120660243854 | 10006043418 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1165 | مدرسة ابتدائية حليمة السعدية و متوسطة, رضي الله عنها , أم المؤمنين خديجة بنت خويلد, رضي الله عنها | Halima Al-Saadia Elementary School and Intermediate School, May Allah be pleased with her, Umm Al-Mu'mineen Khadija bint Khuwailid,May Allah be pleased with her | Primary | Girls | Al Jouf | Al Jouf | 30.4742 | 38.2406 | 30.474216,38.240597 | KFM2120660242533 | 10084707321 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1166 | مدرسة الثانوية الأولى | First Secondary School (THABARJAL) | Secondary | Girls | Al Jouf | Al Jouf | 30.5011 | 38.2233 | 30.5011210128645,38.223296304202 | KFM2120660242489 | 10006043919 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1167 | مدرسة الأولى بأبو عجرم | First School in Abu Ajram | Primary | Girls | Al Jouf | Al Jouf | 29.8918 | 39.306 | 29.891836,39.305969 | KFM2020660181949 | 10006005177 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1168 | متوسطة أبو عجرم | Abu Ajram Intermediate School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8921 | 39.3056 | 29.892126,39.305599 | MMF2420601016831 | 10005989261 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1169 | مدرسة المتوسطة الأولى | First Intermediate School (Tubarjal) | Intermediate | Girls | Al Jouf | Al Jouf | 30.5068 | 38.216 | 30.5067794983064,38.2160472096335 | KFM2120660237823 | 10006027853 |  | 2026-05-05 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1170 | مدرسة الثانوية بالفياض | Al-Fayyadh Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 30.5907 | 38.1065 | 30.5907,38.106491 | KFM2020660158509 | 10006029025 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1171 | الابتدائية الثامنة بطبرجل | The eighth primary school in Tabarjal | Primary | Girls | Al Jouf | Al Jouf | 30.5066 | 38.2168 | 30.5066400800273,38.2167975582566 | KFM2120660237819 | 10006027817 |  | 2026-05-04 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1172 | متوسطة ابو عجرم بنين | Abu Ajram Intermediate School for Boys | Intermediate | Boys | Al Jouf | Al Jouf | 29.8888 | 39.3088 | 29.888781,39.308838 | KFM2120660236939 | 10006007028 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1173 | الابتدائية الثانية بأبو عجرم | The second primary school in Abu Ajram | Primary | Girls | Al Jouf | Al Jouf | 29.89 | 39.3021 | 29.890005,39.302147 | KFM2020660181941 | 10006003637 |  | 2026-05-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1174 | الابتدائية الحادية عشر بطبرجل | Eleventh Primary School in Tabarjal | Primary | Girls | Al Jouf | Al Jouf | 30.5052 | 38.2328 | 30.5052248296382,38.2328183848736 | KFM2120660242502 | 10006043884 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1175 | الابتدائية التاسعة طفولة مبكرة بطبرجل | Ninth Elementary Early Childhood School in Tabarjal | Early Childhood | Girls | Al Jouf | Al Jouf | 30.4807 | 38.2161 | 30.4806928672962,38.2161349942903 | KFM2120660237846 | 10084328122 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1176 | الابتدائية العاشرة بطبرجل | Tabarjal Tenth Primary School | Primary | Girls | Al Jouf | Al Jouf | 30.5023 | 38.2025 | 30.5023030403562,38.2025270783435 | KFM2120660237919 | 10006043964 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1177 | ابتدائية الثالثة والطفولة المبكرة بدومة الجندل - بنات | Third Elementary and Early Childhood School –Dumat Al-Jandal (Girls) | Primary | Girls | Al Jouf | Al Jouf | 29.795 | 39.8739 | 29.794996,39.873928 | KFM2020660184795 | 10005984943 |  | 2026-04-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1178 | متوسطة وثانوية الاولى بحدرج | Intermediate and Secondary School I in Hadraj | Intermediate | Girls | Al Jouf | Al Jouf | 30.5137 | 38.2134 | 30.5136897,38.2133675 | KFM2120660237791 | 10006043875 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1179 | مدرسة الأمير عبد الله بن جلوي | Prince Abdullah bin Jalawi School | Intermediate | Boys | Al Jouf | Al Jouf | 29.8019 | 39.8517 | 29.801853,39.851734 | KFM2020660184819 | 10006004527 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1180 | مدرسة السابعة | Seventh School | Primary | Girls | Al Jouf | Al Jouf | 29.8087 | 39.8478 | 29.808693,39.847805 | KFM2020660185688 | 10006004321 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1181 | الروضة الأولى في طبرجل، | The First Kindergarten in Tabarjal | KinderGarten | Girls | Al Jouf | Al Jouf | 30.5054 | 38.2165 | 30.5054,38.216541 | SMR2420661037204 | 10006027835 |  | 2026-05-03 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1182 | مدرسة الثانوية الحادية عشرة | Eleventh Secondary School | Secondary | Girls | Al Jouf | Al Jouf | 31.3188 | 37.3472 | 31.3187984832071,37.3471771520669 | Kfm2020660182855 | 10006043285 |  | 2026-04-26 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1183 | مدرسة الثانوية الثانية(Thabarjal) | Secondary School II in Thabarjal | Secondary | Girls | Al Jouf | Al Jouf | 30.5062 | 38.2159 | 30.506172,38.215912 | KFM2120660237818 | 10006027871 |  | 2026-05-04 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1184 | الابتدائية الخامسة والطفولة المبكرة بطبرجل | Fifth Elementary and Early Childhood in Tabarjal | Primary | Girls | Al Jouf | Al Jouf | 30.4982 | 38.2085 | 30.498165,38.208549 | KFM2120660242513 | 10006011049 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1185 | ابتدائية تحفيظ القرآن الكريم الأولى بطبب رجالترحب بكم” | “The First Primary Quran Memorization School in Tabb Rajal | Primary | Girls | Al Jouf | Al Jouf | 30.5046 | 38.2129 | 30.50457,38.212868 | KFM2120660237817 | 10006013867 |  | 2026-05-05 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1186 | مدرسة النبيك الابتدائية لتحفيظ القرآن الكريم / مدرسة متوسطة أبي عمرو البصري | Al-Nabik Primary School for Quran Memorization & Abi Amr Al-Basri Intermediate School | Primary | Boys | Al Jouf | Al Jouf | 30.2927 | 38.7024 | 30.292685,38.702396 | SMR2320661029139 | 10006001365 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1187 | المدرسة الثانوية الأولى والمتوسطة الثالثة | First Secondary and Third Intermediate School (Girls) | Secondary | Girls | Al Jouf | Al Jouf | 31.3306 | 37.3564 | 31.330587,37.356392 | KFM2020660182746 | 10005978472 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1188 | مدرسة ب السادسة والعشرون بالقريات | School G, 26th, Al-Qurayyat | Primary | Girls | Al Jouf | Al Jouf | 31.3001 | 37.3384 | 31.3000815695691,37.3383934994072 | KFM2020660180644 | 10006042724 |  | 2025-05-02 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1189 | المدرسة الثانوية الخامسة (بنات) | fifth secondary school | Secondary | Girls | Al Jouf | Al Jouf | 31.3467 | 37.3361 | 31.3466584258551,37.3361234288351 | KFM2020660182789 | 10006042134 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1190 | المدرسة المتوسطة الرابعة | The Fourth Intermediate School | Intermediate | Girls | Al Jouf | Al Jouf | 29.8086 | 39.8467 | 29.80855,39.846706 | KFM2020660182899 | 10006011961 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1191 | مدرسة أم حبيبة للطفولة المبكرة | Umm Habiba Early Childhood School | Early Childhood | Girls | Al Jouf | Al Jouf | 31.3065 | 37.3456 | 31.3064722,37.3455833 | KFM2020660180641 | 10006043061 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
|  | SS-ZAM-JOUF1192 | مدرسة ابتدائية هارون الرشيد | Harun Al Rashid Elementary School | Primary | Boys | Al Jouf | Al Jouf | 29.8725 | 40.2225 | 29.872505,40.222515 | kfm2020660180750 | 10005980229 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1193 | مدرسة ابن رشد | Ibn Rushd School | Primary | Boys | Al Jouf | Al Jouf | 30.1318 | 40.3764 | 30.1318465353351,40.3764419899202 | KFM2120660239565 | 10005996424 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1194 | مدرسة عبد الله بن مسعود | Abdullah bin Masoud School | Primary | Boys | Al Jouf | Al Jouf | 30.1184 | 40.3892 | 30.118429983543,40.3892295698923 | KFM2120660238766 | 10005993989 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1195 | الابتدائية الاولى بهديب | The first elementary school in Hedeib | Primary | Girls | Al Jouf | Al Jouf | 30.0637 | 40.3936 | 30.0637295823545,40.3936393601444 | SMR2220661010372 | 10005967890 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1196 | مدرسة أبي عبيدة | Abu Ubaidah School | Secondary | Boys | Al Jouf | Al Jouf | 29.9789 | 40.2063 | 29.9788733435757,40.2063125052704 | KFM2120660243187 | 10005970634 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
|  | SS-ZAM-JOUF1197 | مدرسة جابر بن حيان | Jabir ibn Hayyan School | Secondary | Boys | Al Jouf | Al Jouf | 29.8615 | 40.2174 | 29.8614942574922,40.2173517513045 | KFM2020660179612 | 10005998608 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1198 | مدرسة أحمد بن حنبل | Ahmad ibn Hanbal School | Primary | Boys | Al Jouf | Al Jouf | 29.9339 | 40.1979 | 29.9339194560175,40.1979232108225 | KFM2020660154927 | 10005940706 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1199 | مدرسة تحفيظ القرآن بهدبان | Quran Memorization School in Hadban | Primary | Girls | Al Jouf | Al Jouf | 30.0731 | 40.3548 | 30.0730681969584,40.3548242822516 | KFM2120660238755 | 10005988076 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
|  | SS-ZAM-JOUF1200 | ابتدائية ومتوسطة هديان لتحفيظ القرآن الكريم | Hadyan Elementary and Intermediate School for Memorizing the Holy Quran | Intermediate | Girls | Al Jouf | Al Jouf | 30.0728 | 40.3546 | 30.072765,40.354591 | KFM2120660238764 | 10005996327 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 1 | 4 | In Progress
[14 empty] | Total | Completed | 154 | 154 | 154 | 154 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 41.8
[15 empty] | In Progress | 0 | 0 | 0 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154
[15 empty] | Not Started | 46 | 46 | 46 | 46 | 72 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 45
Note on O4: 4/2/2025
Note on P4: 4/2/2025

## Hail Schools -1
|  |  | Report Date | 2026-05-10
|  | Schools Information | [12 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
Project | School No | School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordinates |  | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Hail Schools 3.0 MWp | 1 | SS-ZAM-HAIL1001 | مدرسة ابتدائية ابن الهيثم | Ibn Al-Haytham Elementary School | Primary | Boys | Hail | Hail | 27.4947 | 41.6725 | 27.494706,41.672457 | KFM2120660258760 | 10041878778 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | Primary | Boys | Not Started
| 2 | SS-ZAM-HAIL1002 | مدرسة الملك عبد الله بن عبد العزيز المتوسطة | King Abdullah Bin Abdulaziz Intermediate School | Intermediate | Boys | Hail | Hail | 27.4884 | 41.6882 | 27.488438,41.688207 | KFM2020660211924 | 10041719459 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | Intermediate | Girls | In Progress
| 3 | SS-ZAM-HAIL1003 | مدرسة إبتدائية بن باز | Bin Baz Elementary School | Primary | Boys | Hail | Hail | 27.4889 | 41.6879 | 27.488933,41.687945 | KFM2020660211936 | 10041922034 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | Secondary | NA | Completed
| 4 | SS-ZAM-HAIL1004 | مدرسة متوسطة عبادة بن الصامت | Ubadah Ibn Al-Samit Intermediate School | Intermediate | Boys | Hail | Hail | 27.4984 | 41.678 | 27.498398,41.677973 | KFM2020660232305 | 10041609724 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | Kindergarten |  | NA
| 5 | SS-ZAM-HAIL1005 | الروضة الرابعة عشر | Kindergarten Fourteen | Kindergarten | Girls | Hail | Hail | 27.5111 | 41.7063 | 27.511117,41.706348 | KFM2020660211897 | 10041431564 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | Early Childhood
| 6 | SS-ZAM-HAIL1006 | المدرسة المتوسطة الثانية | Second Intermediate School | Intermediate | Girls | Hail | Hail | 27.5227 | 41.6831 | 27.522716054561,41.6831072713425 | KFM2020660170368 | 10041523049 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress | NA
| 7 | SS-ZAM-HAIL1007 | ابتدائية تحفيظ القران الخامسة بحائل | Fifth Quran Memorization Elementary School in Hail | Primary | Girls | Hail | Hail | 27.5045 | 41.6712 | 27.50454113,41.67122841 | KFM2020660232585 | 10041657571 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 8 | SS-ZAM-HAIL1008 | المدرسة الابتدائية الواحدة والخمسون | The fifty-first elementary school | Primary | Girls | Hail | Hail | 27.5047 | 41.6718 | 27.50469814,41.6718185 | KFM2020660232586 | 10041628031 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 9 | SS-ZAM-HAIL1009 | الثانوية الثانية والعشرون - مسارات | Twenty-second secondary school - Pathways | Secondary | Girls | Hail | Hail | 27.505 | 41.6713 | 27.505037,41.671334 | KFM2020660232583 | 10041628158 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 10 | SS-ZAM-HAIL1010 | المتوسطة التاسعة بحائل | Ninth Intermediate School in Hail | Intermediate | Girls | Hail | Hail | 27.5052 | 41.6713 | 27.50515513,41.6713371 | KFM2020660232581 | 10041527478 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 11 | SS-ZAM-HAIL1011 | مدرسة ابن ماجة الابتدائية | Ibn Majah Elementary School | Primary | Boys | Hail | Hail | 27.4939 | 41.6882 | 27.493889,41.688171 | KFM2020660193212 | 10041593581 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 12 | SS-ZAM-HAIL1012 | مدرسة ثانوية الإدريسي | Al-Idrisi High School | Secondary | Boys | Hail | Hail | 27.5043 | 41.6762 | 27.50429521,41.67617942 | KFM2020660199083 | 10041969845 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 13 | SS-ZAM-HAIL1013 | الابتدائية الثامنة والأربعون بحائل | The Forty-Eighth Elementary School in Hail | Primary | Girls | Hail | Hail | 27.4973 | 41.6886 | 27.497298,41.688615 | KFM2020660168102 | 10041554009 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 14 | SS-ZAM-HAIL1014 | متوسطة تحفيظ القرآن الكريم | Intermediate School for Memorizing the Holy Quran | Intermediate | Girls | Hail | Hail | 27.5048 | 41.6766 | 27.50480044,41.67655528 | KFM2020660199084 | 10041637747 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 15 | SS-ZAM-HAIL1015 | المدرسة الإبتدائية السابعة عشر | Seventeenth Elementary School | Primary | Girls | Hail | Hail | 27.5027 | 41.6802 | 27.50273303,41.68016553 | KFM2020660199082 | 10041859306 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 16 | SS-ZAM-HAIL1016 | الابتدائية الرابعة والعشرون | Twenty-fourth Elementary School | Primary | Girls | Hail | Hail | 27.491 | 41.694 | 27.49101,41.693972 | KFM2020660210408 | 10041648796 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 17 | SS-ZAM-HAIL1017 | المتوسطة السادسة عشر للبنات | Sixteenth Intermediate School for Girls | Intermediate | Girls | Hail | Hail | 27.5025 | 41.6808 | 27.502546,41.680776 | KFM2020660210302 | 10041481047 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 18 | SS-ZAM-HAIL1018 | الثانوية السابعة بحائل - مسارات | Seventh Secondary School in Hail - Pathways | Secondary | Girls | Hail | Hail | 27.4917 | 41.6936 | 27.49170068,41.69364357 | KFM2020660210311 | 10041497806 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 19 | SS-ZAM-HAIL1019 | المدرسة المتوسطة الحادية والعشرون | Twenty-first Middle School | Intermediate | Girls | Hail | Hail | 27.4915 | 41.6932 | 27.491546,41.693248 | KFM2020660210314 | 10041666506 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 20 | SS-ZAM-HAIL1020 | مدرسة متوسطة محمد بن عثيمين | Mohammed Bin Uthaimin Intermediate School | Intermediate | Boys | Hail | Hail | 27.507 | 41.6782 | 27.507042,41.678201 | KFM2020660199088 | 10041527342 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 21 | SS-ZAM-HAIL1021 | المدرسة السعودية الإبتدائية | Saudi Elementary School | Primary | Boys | Hail | Hail | 27.5037 | 41.684 | 27.50367515,41.68403864 | KFM2020660199176 | 10041586648 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 22 | SS-ZAM-HAIL1022 | مدرسة ابتدائية تحفيظ القرآن الكريم | Primary school for memorizing the Holy Quran | Primary | Girls | Hail | Hail | 27.4954 | 41.6946 | 27.49535523,41.69460386 | KFM2020660210327 | 10041638619 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 23 | SS-ZAM-HAIL1023 | المدرسة المتوسطة السادسة | Sixth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5015 | 41.6878 | 27.50154824,41.68780714 | KFM2020660211964 | 10041907252 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 24 | SS-ZAM-HAIL1024 | متوسطة المتنبي- المبنى الثاني | Al-Mutanabbi Intermediate School - Building Two | Intermediate | Boys | Hail | Hail | 27.4935 | 41.6968 | 27.493494,41.6967858 | KFM2020660211923 | 10041497950 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 25 | SS-ZAM-HAIL1025 | المدرسة الثانوية الثانية | Second High School | Secondary | Girls | Hail | Hail | 27.5019 | 41.6879 | 27.501868,41.687861 | KFM2020660211967 | 10041427795 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 26 | SS-ZAM-HAIL1026 | المدرسة الإبتدائية الرابعة عشر | Fourteenth Elementary School | Primary | Girls | Hail | Hail | 27.5017 | 41.6884 | 27.50165768,41.68842673 | KFM2020660211966 | 10041413904 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 27 | SS-ZAM-HAIL1027 | إثابت بن قياس التوسيطة | Ithab ibn Qiyas al-Tawsiyyah | Intermediate | Boys | Hail | Hail | 27.5006 | 41.6909 | 27.5006,41.690902 | KFM2020660211961 | 10041591862 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 28 | SS-ZAM-HAIL1028 | الوليد بن عبد الملك للطفولة المبكرة | Al-Walid ibn Abd al-Malik for early childhood | Early Childhood | Boys | Hail | Hail | 27.4993 | 41.6937 | 27.499271,41.693674 | KFM2020660212018 | 10041426107 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 29 | SS-ZAM-HAIL1029 | المدرسة الابتدائية الواحدة والعشرون للطفولة المبكرة | The Twenty-First Primary School for Early Childhood | Primary | Girls | Hail | Hail | 27.5156 | 41.6679 | 27.51560791,41.66793466 | KFM2020660209886 | 10041556513 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 30 | SS-ZAM-HAIL1030 | روضة الأطفال الثالثة | Kindergarten 3 | Kindergarten | Girls | Hail | Hail | 27.5156 | 41.6679 | 27.51560791,41.66793466 | KFM2020660209887 | 30073750764 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 31 | SS-ZAM-HAIL1031 | الثانوية العاشرة بحائل- - مسارات | The Tenth Secondary School in Hail - Tracks | Secondary | Girls | Hail | Hail | 27.5079 | 41.6832 | 27.50788243,41.68322963 | KFM2020660209821 | 10041568327 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 32 | SS-ZAM-HAIL1032 | الإبتدائية الثالثة والثلاثون | The thirty-third elementary school | Primary | Girls | Hail | Hail | 27.508 | 41.6836 | 27.50800497,41.68355048 | KFM2020660199069 | 10041664978 |  | 2026-04-14 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 33 | SS-ZAM-HAIL1033 | المدرسة الثانوية السادسة عشر | Sixteenth High School | Secondary | Girls | Hail | Hail | 27.5162 | 41.6677 | 27.5162228,41.66773965 | KFM2020660209890 | 10041795460 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 34 | SS-ZAM-HAIL1034 | مدرسة متوسطة الشورى | Al-Shura Intermediate School | Intermediate | Boys | Hail | Hail | 27.4847 | 41.7078 | 27.484729,41.707832 | KFM2120660269707 | 10041586254 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 35 | SS-ZAM-HAIL1035 | مدرسة الصديق الثانوية | Al-Siddiq High School | Secondary | Boys | Hail | Hail | 27.5064 | 41.6877 | 27.50643781,41.68768578 | KFM2020660210306 | 10041586371 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 36 | SS-ZAM-HAIL1036 | المدرسة المتوسطة الرابعة | Fourth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5082 | 41.6829 | 27.508244,41.682921 | KFM2020660199068 | 10041526828 |  | 2026-04-15 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 37 | SS-ZAM-HAIL1037 | مدرسة الخماشية للطفولة المبكرة | Al-Khamashiyah Early Childhood School | Early Childhood | Girls | Hail | Hail | 27.4889 | 41.707 | 27.48894159,41.70697584 | KFM2020660211868 | 10041320609 |  | 2025-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 38 | SS-ZAM-HAIL1038 | مدرسة الشهداء الإبتدائية | Martyrs' Primary School | Primary | Boys | Hail | Hail | 27.5232 | 41.6507 | 27.52322936,41.65073633 | KFM2020660172233 | 10041526695 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 39 | SS-ZAM-HAIL1039 | المدرسة المتوسطة العاشرة | Tenth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5203 | 41.6637 | 27.52032024,41.66365385 | KFM2020660195410 | 10041535031 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 40 | SS-ZAM-HAIL1040 | المدرسة الإبتدائية السادسة والثلاثون | The thirty-sixth elementary school | Primary | Girls | Hail | Hail | 27.5205 | 41.6641 | 27.52054621,41.66414738 | KFM2020660199154 | 10041908581 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 41 | SS-ZAM-HAIL1041 | مدرسة ابتدائية عبد الرحمن بن عوف | Abdul Rahman Bin Auf Elementary School | Primary | Boys | Hail | Hail | 27.5068 | 41.692 | 27.5067679,41.69195652 | KFM2020660170266 | 10041554798 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 42 | SS-ZAM-HAIL1042 | الابتدائية الخامسة عشر بحائل‎ | The fifteenth elementary school in Hail | Primary | Girls | Hail | Hail | 27.501 | 41.701 | 27.50099962,41.70102019 | KFM2020660234336 | 10041483364 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 43 | SS-ZAM-HAIL1043 | المتوسطة الثالثة بحائل‎ | Third Intermediate School in Hail | Intermediate | Girls | Hail | Hail | 27.5016 | 41.7006 | 27.50157203,41.7005825 | KFM2020861202258 | 10034328714 |  |  | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 44 | SS-ZAM-HAIL1044 | الثانوية الخامسة | Fifth Secondary | Secondary | Girls | Hail | Hail | 27.5013 | 41.701 | 27.50130543,41.70096154 | KFM2020660193428 | 10041318843 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 45 | SS-ZAM-HAIL1045 | المدرسة المتوسطة الثلاثون | Thirtieth Middle School | Intermediate | Girls | Hail | Hail | 27.5264 | 41.6523 | 27.5263501,41.65225983 | KFM2020660175597 | 10041796574 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 46 | SS-ZAM-HAIL1046 | المدرسة الثانوية التاسعة عشر | Nineteenth High School | Secondary | Girls | Hail | Hail | 27.5263 | 41.6534 | 27.52628644,41.65337788 | KFM2020660175600 | 10041796691 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 47 | SS-ZAM-HAIL1047 | الروضة الـسادسة | Sixth Kindergarten | Kindergarten | Girls | Hail | Hail | 27.5266 | 41.6529 | 27.52661174,41.65287674 | KFM2020660199118 | 10041796921 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 48 | SS-ZAM-HAIL1048 | مدرسة ابتدائية عمرو بن العاص | Amr Ibn Al-Aas Elementary School | Primary | Boys | Hail | Hail | 27.52 | 41.6748 | 27.519972,41.674799 | KFM2020660193414 | 10041592181 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 49 | SS-ZAM-HAIL1049 | المدرسة الابتدائية الواحدة والأربعون | The Forty-First Elementary School | Primary | Girls | Hail | Hail | 27.5268 | 41.6533 | 27.52684484,41.65332198 | KFM2020660199119 | 10041796814 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 50 | SS-ZAM-HAIL1050 | الابتدائية الثالثة والعشرون | Twenty-third Elementary School | Primary | Girls | Hail | Hail | 27.5097 | 41.6934 | 27.50966072,41.69335127 | KFM2020660210350 | 10041538613 |  | 2026-04-14 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 51 | SS-ZAM-HAIL1051 | مدرسة ابتدائية الأندلس / مركز التوحد name changed to | Al-Andalus Elementary School / Autism Center name changed to | Primary | Boys | Hail | Hail | 27.5161 | 41.6843 | 27.51609319,41.68432832 | KFM2020660170285 | 10041507448 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 52 | SS-ZAM-HAIL1052 | مدرسة شراف الإبتدائية | Sharaf Primary School | Primary | Boys | Hail | Hail | 27.5023 | 41.7041 | 27.50226673,41.70406938 | KFM2020660195429 | 10041496040 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 53 | SS-ZAM-HAIL1053 | المدرسة الابتدائية الثانية عشر | Twelfth Elementary School | Primary | Girls | Hail | Hail | 27.5239 | 41.6738 | 27.523887,41.673822 | KFM2020660211919 | 10041481440 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 54 | SS-ZAM-HAIL1054 | مدرسة الإمام محمد بن سعود المتوسطة | Imam Muhammad bin Saud Intermediate School | Intermediate | Boys | Hail | Hail | 27.5157 | 41.6907 | 27.51569355,41.69067979 | KFM2020660195524 | 10041480021 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 55 | SS-ZAM-HAIL1055 | مدرسة ابتدائية الجزيرة | Al Jazeera Primary School | Primary | Boys | Hail | Hail | 27.5145 | 41.6926 | 27.51453744,41.69257879 | KFM2020660170327 | 10041592322 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 56 | SS-ZAM-HAIL1056 | المدرسة المتوسطة التاسعة عشر | Nineteenth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5126 | 41.6961 | 27.51256421,41.69605221 | KFM2020660210197 | 10041549831 |  | 2026-04-08 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 57 | SS-ZAM-HAIL1057 | الروضة الخامسة عشر | Fifteenth Kindergarten | Kindergarten | Girls | Hail | Hail | 27.5126 | 41.6961 | 27.51256421,41.69605221 | KFM2020660210199 | 10042010281 |  | 2026-04-09 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 58 | SS-ZAM-HAIL1058 | الطفولة المبكرة بمبنى المتوسطة الثانية | Early Childhood at the Second Intermediate Building | Intermediate | Girls | Hail | Hail | 27.5219 | 41.6835 | 27.52192125,41.68353345 | KFM2020660170369 | 10041481191 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 59 | SS-ZAM-HAIL1059 | مركز تدريب معلمات رياض الأطفال | Kindergarten Teacher Training Center | Kindergarten | Girls | Hail | Hail | 27.5215 | 41.6845 | 27.521512,41.68448 | MMF2020800150226 | 10041598326 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 60 | SS-ZAM-HAIL1060 | المدرسة الابتدائية الثالثة لتحفيظ القرآن الكريم | Third Primary School for Memorizing the Holy Quran | Primary | Girls | Hail | Hail | 27.5231 | 41.6833 | 27.52307712,41.68325543 | KFM2020660170366 | 10041522927 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 61 | SS-ZAM-HAIL1061 | المدرسة الابتدائية الثانية | Second Elementary School | Primary | Girls | Hail | Hail | 27.5231 | 41.6836 | 27.52310091,41.68359339 | SMR2220661013518 | 10041523174 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 62 | SS-ZAM-HAIL1062 | مدرسة أبي تمام المتوسطة | Abi Tamam Intermediate School | Intermediate | Girls | Hail | Hail | 27.5224 | 41.6884 | 27.52242062,41.68843746 | KFM2020660210136 | 10041858505 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 63 | SS-ZAM-HAIL1063 | مدرسة ثانوية حانل | Hanel High School | Secondary | Girls | Hail | Hail | 27.5145 | 41.7005 | 27.51445034,41.70052165 | KFM2020660232548 | 10041480012 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 64 | SS-ZAM-HAIL1064 | مدرسة عمر بن الخطاب الإبتدائية | Omar Ibn Al-Khattab Elementary School | Primary | Boys | Hail | Hail | 27.5225 | 41.6887 | 27.52248722,41.68868423 | KFM2020660210132 | 10041478319 |  |  | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 1 | 3 | In Progress
| 65 | SS-ZAM-HAIL1065 | المدرسة المتوسطة السابعة | Seventh Intermediate School | Intermediate | Girls | Hail | Hail | 27.5279 | 41.6819 | 27.527886,41.681873 | KFM2020660211971 | 10041958215 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 66 | SS-ZAM-HAIL1066 | المدرسة المتوسطة العشرون | 20th Middle School | Intermediate | Girls | Hail | Hail | 27.5313 | 41.6721 | 27.531318,41.672135 | KFM2020660199102 | 10041834479 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 67 | SS-ZAM-HAIL1067 | الثانوية السابعة عشر | Seventeenth High School | Secondary | Girls | Hail | Hail | 27.5317 | 41.6719 | 27.53173268,41.67185165 | KFM2020660212004 | 10041693503 |  | 2026-05-04 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 68 | SS-ZAM-HAIL1068 | المدرسة الإبتدائية الثانية والأربعون | The Forty-Second Elementary School | Primary | Girls | Hail | Hail | 27.5317 | 41.6721 | 27.53165896,41.67212963 | KFM2020660199105 | 10041819472 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 69 | SS-ZAM-HAIL1069 | المدرسة الإبتدائية السابعة | Seventh Elementary School | Primary | Girls | Hail | Hail | 27.5222 | 41.694 | 27.522213,41.694048 | KFM2020660209866 | 10041319359 |  | 2026-04-15 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 70 | SS-ZAM-HAIL1070 | ابتدائية الطفولة المبكرة في مبنى متوسطة الرياض | Early Childhood Elementary School in the Riyadh Intermediate School Building |  | Girls | Hail | Hail | 27.53 | 41.6775 | 27.53004333,41.67754363 | MMF2420601018595 | 10041427276 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 71 | SS-ZAM-HAIL1071 | الابتدائية الثالثة عشر بحائل | Thirteenth Elementary School in Hail | Primary | Girls | Hail | Hail | 27.5253 | 41.6884 | 27.525294,41.68840796 | KFM2020660199213 | 10041764552 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 72 | SS-ZAM-HAIL1072 | ابتدائية الملك عبد العزيز للطفولة المبكرة | King Abdul Aziz Elementary School for Early Childhood | Primary | Boys | Hail | Hail | 27.5188 | 41.6993 | 27.51878513,41.69925222 | KFM2020660207488 | 10041479227 |  | 2026-04-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 73 | SS-ZAM-HAIL1073 | متوسطة بن هشام | Ibn Hisham Intermediate School | Intermediate | Boys | Hail | Hail | 27.4991 | 41.7207 | 27.4991390916668,41.7207090742996 | KFM2020660193423 | 10041940696 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 74 | SS-ZAM-HAIL1074 | مدرسة ثانوية حراء | Hiraa High School | Secondary | Boys | Hail | Hail | 27.4983 | 41.7214 | 27.49829985,41.72144574 | KFM2020660234321 | 10041951742 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 75 | SS-ZAM-HAIL1075 | مدرسة ابن قدامه الابتدائية | Ibn Qudamah Elementary School | Primary | Boys | Hail | Hail | 27.4984 | 41.7198 | 27.498383,41.71981 | KFM2020660234322 | 10041573505 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 76 | SS-ZAM-HAIL1076 | مدرسة مكة المتوسطة | Makkah Intermediate School | Intermediate | Boys | Hail | Hail | 27.516 | 41.7064 | 27.51597901,41.70644045 | KFM2020660211886 | 10084724018 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 77 | SS-ZAM-HAIL1077 | مدرسة إبتدائية الفيصلية | Al-Faisaliah Elementary School | Primary | Boys | Hail | Hail | 27.517 | 41.7069 | 27.516992,41.706863 | MMF2020800184156 | 10041536083 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 78 | SS-ZAM-HAIL1078 | الابتدائية العشرون بحائل | The twentieth elementary school in Hail | Primary | Girls | Hail | Hail | 27.5335 | 41.6803 | 27.533461,41.680307 | KFM2020660170305 | 10041563901 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 79 | SS-ZAM-HAIL1079 | ابتدائية حطين | Hattin Elementary School | Primary | Boys | Hail | Hail | 27.5346 | 41.6796 | 27.53460821,41.67961836 | KFM2020660170306 | 10041475139 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 80 | SS-ZAM-HAIL1080 | المتوسطة الثانية عشر بحائل | Twelfth Intermediate School in Hail | Intermediate | Girls | Hail | Hail | 27.5029 | 41.7234 | 27.502944,41.723449 | KFM2020660234324 | 10041665090 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 81 | SS-ZAM-HAIL1081 | المدرسة الرابعة الاربعون الإبتدائية | The Forty-Fourth Elementary School | Primary | Girls | Hail | Hail | 27.5027 | 41.7228 | 27.50269497,41.72281265 | KFM2020660232338 | 10041526953 |  |  | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 82 | SS-ZAM-HAIL1082 | ابتدائية تحفيظ القرآن السادسة | Sixth Quran Memorization Primary School | Primary | Girls | Hail | Hail | 27.5024 | 41.7232 | 27.50244754,41.72324181 | KFM2020660232339 | 10041428353 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 83 | SS-ZAM-HAIL1083 | مدرسة ثانوية نجد | Najd High School | Secondary | Boys | Hail | Hail | 27.5343 | 41.6832 | 27.53425064,41.68317442 | KFM2020660195899 | 10041593722 |  | 2025-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 84 | SS-ZAM-HAIL1084 | مدرسة متوسطة الإمام الدوري | Imam Al-Duri Intermediate School | Intermediate | Boys | Hail | Hail | 27.5339 | 41.6841 | 27.53392,41.684111 | KFM2020660199216 | 10041841268 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 85 | SS-ZAM-HAIL1085 | الابتدائية الثالثة بحائل | Third Elementary School in Hail | Primary | Girls | Hail | Hail | 27.5193 | 41.7089 | 27.51930274,41.70886114 | KFM2020660207480 | 10041483490 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 86 | SS-ZAM-HAIL1086 | المعهد الفكري بحائل | The Intellectual Institute in Hail | Primary | Girls | Hail | Hail | 27.5635 | 41.7103 | 27.563459,41.710272 | KFM2020660232523 | 10041774817 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 87 | SS-ZAM-HAIL1087 | ثانوية جنين | Jenin High School | Secondary | Girls | Hail | Hail | 27.5272 | 41.6988 | 27.52715308,41.69876358 | KFM2020660207416 | 10041481477 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 88 | SS-ZAM-HAIL1088 | مدرسة متوسطة ابي أيوب الأنصاري | Abi Ayyub Al-Ansari Intermediate School | Intermediate | Boys | Hail | Hail | 27.5309 | 41.6976 | 27.530908,41.697623 | KFM2020660172189 | 10041592055 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 89 | SS-ZAM-HAIL1089 | مدرسة ابن حبان المتوسطة | Ibn Hibban Intermediate School | Intermediate | Boys | Hail | Hail | 27.5506 | 41.6732 | 27.5506348732857,41.673240010891 | KFM2120660252263 | 10092774604 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 90 | SS-ZAM-HAIL1090 | مدرسة ثانوية المنتزه | Al-Muntazah High School | Secondary | Boys | Hail | Hail | 27.5512 | 41.6863 | 27.551171,41.686266 | KFM2020660170404 | 10041693684 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 91 | SS-ZAM-HAIL1091 | مدرسة أحد الابتدائية | Uhud Elementary School | Primary | Boys | Hail | Hail | 27.5462 | 41.6779 | 27.54619041,41.67792052 | KFM2020660199100 | 10041585918 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 92 | SS-ZAM-HAIL1092 | المدرسة الإبتدائية الخامسة والثلاثون للطفولة المبكرة | The 35th Primary School for Early Childhood | Primary | Girls | Hail | Hail | 27.5486 | 41.6718 | 27.548611,41.671803 | KFM2120660252264 | 10041661813 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 93 | SS-ZAM-HAIL1093 | المتوسطة الرابعة والعشرون بحائل | The twenty-fourth intermediate school in Hail | Intermediate | Girls | Hail | Hail | 27.5493 | 41.6721 | 27.54933983,41.67211622 | KFM2120660252255 | 10041645186 |  | 2026-05-02 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 94 | SS-ZAM-HAIL1094 | الثانوية الرابعة | Fourth Secondary School | Secondary | Girls | Hail | Hail | 27.5463 | 41.6836 | 27.54626573,41.68364162 | KFM2020660164918 | 10041554134 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 95 | SS-ZAM-HAIL1095 | المدرسة المتوسطة الثامنة عشر | Eighteenth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5427 | 41.692 | 27.542729,41.69202 | KFM2020660170409 | 10041657310 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 96 | SS-ZAM-HAIL1096 | مدرسة التاسعة الثانوية | Ninth High School | Secondary | Girls | Hail | Hail | 27.5432 | 41.6914 | 27.54318902,41.69143743 | KFM2020660170401 | 10041834577 |  |  | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 97 | SS-ZAM-HAIL1097 | الابتدائية الثانية والعشرون بحائل | The Twenty-Second Elementary School in Hail | Primary | Girls | Hail | Hail | 27.5475 | 41.682 | 27.54754595,41.68195725 | KFM2020660164913 | 10041773829 |  |  | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 9 | 1 | 5 | In Progress
| 98 | SS-ZAM-HAIL1098 | الابتدائية السادسة والعشرون | Twenty-sixth Elementary School | Primary | Girls | Hail | Hail | 27.5436 | 41.6922 | 27.54355063,41.69219255 | KFM2020660170406 | 10041864119 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 99 | SS-ZAM-HAIL1099 | مدرسة القيروان للطفولة المبكرة | Al-Qayrawan School for Early Childhood | Early Childhood | Boys | Hail | Hail | 27.5502 | 41.6788 | 27.55017625,41.67883096 | KFM2020660199165 | 10041895222 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 100 | SS-ZAM-HAIL1100 | ابتدائية تحفيظ القران الرابعة بحائل | Fourth Quran Memorization Elementary School in Hail | Primary | Girls | Hail | Hail | 27.5504 | 41.6784 | 27.55042819,41.67839527 | KFM2020660199164 | 10041850955 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 101 | SS-ZAM-HAIL1101 | المدرسة الابتدائية الخامسة | Fifth Elementary School | Primary | Girls | Hail | Hail | 27.5504 | 41.6784 | 27.55042819,41.67839527 | KFM2020660199192 | 10041501865 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 102 | SS-ZAM-HAIL1102 | مدرسة المحمدية الابتد نية بعائل | Al-Muhammadiyah Primary School in A'il | Primary | Boys | Hail | Hail | 27.5422 | 41.6977 | 27.54219742,41.69773936 | KFM2020660234372 | 10041554537 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 103 | SS-ZAM-HAIL1103 | الابتدائية الثلاثون بحائل | The Thirtieth Elementary School in Hail | Primary | Girls | Hail | Hail | 27.5483 | 41.6875 | 27.548342,41.687476 | KFM2020660170408 | 10041584714 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 104 | SS-ZAM-HAIL1104 | مدرسة ابن سيرين للطفولة المبكرة | Ibn Sirin School for Early Childhood | Primary | Boys | Hail | Hail | 27.5515 | 41.6825 | 27.551482,41.682512 | KFM2020660211900 | 10041586512 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 105 | SS-ZAM-HAIL1105 | متوسطة المدينة المنورة | Medina Intermediate School | Intermediate | Boys | Hail | Hail | 27.5517 | 41.6848 | 27.55169331,41.6848433 | KFM2020660170402 | 10041586380 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 106 | SS-ZAM-HAIL1106 | ابتدائية الخالدية | Al-Khalidiyah Elementary School | Primary | Boys | Hail | Hail | 27.5495 | 41.6918 | 27.54949123,41.69176877 | KFM2020660170410 | 10041588811 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 107 | SS-ZAM-HAIL1107 | متوسطة أبي بن كعب لتحفيظ القرآن الكريم بحائل | Abi Bin Kaab Intermediate School for Quran Memorization in Hail | Intermediate | Boys | Hail | Hail | 27.5496 | 41.692 | 27.54955306,41.69199944 | KFM2020660170346 | 10041796592 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 108 | SS-ZAM-HAIL1108 | مدرسة ثانوية الفاروق بحائل | Al-Farouq High School in Hail | Secondary | Boys | Hail | Hail | 27.5452 | 41.7034 | 27.5452087,41.70337599 | KFM2020660210395 | 10041586503 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 109 | SS-ZAM-HAIL1109 | المتوسطة الخامسة عشرة تعليم كبيرات 15 | Fifteenth Intermediate School for Adult Education 15 | Intermediate | Girls | Hail | Hail | 27.5467 | 41.7054 | 27.546664,41.705414 | SMR2420661041006 | 10041587672 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 110 | SS-ZAM-HAIL1110 | ابتدائية الامام الصنعاني | Imam Al-San'ani Primary School | Primary | Girls | Hail | Hail | 27.5449 | 41.7022 | 27.544918,41.702243 | KFM2020660199163 | 10041906219 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 111 | SS-ZAM-HAIL1111 | المتوسطة السادسة والعشرون بحائل | The twenty-sixth intermediate school in Hail | Intermediate | Girls | Hail | Hail | 27.5434 | 41.715 | 27.543392,41.714972 | SMR2220661013550 | 10041735603 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 112 | SS-ZAM-HAIL1112 | الابتدائية التاسعة والعشرون | The Twenty-Ninth Elementary School | Primary | Girls | Hail | Hail | 27.5434 | 41.715 | 27.543392,41.714972 | KFM2020660234355 | 10041735720 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 113 | SS-ZAM-HAIL1113 | ابتدائية ابن حزم | Ibn Hazm Elementary School | Primary | Boys | Hail | Hail | 27.5505 | 41.7034 | 27.5505138,41.70341492 | KFM2020660232183 | 10041495955 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 114 | SS-ZAM-HAIL1114 | متوسطة قرطبة | Cordoba Middle School | Intermediate | Boys | Hail | Hail | 27.5421 | 41.7179 | 27.54214748,41.71787739 | KFM2120660252598 | 10041586782 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 115 | SS-ZAM-HAIL1115 | متوسطة اجا | Aja Intermediate | Intermediate | Boys | Hail | Hail | 27.5642 | 41.6749 | 27.56415348,41.6749084 | KFM2020660234287 | 10041965372 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 116 | SS-ZAM-HAIL1116 | مدرسة الثانوية الثانية عامر بحائل | Second Secondary School, Amer, Hail | Secondary | Girls | Hail | Hail | 27.5514 | 41.7086 | 27.55142925,41.70857597 | KFM2020660234413 | 10041427580 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 117 | SS-ZAM-HAIL1117 | الابتدائية التاسعة والثلاثون للطفولة المبكرة | The Thirty-Ninth Elementary School for Early Childhood | Primary | Girls | Hail | Hail | 27.5521 | 41.7085 | 27.552069,41.708527 | KFM2020660234368 | 10041645051 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 118 | SS-ZAM-HAIL1118 | المدرسة المتوسطة الثامنة | Eighth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5521 | 41.7093 | 27.552056,41.709319 | KFM2020660234362 | 10041657703 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 119 | SS-ZAM-HAIL1119 | الابتدائية الرابعة والثلاثون بحائل | The thirty-fourth elementary school in Hail | Primary | Girls | Hail | Hail | 27.5438 | 41.7226 | 27.543773,41.722614 | KFM2120660278119 | 10041526425 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 120 | SS-ZAM-HAIL1120 | المدرسة الإبتدائية الأربعون | The Fortieth Elementary School | Primary | Girls | Hail | Hail | 27.5653 | 41.6829 | 27.5652948,41.68285847 | KFM2020660232595 | 10041638136 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 121 | SS-ZAM-HAIL1121 | الثانوية الحادية والعشرون بحائل - مسارات | The Twenty-First Secondary School in Hail - Pathways | Secondary | Girls | Hail | Hail | 27.5653 | 41.6834 | 27.56526514,41.68342215 | KFM2020660232591 | 10041641211 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 122 | SS-ZAM-HAIL1122 | المتوسطة الحادية والثلاثون بحائل | The thirty-first intermediate school in Hail | Intermediate | Girls | Hail | Hail | 27.5658 | 41.6839 | 27.5658203,41.6838728 | KFM2020660232514 | 10041641338 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 123 | SS-ZAM-HAIL1123 | متوسطة ابراهيم الثويني | Ibrahim Al-Thuwaini Intermediate School | Intermediate | Boys | Hail | Hail | 27.5648 | 41.6884 | 27.56478565,41.68843655 | KFM2120660252618 | 10041823519 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 124 | SS-ZAM-HAIL1124 | مدرسة الفيصل الثانوية | Al Faisal Secondary School | Secondary | Boys | Hail | Hail | 27.5648 | 41.6884 | 27.56478565,41.68843655 | KFM2120660252546 | 10041823386 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 125 | SS-ZAM-HAIL1125 | المدرسة الثانوية الحادية عشر | Eleventh High School | Secondary | Girls | Hail | Hail | 27.5662 | 41.6915 | 27.56622135,41.6914979 | KFM2120660252550 | 10041834675 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 126 | SS-ZAM-HAIL1126 | المدرسة المتوسطة السابعة عشر | Seventeenth Intermediate School | Intermediate | Girls | Hail | Hail | 27.5657 | 41.6933 | 27.56569426,41.69327617 | KFM2120660252622 | 10041535282 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 127 | SS-ZAM-HAIL1127 | مدرسة ثانوية الشيخ محمد بن إبراهيم | Sheikh Mohammed bin Ibrahim High School | Secondary | Boys | Hail | Hail | 27.5544 | 41.7185 | 27.55441026,41.71848674 | KFM2020660234303 | 10041938393 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 128 | SS-ZAM-HAIL1128 | المدرسة الثانوية الثامنة عشر | Eighteenth High School | Secondary | Girls | Hail | Hail | 27.559 | 41.7141 | 27.558969,41.714144 | KFM2020660234420 | 10041657436 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 129 | SS-ZAM-HAIL1129 | المدرسة الابتدائية الخامسة والأربعون | The Forty-Fifth Elementary School | Primary | Girls | Hail | Hail | 27.5635 | 41.7103 | 27.563491,41.710308 | KFM2020660232526 | 10041774693 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 130 | SS-ZAM-HAIL1130 | المدرسة المتوسطة الخامسة والعشرون | Twenty-fifth Intermediate School | Primary | Girls | Hail | Hail | 27.5634 | 41.7112 | 27.56338308,41.71124697 | KFM2020660232528 | 10041775091 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 131 | SS-ZAM-HAIL1131 | مدرسة الأمير سعود بن عبد المحسن الثانوية | Prince Saud bin Abdul Mohsen Secondary School | Secondary | Boys | Hail | Hail | 27.5615 | 41.7215 | 27.56154744,41.72146082 | KFM2020660232520 | 10041856654 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 132 | SS-ZAM-HAIL1132 | ثانوية الحكمة - مسارات‎ | Al-Hikma High School - Pathways | Secondary | Girls | Hail | Hail | 27.564 | 41.6744 | 27.5640132184547,41.6743923882036 | KFM2020660234288 | 10041965265 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 133 | SS-ZAM-HAIL1133 | مدرسة حاتم الابتدائية بحائل‎ | Hatem Elementary School in Hail | Primary | Boys | Hail | Hail | 27.5686 | 41.685 | 27.568647,41.684954 | KFM2020660232594 | 10041807641 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 134 | SS-ZAM-HAIL1134 | ابتدائية الغافقي‎ | Al-Ghafiqi Primary School | Primary | Boys | Hail | Hail | 27.4829 | 41.7071 | 27.482901,41.707109 | KFM2020660210331 | 10041639198 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 135 | SS-ZAM-HAIL1135 | مدرسة ثانوية صقر قريش‎ | Saqr Quraish High School | Secondary | Boys | Hail | Hail | 27.4823 | 41.7087 | 27.482334,41.708655 | KFM2020660211905 | 10041810243 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 136 | SS-ZAM-HAIL1136 | الابتدائية الثانية والخمسون بحائل‎ | The fifty-second elementary school in Hail | Primary | Girls | Hail | Hail | 27.4859 | 41.6708 | 27.485868,41.670781 | KFM2120660252256 | 10041927738 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 137 | SS-ZAM-HAIL1137 | المدرسة المتوسطة الثالثة عشر‎ | Thirteenth Intermediate School | Intermediate | Girls | Hail | Hail | 27.48 | 41.7096 | 27.480027,41.709572 | KFM2020660210333 | 10041648929 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 138 | SS-ZAM-HAIL1138 | الثانوية الخامسة عشر‎ | Fifteenth High School | Secondary | Girls | Hail | Hail | 27.4798 | 41.709 | 27.479839,41.709047 | KFM2020660210260 | 10041501721 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 139 | SS-ZAM-HAIL1139 | الإبتدائية السابعة والثلاثون‎ | The thirty-seventh elementary school | Primary | Girls | Hail | Hail | 27.4794 | 41.7103 | 27.47939,41.71031 | KFM2020660211988 | 10041907691 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 140 | SS-ZAM-HAIL1140 | المدرسة الإبتدائية السادسة عشر‎ | Sixteenth Elementary School | Primary | Girls | Hail | Hail | 27.4854 | 41.7056 | 27.485355,41.705621 | KFM2020660211986 | 10041527262 |  | 2026-04-13 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 141 | SS-ZAM-HAIL1141 | ثانوية اميمة بنت قيس‎ | Ummaymah Bint Qais Secondary School | Secondary | Girls | Hail | Hail | 27.4847 | 41.6687 | 27.48473,41.668686 | KFM2120660258845 | 10041989795 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 142 | SS-ZAM-HAIL1142 | ثانوية الطفيل بن عمرو‎ | Al-Tufail Bin Amr High School | Secondary | Boys | Hail | Hail | 555169499 | yes | 555169499,yes | SMR2220661004736 | 10104671983 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 143 | SS-ZAM-HAIL1143 | المتوسطة الثانية والثلاثون بحائل‎ | The thirty-second intermediate school in Hail | Intermediate | Girls | Hail | Hail | 27.4784 | 41.6719 | 27.478386,41.671909 | KFM2120660267931 | 10041918087 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 144 | SS-ZAM-HAIL1144 | مدرسة ابتدائية المصيف‎ | Al-Masif Elementary School | Primary | Boys | Hail | Hail | 27.5757 | 41.6758 | 27.575734,41.675759 | KFM2120660252587 | 10041818635 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 145 | SS-ZAM-HAIL1145 | الروضة السادسة والثلاثون‎ | The thirty-sixth kindergarten | Kindergarten | Girls | Hail | Hail | 27.5781 | 41.7152 | 27.578081,41.715167 | KFM2120660248389 | 10087165085 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 146 | SS-ZAM-HAIL1146 | ثانوية الأميرة نورة بنت عبد الرحمن ال سعود‎ | Princess Noura bint Abdul Rahman Al Saud High School | Secondary | Girls | Hail | Hail | 27.5786 | 41.7155 | 27.57858,41.715466 | KFM2120660248388 | 10087163948 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 147 | SS-ZAM-HAIL1147 | مدرسة غرناطة الإبتدائية‎ | Granada Primary School | Primary | Boys | Hail | Hail | 27.47 | 41.7175 | 27.470046,41.717459 | KFM2020660211909 | 10041974891 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 148 | SS-ZAM-HAIL1148 | الروضة الثالثة والثلاثون‎ | The thirty-third kindergarten | Kindergarten | Girls | Hail | Hail | 27.4705 | 41.7207 | 27.470548,41.720653 | KFM2020660211901 | 10041782158 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 149 | SS-ZAM-HAIL1149 | المدرسة الثانوية العشرون‎ | 20th High School | Secondary | Girls | Hail | Hail | 27.4696 | 41.72 | 27.469558,41.720043 | KFM2020660211907 | 10041782283 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 150 | SS-ZAM-HAIL1150 | الابتدائية الرابعة والخمسون بحائل‎ | The fifty-fourth elementary school in Hail | Primary | Girls | Hail | Hail | 27.5578 | 41.7141 | 27.557839,41.714105 | KFM2020660232303 | 10041851498 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 151 | SS-ZAM-HAIL1151 | ابتدائية ابن تيمية للطفولة المبكرة‎ | Ibn Taymiyyah Primary School for Early Childhood | Primary | Boys | Hail | Hail | 27.4648 | 41.6562 | 27.464834,41.656236 | KFM2120660252193 | 10041757647 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 152 | SS-ZAM-HAIL1152 | المدرسة الإبتدائية الخامسة والستون‎ | The Sixty-Fifth Elementary School | Primary | Boys | Hail | Hail | 27.4612 | 41.6519 | 27.461207,41.65185 | KFM2120660258853 | 10041814144 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 153 | SS-ZAM-HAIL1153 | المتوسطة السادسة والثلاثون (متوسطة نقرة قفار)‎ | The thirty-sixth intermediate school (Naqrat Qafar Intermediate School) | Intermediate | Boys | Hail | Hail | 27.4624 | 41.6452 | 27.462368,41.645226 | KFM2020660229590 | 10041814082 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 154 | SS-ZAM-HAIL1154 | مدرسة ثانوية الكسائي‎ | Al-Kisa'i High School | Secondary | Boys | Hail | Hail | 27.4559 | 41.6454 | 27.455903,41.645403 | KFM2120660258822 | 10041936540 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 155 | SS-ZAM-HAIL1155 | الطفولة المبكرة بالروضة الثامنة والعشرون‎ changed to الابتدائية التاسعة والخمسون | Early Childhood at Kindergarten 28 changed to Elementary School 59 | Primary | Girls | Hail | Hail | 27.4479 | 41.6384 | 27.447857,41.638373 | KFM2120660258867 | 10041922796 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 156 | SS-ZAM-HAIL1156 | الثانوية الرابعة والعشرون - مسارات‎ | Twenty-fourth Secondary School - Pathways | Secondary | Girls | Hail | Hail | 27.4487 | 41.6383 | 27.448699,41.638303 | KFM2120660258873 | 10041639017 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 157 | SS-ZAM-HAIL1157 | مدرسة إبتدائية النيصية‎ | Al-Nisiyah Elementary School | Primary | Girls | Hail | Hail | 27.6259 | 41.6907 | 27.625861,41.690748 | KFM2020660207389 | 10041567661 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 158 | SS-ZAM-HAIL1158 | متوسطة النيصية‎ | Al-Nisiyah Intermediate School | Intermediate | Girls | Hail | Hail | 27.633 | 41.7022 | 27.633031,41.702164 | KFM2120660269657 | 10041568176 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 159 | SS-ZAM-HAIL1159 | مدرسة بدائع نقبين الإبتدائية‎ | Bada'i Naqbin Primary School | Primary | Boys | Hail | Hail | 27.632 | 41.6468 | 27.631978,41.646778 | KFM2120660269672 | 10041570479 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 160 | SS-ZAM-HAIL1160 | مدرسة ثانوية قفار-( بنين )‎ | Qifar Secondary School (Boys) | Secondary | Boys | Hail | Hail | 27.4101 | 41.6221 | 27.410113,41.622082 | KFM2020760009526 | 10041796734 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 161 | SS-ZAM-HAIL1161 | مدرسة متوسطة قفار‎ | Qaffar Intermediate School | Intermediate | Boys | Hail | Hail | 27.4053 | 41.5881 | 27.405346,41.588116 | KFM2120660252532 | 10041588562 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 162 | SS-ZAM-HAIL1162 | مدرسة ثانوية قفار‎ | Qaffar High School | Secondary | Boys | Hail | Hail | 27.4032 | 41.5858 | 27.403159,41.585814 | KFM2120660252658 | 10041568499 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 163 | SS-ZAM-HAIL1163 | مدرسة مريفق الإبتدائية‎ | Mreifq Primary School | Primary | Boys | Hail | Hail | 27.3594 | 41.6448 | 27.359427,41.644797 | KFM2120660281123 | 10041588301 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 164 | SS-ZAM-HAIL1164 | ابتدائية الودي‎ | Al-Wadi Primary School | Primary | Girls | Hail | Hail | 27.3784 | 41.5441 | 27.378441,41.544061 | KFM2020660232555 | 10041588698 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 165 | SS-ZAM-HAIL1165 | مدرسة الوادي الإبتدائية‎ | Al Wadi Elementary School | Primary | Girls | Hail | Hail | 27.364 | 41.5401 | 27.364022,41.540129 | KFM2020660232325 | 10041572858 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 166 | SS-ZAM-HAIL1166 | مدرسة حمزة بن عبد المطلب الإبتدائية‎ | Hamza Bin Abdul Muttalib Elementary School | Primary | Boys | Hail | Hail | 27.3184 | 41.427 | 27.318368,41.426957 | KFM2120660252283 | 10041956711 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 167 | SS-ZAM-HAIL1167 | مدرسة القاعد المتوسطة‎ | Al-Qaed Intermediate School | Intermediate | Boys | Hail | Hail | 27.8471 | 41.7158 | 27.847127,41.715821 | KFM2120660269713 | 10041846881 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 168 | SS-ZAM-HAIL1168 | مدرسة القاعد الثانوية‎ | Al-Qaed Secondary School | Secondary | Boys | Hail | Hail | 27.8467 | 41.7278 | 27.846709,41.727798 | KFM2120660248728 | 10041769970 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 169 | SS-ZAM-HAIL1169 | مدرسة القاعد الابتدائية‎ | Al-Qaed Primary School | Primary | Boys | Hail | Hail | 27.8483 | 41.7216 | 27.848309,41.721617 | KFM2120660263854 | 10041711773 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 170 | SS-ZAM-HAIL1170 | ابتدائية صحى‎ | Health Primary School | Primary | Boys | Hail | Hail | 27.2712 | 41.269 | 27.271219,41.269013 | KFM2120660252276 | 10041794892 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 171 | SS-ZAM-HAIL1171 | الإبتدائية الأولى بموفق‎ | First Elementary School in Muwafaq | Primary | Girls | Hail | Hail | 27.3787 | 41.1955 | 27.378728,41.195469 | KFM2120660252196 | 10041508543 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 172 | SS-ZAM-HAIL1172 | متوسطة موقق‎ | Mowaqq Intermediate School | Intermediate | Girls | Hail | Hail | 27.3864 | 41.1875 | 27.386427,41.18753 | KFM2120660252250 | 10041538631 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 173 | SS-ZAM-HAIL1173 | ابتدائية الحطي‎ | Al-Hatty Primary School | Primary | Boys | Hail | Hail | 27.5167 | 41.0837 | 27.516686,41.083692 | KFM2120660252293 | 10041536154 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 174 | SS-ZAM-HAIL1174 | ابتدائية ابن خلدون بعقلة بن جبرين‎ | Ibn Khaldoun Primary School in Aqla Ben Jabrin | Primary | Boys | Hail | Hail | 27.1023 | 41.2811 | 27.102283,41.281055 | KFM2120660269000 | 10041857339 |  | 2026-04-21 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 175 | SS-ZAM-HAIL1175 | متوسطة عقلة بن جبرين‎ | Aqla Bin Jabrin Intermediate School | Intermediate | Boys | Hail | Hail | 27.1023 | 41.2811 | 27.102283,41.281055 | KFM2120660268999 | 10041430315 |  | 2026-04-22 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 176 | SS-ZAM-HAIL1176 | متوسطة الصفا بالصنينا‎ | Al-Safa Intermediate School in Al-Sunayna | Intermediate | Boys | Hail | Hail | 27.3174 | 41.0513 | 27.317445,41.051319 | SMR2220661013183 | 10041536403 |  | 2026-04-15 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 177 | SS-ZAM-HAIL1177 | ابتدائية دليهان‎ | Dalihan Primary School | Primary | Boys | Hail | Hail | 27.2896 | 40.9698 | 27.289599,40.969838 | KFM2120660252269 | 10041844054 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 177 | SS-ZAM-HAIL1177 | المدرسه المشار الابتدايه | Mashar Primary School | Primary | Boys | Hail | Hail | 33.2915 | 44.5507 | KFM2020660232307 | 10041685056 |  |  | 2026-04-19 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 10 | 0 | In Progress | In Progress
| 178 | SS-ZAM-HAIL1178 | ثانوية الخبة - مسارات‎ | Al-Khabah Secondary School - Pathways | Secondary | Boys | Hail | Hail | 27.4282 | 40.9091 | 27.428155,40.909146 | KFM2120660287553 | 10041743051 |  | 2026-04-22 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | Not Started
| 179 | SS-ZAM-HAIL1179 | ابتدائية الخبة‎ | Al-Khabah Primary School | Primary | Boys | Hail | Hail | 27.4272 | 40.9061 | 27.427188,40.906074 | KFM2120660252341 | 10041851282 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | In Progress
| 180 | SS-ZAM-HAIL1180 | متوسطة الخبة‎ | Medium-sized expertise | Intermediate | Boys | Hail | Hail | 27.4265 | 40.9055 | 27.426456,40.905463 | KFM2120660252340 | 10041534866 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | Not Started
| 181 | SS-ZAM-HAIL1181 | متوسطة الفرحانية-بنين‎ | Al-Farhaniyah Intermediate School for Boys | Intermediate | Boys | Hail | Hail | 27.3086 | 40.9297 | 27.308602,40.929693 | KFM2120660284102 | 10041743258 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 182 | SS-ZAM-HAIL1182 | مدرسة الفرحانية الثانوية‎ | Al-Farhaniyah Secondary School | Secondary | Boys | Hail | Hail | 27.3079 | 40.9228 | 27.307859,40.922834 | KFM2120660284101 | 10042010422 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | In Progress
| 183 | SS-ZAM-HAIL1183 | مدرسة متوسطة صبابة‎ | Sababa Intermediate School | Intermediate | Boys | Hail | Hail | 27.5262 | 41.647 | 27.526183,41.647032 | KFM2120660252522 | 10042010567 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 184 | SS-ZAM-HAIL1184 | مدرسة النيصية الثانوية‎ | Al-Nisiyah Secondary School | Secondary | Boys | Hail | Hail | 27.6164 | 41.6886 | 27.616359,41.688613 | KFM2120660269656 | 10041646432 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 185 | SS-ZAM-HAIL1185 | الثانوية الرابعة عشر | Fourteenth High School | Secondary | Girls | Hail | Hail | 27.5027 | 41.7221 | 27.50270609,41.72212824 | KFM2020660234330 | 10041699481 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 186 | SS-ZAM-HAIL1186 | مدرسة السلام الإبتدائية | Al Salam Primary School | Primary | Boys | Hail | Hail | 27.5505 | 41.674 | 27.55050191,41.67402595 | KFM2120660252310 | 10041507312 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 187 | SS-ZAM-HAIL1187 | الثانوية الاولى بحائل نظام - مسارات | First Secondary School in Hail - Track System | Secondary | Girls | Hail | Hail | 27.5211 | 41.6844 | 27.52112925,41.68443334 | KFM2020660170363 | 10041482376 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | Not Started
| 188 | SS-ZAM-HAIL1188 | مدرسة النووي الإبتدائية | Al-Nawawi Elementary School | Primary | Boys | Hail | Hail | 27.5242 | 41.6649 | 27.52420222,41.6649279 | KFM2020660232289 | 10041685172 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | In Progress
| 189 | SS-ZAM-HAIL1189 | مدرسة معن بن زائدة الإبتدائية | Ma'an Bin Zaidah Elementary School | Primary | Boys | Hail | Hail | 27.5045 | 41.6788 | 27.50449875,41.6787873 | KFM2020660210310 | 10041588947 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 190 | SS-ZAM-HAIL1190 | الابتدائية الخامسة والخمسون بحائل | The fifty-fifth elementary school in Hail | Primary | Girls | Hail | Hail | 27.4876 | 41.6802 | 27.48761202,41.68015419 | KFM2020660229534 | 10098333957 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 191 | SS-ZAM-HAIL1191 | ابتدائية السويفله | Al-Suwaifila Primary School | Primary | Girls | Hail | Hail | 27.5557 | 41.7445 | 27.555735,41.744457 | KFM2020660234387 | 10093505610 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 192 | SS-ZAM-HAIL1192 | ابتدائية بلال بن رباح‎ | Bilal Bin Rabah Elementary School | Primary | Boys | Hail | Hail | 27.4083 | 41.5784 | 27.408283,41.578363 | KFM2120660252664 | 10041937402 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 193 | SS-ZAM-HAIL1193 | ثانوية قصر العشروات‎ | Qasr Al-Ashrawat High School | Secondary | Girls | Hail | Hail | 27.3294 | 41.4546 | 27.329437,41.454647 | KFM2120660252328 | 10101912976 |  | 2026-04-14 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | Not Started
| 194 | SS-ZAM-HAIL1194 | المتوسطة الرابعة عشر | Fourteenth Intermediate | Intermediate | Girls | Hail | Hail | 27.5099 | 41.693 | 27.50987007,41.69296771 | KFM2020660210348 | 10041731963 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 195 | SS-ZAM-HAIL1195 | الشيخ محمد بن عبد الوهاب الإبتدائية | Sheikh Muhammad bin Abdul Wahhab Elementary School | Primary | Boys | Hail | Hail | 27.5321 | 41.6896 | 27.532091,41.689575 | KFM2020660199215 | 10041482241 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | In Progress
| 196 | SS-ZAM-HAIL1196 | المدرسة الإبتدائية التاسعة ومعهد الأمل | Ninth Elementary School and Al Amal Institute | Primary | Girls | Hail | Hail | 27.5356 | 41.6858 | 27.53560238,41.68578208 | KFM2020660199218 | 10041683098 |  | 2026-04-13 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 197 | SS-ZAM-HAIL1197 | المدرسة الثانوية الثالثة | Third High School | Secondary | Girls | Hail | Hail | 27.5233 | 41.7109 | 27.52333835,41.71085597 | KFM2020660207518 | 10041556611 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 198 | SS-ZAM-HAIL1198 | المدرسة المتوسطة الخامسة للبنات | Fifth Intermediate School for Girls | Intermediate | Girls | Hail | Hail | 27.5466 | 41.6843 | 27.54661372,41.68434978 | KFM2020660164914 | 10041908714 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 199 | SS-ZAM-HAIL1199 | المدرسة السادسة الابتدائية | Sixth Elementary School | Primary | Girls | Hail | Hail | 27.5394 | 41.701 | 27.539434,41.701034 | KFM2020660210391 | 10041655315 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | In Progress
| 200 | SS-ZAM-HAIL1200 | روضة الأطفال الثانية | Kindergarten 2 | Kindergarten | Girls | Hail | Hail | 27.5427 | 41.7141 | 27.542746,41.71409 | KFM2020660234353 | 10041736020 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 11 | 0 | 4 | 41.1333
[14 empty] | Total | Completed | 152 | 152 | 151 | 152 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | In Progress | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152
[15 empty] | Not Started | 49 | 49 | 49 | 49 | 191 | 191 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 49
Note on O4: 4/2/2025
Note on P4: 4/2/2025

## NB Schools -1
|  | Report Date | 2026-05-10
Project | Schools Information | [11 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School No | School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [8 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
NB-1 | 1 | SS-ZAM-NB1001 | مدرسة المغيرة بن شعبة الثانوية برفحاء( بنين ) | Al-Mughira bin Shu'bah Secondary School in Rafha (Boys) | Secondary | Boys | NB | RAFHA | 29.631916,43.525776 | KFM2120660277433 | 10006039710 |  | 2026-04-08 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress | 1 | 1 | 5 | In Progress |  | Primary | Boys | Not Started
| 2 | SS-ZAM-NB1002 | مدرسة عبادة بن الصامت المتوسطة برفحاء( بنين ) | Ubadah bin Al-Samit Intermediate School in Rafha (Boys) | Intermediate | Boys | NB | RAFHA | 29.631893,43.526810 | KFM2120660277426 | 10006039451 |  | 2026-04-07 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress |  | Intermediate | Girls | In Progress
| 3 | SS-ZAM-NB1003 | مدرسة عمرو بن العاص الإبتدائية ( بنين ) | Amr ibn al-Aas Elementary School (Boys) | Primary | Boys | NB | RAFHA | 29.630373,43.523712 | SMR2220661010604 | 10006038427 |  | 2026-04-28 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress | Not Started | Secondary | NA | Completed
| 4 | SS-ZAM-NB1004 | مدرسة رفحاء الثانوية | Rafha Secondary School | Secondary | Boys | NB | RAFHA | 29.628679,43.515259 | KFM2120660277333 | 10005991831 |  | 2026-04-16 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress | Completed | NA |  | NA
| 5 | SS-ZAM-NB1005 | مدرسة موسى بن نصير الإبتدائية | Musa bin Nusayr Elementary School | Primary | Boys | NB | RAFHA | 29.633644,43.527824 | KFM2120660277367 | 10006036244 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 6 | SS-ZAM-NB1006 | المدرسة الثانوية الثالثة برفحاء ( بنات) | The Third Secondary School in Rafha (Girls) | Secondary | Girls | NB | RAFHA | 29.628309,43.527180 | KFM2120660277371 | 10006030376 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 7 | SS-ZAM-NB1007 | المدرسة الثانوية الرابعة بحي المدينة ( للبنات ) | Fourth Secondary School in Al-Madinah District (for girls) | Secondary | Girls | NB | RAFHA | 29.638298,43.512249 | KFM2120660281228 | 10006039273 |  | 2026-04-19 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 8 | SS-ZAM-NB1008 | ابتدائية المثنى بن حارثه للطفولة المبكرة | Al-Muthanna bin Haritha Elementary School for Early Childhood | Primary | Boys | NB | RAFHA | 29.637457,43.501484 | KFM2120660281301 | 10006040176 |  | 2026-04-22 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 9 | SS-ZAM-NB1009 | المدرسة المتوسطة الرابعة بحي المدينة ( بنات ) | Fourth Intermediate School in Al-Madinah District (Girls) | Intermediate | Girls | NB | RAFHA | 29.637917,43.511307 | KFM2120660281234 | 10006039264 |  | 2026-04-16 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 10 | SS-ZAM-NB1010 | الروضة الاولى بزفحاء | The first garden in Zafhā | Kindergarten | Girls | NB | RAFHA | 29.626137,43.511772 | SMR2220661010599 | 10104624016 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 11 | SS-ZAM-NB1011 | مدرسة الابتدائية الثانية بنات | The Second Primary School for Girls | Primary | Girls | NB | RAFHA | 29.626257,43.511669 | KFM2120660276896 | 10082788080 |  | 2026-04-27 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 12 | SS-ZAM-NB1012 | مدرسة هارون الرشيد الابتدائية برفحاء | Haroun Al Rashid Elementary School in Rafha | Primary | Boys | NB | RAFHA | 29.630093,43.498390 | KFM2120660275648 | 10006023531 |  | 2026-04-21 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 13 | SS-ZAM-NB1013 | مدرسة رفحاء المتوسطة (بنين) | Rafha Intermediate School (Boys) | Intermediate | Boys | NB | RAFHA | 29.626026,43.517735 | KFM2120660276922 | 10006023881 |  | 2026-04-19 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 1 | 5 | In Progress
| 14 | SS-ZAM-NB1014 | مدرسة القدس المتوسطة ( بنين ) | Al-Quds Intermediate School (Boys) | Intermediate | Boys | NB | RAFHA | 29.64743595581304, 43.524362188359596 | KFM2120660277703 | 10006036281 |  | 2026-04-29 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 15 | SS-ZAM-NB1015 | مدرسة ابن كثير الإبتدائية ( بنين ) | Ibn Kathir Elementary School (Boys) | Primary | Boys | NB | RAFHA | 29.643631,43.528080 | KFM2120660275593 | 10006035381 |  | 2026-04-14 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 16 | SS-ZAM-NB1016 | مدرسة قتيبة بن مسلم الثانوية (بنين) | Qutaybah bin Muslim Secondary School (Boys) | Secondary | Boys | NB | RAFHA | 29.642422256666716, 43.53349953571346 | KFM2120660277704 | 10006039442 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 17 | SS-ZAM-NB1017 | متوسطة الملك فيصل اللوحه ممسوحه | King Faisal Intermediate School, the board is erased. | Intermediate | Boys | NB | RAFHA | 29.638830,43.504150 | KFM2120660282172 | 10006030438 |  | 2026-04-23 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 18 | SS-ZAM-NB1018 | المدرسة المتوسطة الثالثة ( بنات ) | Third Intermediate School (Girls) | Intermediate | Girls | NB | RAFHA | 29.628633,43.527382 | KFM2120660277370 | 10006036763 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 19 | SS-ZAM-NB1019 | الإبتدائية الثانية عشر برفحاء بنات | Twelfth Elementary School in Rafha Girls | Primary | Girls | NB | RAFHA | 29.628267,43.550644 | KFM2120660277090 | 10096361738 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 20 | SS-ZAM-NB1020 | المتوسطة الثامنة برفحاء بنات | The Eighth Intermediate School in Rafha Girls | Intermediate | Girls | NB | RAFHA | 29.628414,43.549767 | KFM2120660277092 | 10096202689 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 21 | SS-ZAM-NB1021 | الحادية عشر الابتدائية ومتوسطة حفصة بنت عمر بنات | Eleventh Elementary and Intermediate Hafsa bint Omar | Intermediate | Girls | NB | RAFHA | 29.646574,43.518230 | KFM2120660277329 | 10089327594 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 22 | SS-ZAM-NB1022 | المتوسطة السابعة والابتدائية الرابعه عشر | Seventh Intermediate and Fourteenth Primary | Intermediate | Girls | NB | RAFHA | 29.646677,43.518040 | KFM2120660277400 | 10089332001 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 23 | SS-ZAM-NB1023 | لثانوية الحسن البصري برفحاء بنين | Al-Hasan Al-Basri Secondary School for Boys in Rafha | Secondary | Boys | NB | RAFHA | 29.629080,43.506866 | KFM2020660155023 | 10006023157 |  |  | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 24 | SS-ZAM-NB1024 | المعهد العلمي في محافظة رفحاء | Scientific Institute in Rafha Governorate | Kindergarten | Girls | NB | RAFHA | 29.621780,43.518803 | KFM2020560003952 | 10042315981 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 25 | SS-ZAM-NB1025 | مدرسة متوسطة أبو جعفر المنصور | Abu Jaafar Al-Mansour Intermediate School | Intermediate | Boys | NB | RAFHA | 29.572403,43.632927 | KFM2120660276867 | 10006039433 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 26 | SS-ZAM-NB1026 | مدرسة الزبير بن العوام الابتدائية | Al-Zubair bin Al-Awam Primary School | Primary | Boys | NB | RAFHA | 29.572289,43.632851 | KFM2120660277721 | 10006035434 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 27 | SS-ZAM-NB1027 | روضة أم الزبير | Umm Al-Zubair Kindergarten | Kindergarten | Girls | NB | RAFHA | 29°34'24.9"N 43°38'09.0"E | SMR2220661010342 | 10104030020 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 28 | SS-ZAM-NB1028 | مدرسه الجبهان الابتدائيه والمتوسطه | Al-Jabhan Elementary and Intermediate School | Intermediate | Boys | NB | RAFHA | 29°34'26.6"N 43°38'07.3"E | KFM2120660275557 | 10006041843 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 29 | SS-ZAM-NB1029 | الثانوية الثانية للبنات بحي العزيزية | Second Secondary School for Girls in Al-Aziziyah District | Secondary | Girls | NB | RAFHA | 29°37'20.5"N 43°31'10.2"E | KFM2120660277763 | 10006037591 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 30 | SS-ZAM-NB1030 | المدرسة الإبتدائية الخامسة بحي القادسية ( بنات ) | The Fifth Elementary School in Al-Qadisiyah District (Girls) | Primary | Girls | NB | RAFHA | 29°38'14.7"N 43°31'25.1"E | KFM2120660276904 | 10006035247 |  | 2026-04-22 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 31 | SS-ZAM-NB1031 | الابتدائية الثامنة للبنات | Eighth Elementary School for Girls | Primary | Girls | NB | RAFHA | 29°37'27.1"N 43°31'20.2"E | KFM2120660277042 | 10006024216 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 32 | SS-ZAM-NB1032 | مدرسة ثانوية طلعة التمياط | Talat Al-Tamyat Authority and Talat Al-Tamyat Secondary School | Secondary | Boys | NB | RAFHA | 29°51'22.5"N 43°08'33.3"E | KFM2120660282140 | 10006030591 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 33 | SS-ZAM-NB1033 | مدرسة مشل الطمييات الابتدائية للبنين | Mathl Al-Tamiyat Elementary School (BOYS) | Primary | Boys | NB | RAFHA | 29°51'27.7"N 43°08'12.5"E | KFM2120660282144 | 10087048294 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 34 | SS-ZAM-NB1034 | المدرسة المتوسطة والثانوية للبنات بطلعة التمياط | Intermediate and Secondary School for Girls in Talat Al-Tamiyat | Intermediate | Girls | NB | RAFHA | 29°51'17.4"N 43°08'23.1"E | SMR2220661019741 | 10006041502 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 35 | SS-ZAM-NB1035 | ابتدائية مشل التمياط | Elementary school Meshal Altemyat | Primary | Girls | NB | RAFHA | 29°51'15.5"N 43°08'22.0"E | KFM2120660282135 | 10006030053 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 36 | SS-ZAM-NB1036 | مدرسة احد الابتدائية والمتوسطة | Uhud Elementary and Intermediate School (boys) | Intermediate | Boys | NB | RAFHA | 29°45'35.1"N 43°15'51.6"E | KFM2120660282176 | 10006025634 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 37 | SS-ZAM-NB1037 | المدرسة المتوسطة والثانوية الخامسة بحي القادسية ( بنات ) | The Fifth Intermediate and Secondary School in Al-Qadisiyah District (Girls) | Secondary | Girls | NB | RAFHA | 29°38'12.1"N 43°31'24.0"E | KFM2120660276902 | 10006035345 |  | 2026-04-25 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 38 | SS-ZAM-NB1038 | المدرسة الابتدائية الثالثة عشر للبنات برفحاء | The Thirteenth Primary School for Girls in Rafha | Primary | Girls | NB | RAFHA | 29°37'27.7"N 43°31'24.5"E | KFM2120660277039 | 10006037537 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 39 | SS-ZAM-NB1039 | الروضة الرابعة | Fourth Kindergarten | Kindergarten | Girls | NB | RAFHA | 29°37'40.0"N 43°33'00.2"E | KFM2120660277706 | 10103920716 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 40 | SS-ZAM-NB1040 | في الابتدائية السابعة للطفولة المبكرة | Seventh Elementary School for Early Childhood | Primary |  | NB | RAFHA | 29°38'16.6"N 43°30'40.2"E | KFM2120660281229 | 10006037813 |  | 2026-04-18 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 41 | SS-ZAM-NB1041 | مدرسة روضة هباس الثانوية ( بنين ) | Rawdat Habas Secondary School (Boys) | Secondary | Boys | NB | RAFHA | 29.149530,44.319775 | KFM2120660277008 | 10006029689 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 42 | SS-ZAM-NB1042 | إبتدائية ومتوسطة تحفيظ القرآن الكريم (بنين) | Elementary and Intermediate Quran Memorization (Boys) | Primary | Boys | NB | RAFHA | 29°09'33.4"N 44°18'49.4"E | KFM2120660275573 | 10006034670 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 43 | SS-ZAM-NB1043 | متوسطة وثانوية روضة مباد ( للبنات ) | Rawdat Mabad Intermediate and Secondary School (for girls) | Intermediate | Girls | NB | RAFHA | 29°09'11.2"N 44°19'16.2"E | KFM2120660277012 | 10006033663 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 44 | SS-ZAM-NB1044 | مدرسة روضة هباس الابتدائية .( بنين ) | Rawdat Habas Elementary School. (Boys) | Primary | Boys | NB | RAFHA | 29°09'03.8"N 44°18'50.4"E | KFM2120660277006 | 10006029713 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 45 | SS-ZAM-NB1045 | درسة الابتدار المتوسطة والثانوية للبنات بالخشبب( بنات | Intermediate and Secondary School for Girls in Al-Khashab Elementary School | Secondary | Girls | NB | RAFHA | 29°17'54.6"N 44°02'06.4"E | KFM2120660276966 | 10006033805 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 46 | SS-ZAM-NB1046 | روضة ام غار الخشيبي | Umm Ghar Al-Khushaibi Kindergarten | Kindergarten | Girls | NB | RAFHA | 29°17'53.5"N 44°02'07.3"E | SMR2220661010613 | 10104043752 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 47 | SS-ZAM-NB1047 | مدرسة متوسطة ام غار الخشيبي بنين | Umm Ghar Al-Khushaibi Intermediate School (boys) | Intermediate | Boys | NB | RAFHA | 29°18'10.4"N 44°02'02.2"E | KFM2120660276971 | 10087852209 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 48 | SS-ZAM-NB1048 | مدرسة أم غار الخشيبي الابتدائية والمتوسطة (بنين) | Umm Ghar Al-Khushaibi Elementary and Intermediate School (Boys) | Primary | Boys | NB | RAFHA | 29°17'52.1"N 44°01'52.3"E | KFM2120660276972 | 10006033851 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 49 | SS-ZAM-NB1049 | مجمع مدارس المحمدية الإبتدائية برفحاء (بنات) | Al-Muhammadiyah Elementary Schools Complex in Rafha (Girls) | Primary | Girls | NB | RAFHA | 29°37'50.0"N 43°31'45.0"E | KFM2120660277374 | 10006036825 |  | 2026-04-21 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 50 | SS-ZAM-NB1050 | مدرسة متوسطة وثانوية ابن شريم ( بنين ) | Ibn Shuraim Intermediate and Secondary School (Boys) | Secondary | Boys | NB | RAFHA | 29°56'56.8"N 43°22'00.7"E | KFM2120660277074 | 10006036511 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 51 | SS-ZAM-NB1051 | مدرسة ابتدائية ابن شريم بنين | Ibn Shuraim Elementary School Boys | Primary | Boys | NB | RAFHA | 29°56'56.7"N 43°21'46.4"E | KFM2120660282110 | 10006025321 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 52 | SS-ZAM-NB1052 | مدرسة ابتدائية ومتوسطة وثانوية ابن شريم ( بنات ) | Ibn Shuraim Elementary, Intermediate, and Secondary School (Girls) | Secondary | Girls | NB | RAFHA | 29°56'43.4"N 43°21'59.8"E | KFM2120660277021 | 10006025349 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 53 | SS-ZAM-NB1053 | الروضة الثالثة | Third Kindergarten | Kindergarten | Girls | NB | RAFHA | 29°37'29.6"N 43°31'17.0"E | KFM2120660277432 | 10103724456 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 54 | SS-ZAM-NB1054 | المدرسة الثانوية الأولى برفحاء ( بنات ) | The First Secondary School in Rafha (Girls) | Secondary | Girls | NB | RAFHA | 29°38'01.3"N 43°30'29.1"E | KFM2120660276862 | 10006038697 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 55 | SS-ZAM-NB1055 | المدرسة الابتدائية والمتوسطة لتحفيظ القرآن برفحاء (بنات) | Rafha Elementary and Intermediate School for Quran Memorization (Girls) | Intermediate | Girls | NB | RAFHA | 29°37'23.8"N 43°31'04.6"E | KFM2120660277762 | 10006033289 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 56 | SS-ZAM-NB1056 | المتوسطة الأولى برفحاء (بنات) | First Intermediate School in Rafha (Girls) | Intermediate | Girls | NB | RAFHA | 29°38'12.6"N 43°29'57.9"E | KFM2120660281296 | 10006037054 |  | 2026-04-25 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 57 | SS-ZAM-NB1057 | ابتدائية تحفيظ القرآن الكريم | Elementary Memorization of the Holy Qur'an (Boys) | Primary | Boys | NB | AL-WOIQILAT | 30°21'20.7"N 42°14'06.6"E | KFM2020660157647 | 10006062315 |  | 2026-04-30 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 58 | SS-ZAM-NB1058 | ابتدائية طارق بن زياد بنين | Tariq bin Ziyad Elementary School (Boys) | Primary | Boys | NB | AL-WOIQILAT | 30.364100,42.232296 | KFM2120660242665 | 10006016027 |  | 2026-05-06 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 59 | SS-ZAM-NB1059 | مدرسة قرطبة الابتدائية | Cordoba Elementary School | Primary | Boys | NB | AL-WOIQILAT | 30°22'24.3"N 42°13'43.3"E | KFM2120660237744 | 10006016045 |  | 2026-05-04 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 60 | SS-ZAM-NB1060 | ثانوية ابن الجوزي بالعويقيلة بنين | Ibn Al-Jawzi Secondary School in Al-Uwaigilah (Boys) | Secondary | Boys | NB | AL-WOIQILAT | 30°22'28.3"N 42°13'37.8"E | KFM2120660237739 | 10088728552 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 61 | SS-ZAM-NB1061 | متوسطة العويقيلة بنين | Al-Uwaigilah Intermediate School (Boys) | Intermediate | Boys | NB | AL-WOIQILAT | 30°22'01.0"N 42°14'33.5"E | KFM2120660237709 | 10006016152 |  | 2026-05-05 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 62 | SS-ZAM-NB1062 | ثانوية العويقيلة بنين | Al-Uwaigilah Secondary School (Boys) | Secondary | Boys | NB | AL-WOIQILAT | 30°22'03.3"N 42°14'35.4"E | KFM2120660237713 | 10006062351 |  | 2026-05-05 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 63 | SS-ZAM-NB1063 | متوسطة ابن القيم الجوزية بنين | Ibn al-Qayyim Al-Jawziyya Intermediate School (Boys) | Intermediate | Boys | NB | AL-WOIQILAT | 30°21'51.0"N 42°14'43.1"E | KFM2120660242736 | 10006016036 |  | 2026-05-07 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 64 | SS-ZAM-NB1064 | الروضة الأولى بنات بالعويقلية | First Kindergarten (Girls) | Kindergarten | Girls | NB | AL-WOIQILAT | 30.368511,42.239521 | KFM2120660237708 | 10006015763 |  | 2026-05-07 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 65 | SS-ZAM-NB1065 | الابتدائية الأولى بنات | First Elementary School (Girls) | Primary | Girls | NB | AL-WOIQILAT | 30°21'42.8"N 42°14'03.8"E | KFM2120660242673 | 10006062333 |  | 2026-05-04 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 66 | SS-ZAM-NB1066 | الروضة الثانية بنات | Second Kindergarten (Girls) | Kindergarten | Girls | NB | AL-WOIQILAT | 30°21'42.6"N 42°14'03.5"E | KFM2120660242666 | 10006015899 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 67 | SS-ZAM-NB1067 | تحفيظ القرآن الكريم التعليمي ابتدائية - متوسط بنات | Educational Quran Memorization Elementary - Intermediate (Girls) | Intermediate | Girls | NB | AL-WOIQILAT | 30°21'44.1"N 42°14'00.0"E | KFM2120660242672 | 10006062549 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 68 | SS-ZAM-NB1068 | الثانوية الأولى بنات | First Secondary School (Girls) | Secondary | Girls | NB | AL-WOIQILAT | 30°21'42.0"N 42°14'23.3"E | KFM2120660242716 | 10006016125 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 69 | SS-ZAM-NB1069 | ابتدائية المركوز بنين | Al-Markouz Elementary School (Boys) | Primary | Boys | NB | AL-WOIQILAT | 30°07'53.2"N 42°37'50.9"E | KFM2120660242596 | 10006015656 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 70 | SS-ZAM-NB1070 | مجمع متوسطة وثانوية المركوز | Al-Markouz Intermediate and Secondary School Complex | Intermediate | Girls | NB | AL-WOIQILAT | 30°08'00.9"N 42°38'03.5"E | KFM2120660242603 | 10006015871 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 71 | SS-ZAM-NB1071 | المتوسطة الثانية بنات | Second Intermediate School (Girls) | Intermediate | Girls | NB | AL-WOIQILAT | 30°22'13.5"N 42°14'16.8"E | KFM2120660237652 | 10006016279 |  | 2026-05-03 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 72 | SS-ZAM-NB1072 | ابتدائية الكاسب بنين | Al-Kaseb Elementary School (Boys) | Primary | Boys | NB | AL-WOIQILAT | 30°30'11.4"N 41°56'03.7"E | KFM2120660242629 | 10006015988 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 73 | SS-ZAM-NB1073 | ابتدائية الثنيان بنات | Al-Thunayan Elementary School (Girls) | Primary | Girls | NB | AL-WOIQILAT | 30°27'23.8"N 42°00'29.6"E | KFM2020760238975 | 10010338967 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 74 | SS-ZAM-NB1074 | ابتدائية عبد الله بن رواحة بنين | Abdullah bin Rawaha Elementary School Boys | Primary | Boys | NB | AL-WOIQILAT | 30°21'28.7"N 42°14'26.6"E | SMR2220661010533 | 10006014631 |  | 2026-05-06 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 75 | SS-ZAM-NB1075 | الابتدائية الثانية بنات | Second Elementary School Girls | Primary | Girls | NB | AL-WOIQILAT | 30°21'39.1"N 42°14'23.1"E | KFM2120660242719 | 10006016134 |  | 2026-05-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 76 | SS-ZAM-NB1076 | مجمع المركوز التعليمي متوسط - ثانوي بنات | Al-Markouz Educational Complex Intermediate - Secondary Girls | Secondary | Girls | NB | AL-WOIQILAT | 30°08'10.3"N 42°37'57.2"E | KFM2120660242703 | 30113345066 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 77 | SS-ZAM-NB1077 | ابتدائية المركوز بنات | Al-Markouz Elementary School Girls | Primary | Girls | NB | AL-WOIQILAT | 30°08'10.3"N 42°37'57.2"E | KFM2120660242697 | 10006016072 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 78 | SS-ZAM-NB1078 | مجمع المقدسي التعليمي ابتدائي - متوسط - ثانوي بنين | Al-Maqdisi Educational Complex: Elementary - Intermediate - Secondary Boys | Secondary | Boys | NB | AL-WOIQILAT | 29°32'35.0"N 42°05'39.3"E | KFM2120660242730 | 10006016288 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 79 | SS-ZAM-NB1079 | محمد بن القاسم | Muhammad ibn al-Qasim | Primary | Boys | NB | ARAR | 30.99190542, 41.05596459 | KFM2020660033288 | 10006064187 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 80 | SS-ZAM-NB1080 | الإمام الشافعي | Imam Al-Shafi'i | Primary | Boys | NB | ARAR | 30.97653773756366, 41.043837691729436 | KFM2120660237669 | 10006040819 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 81 | SS-ZAM-NB1081 | معن بن زائده | Ma'n ibn Za'idah | Primary | Boys | NB | ARAR | 30.979070277627, 41.036888859193496 | KFM2020760235253 | 10006063878 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 82 | SS-ZAM-NB1082 | خالد بن الوليد | Khalid ibn al-Walid | Primary | Boys | NB | ARAR | 30.977380539454288, 41.03015668987942 | KFM2020660025402 | 10006019691 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 83 | SS-ZAM-NB1083 | عين جالوت | Ain Jalut | Primary | Boys | NB | ARAR | 30.96484797151749, 41.00182822426583 | KFM2020660178698 | 10006045431 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 84 | SS-ZAM-NB1084 | الإمام مسلم | Imam Muslim | Primary | Boys | NB | ARAR | 30.992609549553734, 41.007128483613855 | KFM2020660178650 | 10006062656 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 85 | SS-ZAM-NB1085 | سلمان الفارسي | Salman Al-Farsi | Intermediate | Boys | NB | ARAR | 30.95884693690836, 41.03818996595516 | KFM2020660178893 | 10006041315 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 86 | SS-ZAM-NB1086 | الابتدائية التاسعة عشرة بعرعر | The nineteenth elementary school in Arar | Primary | Girls | NB | ARAR | 30.98030170499109, 41.05499840321394 | KFM2020660024365 | 10006064024 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 87 | SS-ZAM-NB1087 | الابتدائية الثلاثون بنات | thirty elementary school, girls | Primary | Girls | NB | ARAR | 30.986672280696574, 41.05731778360853 | KFM2020660180973 | 10101112810 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 88 | SS-ZAM-NB1088 | ابتدائية التاسعة | Ninth Elementary | Primary | Girls | NB | ARAR | 30.985033389151816, 41.03923087308402 | KFM2020660178712 | 10006049743 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 89 | SS-ZAM-NB1089 | ابن باز | Ibn Baz | Secondary | Boys | NB | ARAR | 30.97274392555545, 41.01809256588719 | KFM2020660178596 | 10006073696 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 90 | SS-ZAM-NB1090 | صهيب الرومي | Suhaib Al-Rumi | Intermediate | Boys | NB | ARAR | 30.977730483166297, 41.05189625919362 | KFM2020660024326 | 10006064418 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 91 | SS-ZAM-NB1091 | الخامسة والثلاثون | Thirty-fifth | Primary | Boys | NB | ARAR | 30.966573588216104, 41.001945925718104 | KFM2120660242607 | 10086336642 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 92 | SS-ZAM-NB1092 | السادسة الابتدائية | Sixth Elementary | Primary | Girls | NB | ARAR | 30.969500044529358, 41.038865589188376 | KFM2020660033423 | 10006041763 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 93 | SS-ZAM-NB1093 | الرابعة المتوسطة | Fourth intermediate | Intermediate | Girls | NB | ARAR | 30.985603870838414, 41.03523185246135 | KFM2020660178714 | 10006017697 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 94 | SS-ZAM-NB1094 | الثالثة الابتدائية بنات | Third ELEMENTARY SCHOOL, Girls | Primary | Girls | NB | ARAR | 30.97223198585954, 41.01638828880997 | KFM2020660178811 | 10006019314 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 95 | SS-ZAM-NB1095 | الحادية عشر الابتدائية- | Eleventh Elementary | Primary | Girls | NB | ARAR | 30.689936358, 41.0257475110292 | KFM2020660034317 | 30018617390 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 96 | SS-ZAM-NB1096 | الثانية والثلاثون الابتدائية | Thirty-two elementary school | Primary | Girls | NB | ARAR | 31.0030670466253, 41.0487399493997 | KFM2120660242632 | 10091522701 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 97 | SS-ZAM-NB1097 | الاولى المتوسطة بنات | First Intermediate school in Arar, girls | Intermediate | Girls | NB | ARAR | 30.9715252146897, 41.012112177195 | KFM2020660178871 | 10006018916 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 98 | SS-ZAM-NB1098 | الروضة الخامسة حكومي | Fifth Kindergarten (Governmental) | Kindergarten | Girls | NB | ARAR | 30.956856, 41.039967 | KFM2020660178665 | 10006063537 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 99 | SS-ZAM-NB1099 | عبدالله بن الزبير | Abdullah ibn al-Zubayr | Intermediate | Boys | NB | THURAIF | 31.6674347404418, 38.6722458935453 | KFM2020660181715 | 10109151341 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 100 | SS-ZAM-NB1100 | الابتدائية التاسعة | Ninth Elementary | Primary | Girls | NB | THURAIF | 31.6726110982658, 38.6794314460432 | KFM2020660180808 | 10005981899 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 101 | SS-ZAM-NB1101 | بلال بن رباح | Bilal ibn Rabah | Intermediate | Boys | NB | THURAIF | 31.681527514833, 38.655944353066 | KFM2020660181478 | 10006035078 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 102 | SS-ZAM-NB1102 | حطين | Hittin | Primary | Boys | NB | THURAIF | 31.6790661820941, 38.6492699390904 | KFM2020660181774 | 10006046231 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 103 | SS-ZAM-NB1103 | الخامسه | Fifth | Secondary | Girls | NB | NB | 30.96091, 41.03268 | KFM2020660178751 | 10006073981 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 104 | SS-ZAM-NB1104 | صقر قريش | Saqar Quraish | Secondary | Boys | NB | NB | 30.9826495 41.0526728 | KFM2020660024070 | 10006041093 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 105 | SS-ZAM-NB1105 | السابعه | Seventh | Primary | Girls | NB | NB | 30.98507916778916, 41.03533026164307 | KFM2120660277688 | 10103952308 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 106 | SS-ZAM-NB1106 | مصعب بن عمير | Mus'ab ibn 'Umair | Intermediate | Boys | NB | NB | 30.98881261876433, 41.011815000000006 | KFM2020660178647 | 10006041164 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 107 | SS-ZAM-NB1107 | الفاروق | Al-Farouq | Intermediate | Boys | NB | NB | 30.990008 41.0452437 | KFM2020660178607 | 10006046429 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 108 | SS-ZAM-NB1108 | العباس بن عبدالمطلب | Al-Abbas ibn Abd al-Muttalib | Primary | Boys | NB | NB | 31.6610424,38.6537343 | KFM2020660181471 | 10006045941 |  | 2026-04-11 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 109 | SS-ZAM-NB1109 | المتوسطة الثانية | Second Intermediate | Intermediate | Girls | NB | NB | 30.37043, 42.21642 | KFM2020660181600 | 10006034025 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 110 | SS-ZAM-NB1110 | الابتدائية الثانية والعشرون بعرعر - بنات | The twenty-second elementary school in Arar | Primary | Girls | NB | NB | 30.98340820006508, 41.011149043368455 | KFM2020660178726 | 10006019637 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 111 | SS-ZAM-NB1111 | صلاح الدين الأيوبي-147 A | Saladin | Intermediate | Boys | NB | NB | 30.9631681 41.0302651 | KFM2120660237775 | 10006073945 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 112 | SS-ZAM-NB1112 | السادسة عشر | Sixteenth | Primary | Girls | NB | NB | 30.961162904217954, 41.032913655821524 | KFM2120660237726 | 30096641377 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 113 | SS-ZAM-NB1113 | ثانوية الثامنة | Eighth High School | Secondary | Girls | NB | NB | 30.96841, 41.04246 | KFM2020660033427 | 10006041960 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 114 | SS-ZAM-NB1114 | الامام عاصم للطفوله المبكره | Imam Asim for Early Childhood | Early Childhood | Boys | NB | NB | 30.96466, 41.03961 | KFM2020660180876 | 10006064392 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 115 | SS-ZAM-NB1115 | الرابعه عشر | Fourteenth | Intermediate | Girls | NB | NB | 30.9523696,41.0043723 | KFM2020660181851 | 10103342407 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 116 | SS-ZAM-NB1116 | الثانوية العاشرة بعرعر/12th thania ashar | Tenth Secondary School in Arar | Secondary | Girls | NB | NB | 30.9855, 41.03575 | KFM2020660157483 | 10006063706 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 117 | SS-ZAM-NB1117 | الرابعة والثلاثون | Thirty-fourth | Primary | Girls | NB | NB | 30.969819,41.052545 | KFM2020660024374 | 10101583359 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 118 | SS-ZAM-NB1118 | السابعة والعشرون | Twenty-seventh | Primary | Girls | NB | NB | 30.972957096064604, 41.05038109205669 | KFM2020660033419 | 10006062511 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 119 | SS-ZAM-NB1119 | الثامنه عشره | eighteenth | Primary | Girls | NB | NB | 30.97901624279709, 41.048576969651386 | KFM2020660178677 | 10006049190 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 120 | SS-ZAM-NB1120 | العشرون | Twenty Elemantry School | Primary | Girls | NB | NB | 30.980866124126408, 41.04545071242767 | KFM2120660237673 | 10006041629 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 121 | SS-ZAM-NB1121 | الأمير عبد العزيز بن مساعد | Prince Abdul Aziz bin Musa'id | Primary | Boys | NB | NB | 30.9771805 41.0520274 | KFM2020660033414 | 10006040318 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 122 | SS-ZAM-NB1122 | المتوسطة السادسة بعرعر | Sixth Intermediate School in Arar | Intermediate | Girls | NB | NB | 30.98024, 41.04545 | KFM2020660229103 | 10006041290 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 123 | SS-ZAM-NB1123 | الواحده والثلاثون | Thirty-one | Primary | Girls | NB | NB | 30.99093075391898, 41.00312264232861 | KFM2020660178856 | 10094553003 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 124 | SS-ZAM-NB1124 | التاسعة | Ninth | Secondary | Girls | NB | NB | 30.98075, 41.0552 | KFM2020660024063 | 10006040167 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 125 | SS-ZAM-NB1125 | الملك سعود | King Saud | Secondary | Boys | NB | NB | 30.9660424 41.0360181 | KFM2020660033367 | 10006062772 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 126 | SS-ZAM-NB1126 | ثانوية أجنادين | Ajnadin High School | Secondary | Boys | NB | NB | 30.991034556462388, 41.05764562698583 | KFM2020660181815 | 10006063331 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 127 | SS-ZAM-NB1127 | عبدالله بن عباس للطفولة المبكرة | Abdullah bin Abbas for Early Childhood | Primary | Boys | NB | NB | 30.98405, 41.04903 | KFM2020660180871 | 10006041146 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 128 | SS-ZAM-NB1128 | مكة المكرمة | Mecca | Secondary | Boys | NB | NB | 30.971821 41.040918 | KFM2020660178627 | 10006041119 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 129 | SS-ZAM-NB1129 | الثانوية الرابعة | Fourth Secondary School | Secondary | Girls | NB | NB | 31.68285, 38.65007 | KFM2020660181477 | 10087174979 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 130 | SS-ZAM-NB1130 | الابتدائية الثالثة والعشرون | Twenty-third Elementary School | Primary | Girls | NB | NB | 30.97566476666473, 41.03413003068555 | KFM2020660025407 | 10006063063 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 131 | SS-ZAM-NB1131 | مدارس التميز العلمي | Schools of Scientific Excellence | Secondary | Girls | NB | NB | 30.975027,41.058163 | KFM2020660180976 | 10096479667 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 132 | SS-ZAM-NB1132 | الإمام البخاري | Imam Bukhari | Intermediate | Boys | NB | NB | 30.9826694 41.0517933 | KFM2020660180873 | 10083653708 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 133 | SS-ZAM-NB1133 | لمدرسة الإبتدائية السابعة | Seventh Elementary School | Primary | Girls | NB | ARAR | 30.984335,41.035381 | SMR2220661010630 | 10006018854 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 134 | SS-ZAM-NB1134 | طلحة بن عبيدالله | Talha ibn Ubaydullah | Primary | Boys | NB | NB | 30.9965756 41.0226994 | KFM2020660178595 | 10006017061 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 135 | SS-ZAM-NB1135 | مدرسة ابن الأثير الإبتضائية | Ibn al-Athir | Primary | Boys | NB | NB | 30.9837501, 41.0106567 | KFM2020660178727 | 10006045225 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 136 | SS-ZAM-NB1136 | المعهد العلمي | Scientific Institute | Primary | Girls | NB | NB | 30.9954154 41.0213752 | KFM2020660154974 | 10006019495 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 137 | SS-ZAM-NB1137 | ثانوية أبي بكر الصديق بعرعر | Abu Bakr Al-Siddiq High School in Arar | Secondary | Boys | NB | NB | 30.989017953404584, 41.04454015027195 | KFM2020660178608 | 10006019753 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 138 | SS-ZAM-NB1138 | الملك خالد | King Khalid | Primary | Boys | NB | NB | 30.9869115 41.0423959 | Kfm2020660178621 | 10006018461 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 139 | SS-ZAM-NB1139 | المتطوسطه سابعه بعرعر | Seventh Middle school | Intermediate | Girls | NB | NB | 30.99569420558648, 41.02883237080394 | KFM2020660178811 | 10006019314 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 140 | SS-ZAM-NB1140 | ثانوية الملك فهد | King Fahd High School | Secondary | Boys | NB | NB | 30.9830639 41.0121429 | Kfm2020660178844 | 10006019619 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 141 | SS-ZAM-NB1141 | الابتدائية السابعة عشرة بعرعر | The Seventeenth Elementary School in Arar | Primary | Boys | NB | NB | 30.99401102190495, 41.026572909521605 | KFM2120660277685 | 10006064285 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 142 | SS-ZAM-NB1142 | الروضه حكومي السادسه | Sixth Government Kindergarten | Kindergarten | Girls | NB | NB | 30.991265070316686, 41.01818545281235 | KFM2020660178599 | 10006049734 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 143 | SS-ZAM-NB1143 | الحاديه عشر | Eleventh | Intermediate | Girls | NB | NB | 30.97282, 41.04994 | Kfm2020660033417 | 10006064015 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 144 | SS-ZAM-NB1144 | الثانوية الثانيه | Second Secondary School | Secondary | Girls | NB | NB | 30.997342794551894, 41.0307545505276 | KFM2020660178787 | 10006063457 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 145 | SS-ZAM-NB1145 | محمد بن عبدالوهاب | Muhammad ibn Abd al-Wahhab | Primary | Boys | NB | NB | 30.9819565 41.0203502 | Kfm2020660178840 | 10006045637 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 146 | SS-ZAM-NB1146 | غرناطه | Granada | Intermediate | Boys | NB | ARAR | 30.991336565522772, 41.056582799243365 | KFM2020660033282 | 10006064178 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 147 | SS-ZAM-NB1147 | المتوسطة الأولى | First Intermediate | Intermediate | Girls | NB | NB | 31.67139, 38.65257 | KFM2020660180576 | 10006046062 |  | 2026-04-21 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 148 | SS-ZAM-NB1148 | الابتدائية العاشرة | Tenth Elementary | Primary | Girls | NB | NB | 31.67182, 38.65309 | KFM2020660180559 | 10006034268 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 4 | In Progress
| 149 | SS-ZAM-NB1149 | الابتدائية الرابعة عشرة | Fourteenth Elementary School | Primary | Girls | NB | THURAIF | 31.6594616619569, 38.6735949594113 | KFM2020660180807 | 10093083557 |  | 2026-04-11 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 150 | SS-ZAM-NB1150 | الابتدائية الثامنة | Eighth Elementary | Primary | Girls | NB | THURAIF | 31.6714788589381 38.6744961816118 | KFM2020660181593 | 10085050730 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 151 | SS-ZAM-NB1151 | الابتدائية الثانية عشرة | Twelfth Elementary | Primary | Girls | NB | THURAIF | 31.6699083105663 38.6653981289209 | KFM2020660181504 | 10006034007 |  | 2026-04-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 152 | SS-ZAM-NB1152 | مدرسة ابن جبير الابتدائية للبنين | Ibn Jubair Elementary School for Boys | Primary | Boys | NB | ARAR | 30.9946329356615 '41.0165508205643 | KFM2020660178601 | 10006019673 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 153 | SS-ZAM-NB1153 | أسامة بن زيد | Usama ibn Zayd | Primary | Boys | NB | ARAR | 30.9905503495952 41.0265092105344 | KFM2020660178789 | 10006048399 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 154 | SS-ZAM-NB1154 | التاسعه المتوسطة بنات | ninth intermediate girls | Intermediate | Girls | NB | ARAR | 30.99180761035608, 41.008037152063 | KFM2020660178644 | 10006063582 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 155 | SS-ZAM-NB1155 | أم المؤمنين عائشه رضي الله عنها | Mother of the Believers Aisha | Primary | Girls | NB | ARAR | 30.9957395607812 40.9973425174746 | kfm2120660242722 | 10006064571 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 156 | SS-ZAM-NB1156 | سليمان بن عبدالملك | Sulayman ibn Abd al-Malik | Primary | Boys | NB | ARAR | 30.9319085519574 41.092538847553 | KFM2020660178708 | 10006064070 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 157 | SS-ZAM-NB1157 | المتوسطة السادسة عشر للبنات | 16th Middle School | Intermediate | Girls | NB | NB | 30.99517611379525, 40.999673713066244 | KFM2020660178858 | 10089666884 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 158 | SS-ZAM-NB1158 | الثانوية السادسة بنات | Sixth Girls' High School | Secondary | Girls | NB | NB | 30.974848,41.003529 | kfm2020660180855 | 10006018891 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 159 | SS-ZAM-NB1159 | الثانية عشر | Twelfth | Primary | Girls | NB | NB | 30.984972,41.035084 | KFM2020660180970 | 10006063798 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 160 | SS-ZAM-NB1160 | الثامنة والعشرون | Twenty-eighth | Primary | Girls | NB | NB | 30.95926315476062, 41.0397053227521 | kfm2020660178707 | 10006063528 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 161 | SS-ZAM-NB1161 | الرابعة عشر | Fourteenth | Intermediate | Girls | NB | NB | 30.9865787177264 41.0634261309833 | MMF2320601008493 | 10089394855 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 162 | SS-ZAM-NB1162 | أبو أيوب الأنصاري | Abu Ayyub al-Ansari | Primary | Boys | NB | NB | 30.9728449 41.0177511 | KFM2020660180970 | 10006063798 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 163 | SS-ZAM-NB1163 | الثانوية الثالثة بطريف | Third Secondary School in Tarif | Secondary | Girls | NB | NB | 31.670245,38.6657317 | KFM2020660181501 | 10006033986 |  | 2026-04-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 164 | SS-ZAM-NB1164 | المتوسطة الخامسة | Fifth Intermediate | Intermediate | Girls | NB | NB | 31.68266, 38.65077 | KFM2020660181480 | 10087178593 |  | 2026-05-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 165 | SS-ZAM-NB1165 | الابتدائية الثانية للبنات بطريف | Second Elementary School for Girls in Tarif | Primary | Girls | NB | NB | 31.68027, 38.64762 | SMR2220661010530 | 10006045360 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 166 | SS-ZAM-NB1166 | معاويه بن أبي سفيان | Muawiyah ibn Abi Sufyan | Secondary | Boys | NB | NB | 31.67376, 38.67983 | KFM2020660180560 | 10006034535 |  | 2026-04-22 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 167 | SS-ZAM-NB1167 | أبو موسى الأشعري | Abu Musa al-Ash'ari | Primary | Boys | NB | NB | 31.674, 38.67117 | KFM2020660230693 | 10006033903 |  | 2026-04-27 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 168 | SS-ZAM-NB1168 | مجمع علي بن أبي طالب التعليمي | Ali Bin Abi Talib Educational Complex | Intermediate | Boys | NB | NB | 31.67557, 38.67567 | KFM2020660181531 | 10006044881 |  | 2026-04-21 | Completed | Completed | Completed | Completed | In Progress | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 5 | In Progress
| 169 | SS-ZAM-NB1169 | الروضة الخامسة | Fifth Kindergarten | Kindergarten | Girls | NB | NB | 31.67274, 38.6841 | KFM2020660180662 | 10103074431 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 170 | SS-ZAM-NB1170 | نايف بن عبدالعزيز | Naif bin Abdulaziz | Secondary | Boys | NB | NB | 31.66586, 38.65846 | KFM2020660230699 | 10005981880 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 171 | SS-ZAM-NB1171 | جعفر الطيار | Jafar al-Tayyar | Secondary | Boys | NB | NB | 31.65684, 38.68191 | KFM2020660181461 | 10006034562 |  | 2026-04-25 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 172 | SS-ZAM-NB1172 | الابتدائية الحادية عشرة | Eleventh Elementary | Primary | Girls | NB | NB | 31.667769,38.657113 | KFM2020660180571 | 10006047963 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 0 | In Progress
| 173 | SS-ZAM-NB1173 | الروضة الثانية | Kindergarten 2 | Kindergarten | Girls | NB | NB | 31.666882591236885, 38.65767267800416 | KFM2020660180720 | 10006047981 |  | 2026-04-12 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 174 | SS-ZAM-NB1174 | عبدالرحمن بن عوف | Abdul Rahman bin Awf | Primary | Boys | NB | NB | 31.67376, 38.64507 | KFM2020660230695 | 10006047678 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 175 | SS-ZAM-NB1175 | القادسية الإبتدائية بنين | Al-Qadisiyah | Intermediate | Boys | NB | THURAIF | 31.66957, 38.648 | KFM2020660230619 | 10006033814 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 176 | SS-ZAM-NB1176 | احمد بن حنبل | Ahmad ibn Hanbal | Primary | Boys | NB | THURAIF | 31.67537, 38.68026 | KFM2020660230634 | 10006046151 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started |  | 0 | 4 | In Progress
| 177 | SS-ZAM-NB1177 | الابتدائية الثانية بنات | Second Primary School for Girls | Primary | Girls | NB | ARAR | 30.994370,41.026154 | KFM2020660157467 | 10006063081 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 178 | SS-ZAM-NB1178 | الثانوية الثالثه بنات | Third High School for Girls | Secondary | Girls | NB | ARAR | 30.961216,41.033810 | KFM2120660237762 | 10006073963 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 179 | SS-ZAM-NB1179 | النعمان بن مقرن | Al-Numan ibn Muqrin | Intermediate | Boys | NB | ARAR | 30°59'42.4"N 41°01'22.6"E | KFM2020660157535 | 10006016724 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 180 | SS-ZAM-NB1180 | الملك عبدالعزيز | King Abdulaziz | Primary | Boys | NB | ARAR | 30.962561825393145, 41.04226583583268 | KFM2020660024419 | 10006041208 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 181 | SS-ZAM-NB1181 | الروضة العاشرة بعرعر | The tenth kindergarten in Arar | Kindergarten | Girls | NB | NB | 30.976063734366452, 41.00935991777005 | KFM2020660180856 | 10006019717 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 0 | 4 | In Progress
| 182 | SS-ZAM-NB1182 | الابتدائية الرابعة عشر بعرعر | Fourteenth Elementary School in Arrar | Primary | Girls | NB | NB | 30.99493733726857, 41.03028808091357 | KFM2120660242640 | 10084051053 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 183 | SS-ZAM-NB1183 | المساعدية الابتدائية | Al-Musaidia Primary | Primary | Boys | NB | ARAR | 30.975889, 41.009316 | KFM2020660180856 | 10006019717 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 184 | SS-ZAM-NB1184 | تحفيظ القرآن الكريم | Memorization of the Holy Quran | Primary | Girls | NB | ARAR | 30.996674951588716, 41.02977698511809 | KFM2020660178782 | 10006048998 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 185 | SS-ZAM-NB1185 | الثانية عشر الثانوية | 12th High school - Girls | Secondary | Girls | NB | ARAR | 30.97146833108967, 41.04691335326192 | SMR2220661010644 | 10104775825 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 186 | SS-ZAM-NB1186 | الروضة الثالثة حكومي | Al-Rawda Third Governmental | Kindergarten | Girls | NB | ARAR | 30.99585921524034, 41.028449955374086 | KFM2020660180870 | 10006018774 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 187 | SS-ZAM-NB1187 | الروضة الثالثة عشر حكومي | Al-Rawda 13 Government School | Kindergarten | Girls | NB | ARAR | 30.98177254060676, 40.96602206775324 | SMR2220661010640 | 10104212597 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 188 | SS-ZAM-NB1188 | روضة إم كلثوم الاموية | Roza Umm Kulthum Al-Umayyad | Kindergarten | Girls | NB | ARAR | 30.999575763312674, 41.06584415321321 | SMR2220661010622 | 10104099589 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 189 | SS-ZAM-NB1189 | الروضة الرابعة حكومي | Al-Rawda Fourth Governmental | Kindergarten | Girls | NB | ARAR | 30.968117941298868, 41.0429115788357 | KFM2020660033424 | 10006041941 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 190 | SS-ZAM-NB1190 | الابتدائية الثالثة | Third Primary School | Primary | Girls | NB | THURAIF | 31.678846497548985, 38.651332322546274 | KFM2020660181595 | 10006046115 |  | 2026-04-11 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 191 | SS-ZAM-NB1191 | الروضة الحادية عشر حكومي | Eleventh Governmental Kindergarten | Kindergarten | Girls | NB | ARAR | 31.0031788578744, 41.04903726368209 | KFM2020660181800 | 10091519920 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 192 | SS-ZAM-NB1192 | روضة درة الاموية | Umayyad Darrah Garden | Kindergarten | Girls | NB | ARAR | 30.924019, 41.090591 | SMR2220661010682 | 10104181697 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 193 | SS-ZAM-NB1193 | المتوسطة الثالثة | Third Intermediate | Intermediate | Girls | NB | THURAIF | 31.676647403407323, 38.65071442245288 | KFM2020660182886 | 10006033215 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 194 | SS-ZAM-NB1194 | محمد بن سيرين | Muhammad ibn Sirin | Intermediate | Boys | NB | ARAR | 30.995161202802173, 41.004685761042666 | SMR2220661010626 | 10104571413 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 195 | SS-ZAM-NB1195 | الثانوية الثانية الثانوية بنت | The second secondary, the secondary girl | Secondary | Girls | NB | THURAIF | 31.67211515326865, 38.670749036744155 | KFM2020660181545 | 10006045163 |  | 2026-04-09 | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 196 | SS-ZAM-NB1196 | روضة بثينة الإنصارية | Rawda Buthaina Al-Ansariyah | Kindergarten | Girls | NB | THURAIF | 31.671290477981877, 38.64312715444876 | SMR2220661010527 | 10006046133 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 197 | SS-ZAM-NB1197 | الروضة الرابعة بنت | Al-Rawda Fourth Girl | Kindergarten | Girls | NB | THURAIF | 31.66801860335775, 38.676738116778814 | KFM2020660180802 | 10101986942 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 198 | SS-ZAM-NB1198 | ابن تيمية | Ibn Taymiyyah | Primary | Boys | NB | NB | 30.9963655524018, 41.0215916726677 | KFM2020660178646 | 10006063199 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 199 | SS-ZAM-NB1199 | الأندلس | Andalusia | Primary | Boys | NB | NB | 30.9835889 41.0651961 | KFM2020660180978 | 10006064202 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
| 200 | SS-ZAM-NB1200 | عبدالله بن مسعود | Abdullah bin Masoud | Primary | Boys | NB | NB | 31.68169, 38.65539 | KFM2020660219253 | 10006046563 |  |  | Completed | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | In Progress |  | 1 | 4 | In Progress
Total | [11 empty] | Total | Completed | 165 | 165 | 165 | 165 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.2
[13 empty] | In Progress | 0 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162
[13 empty] | Not Started | 35 | 35 | 35 | 35 | 85 | 182 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 38
Note on N4: 4/2/2025

## Najran Schools -1
|  | Report Date | 2026-05-10
Project | Schools Information | [11 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School No | School ID | School Name (Arabic) | School Name (English) | School Level | School Gender (Boys / Girls) | Region | City | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Najran -1 | 1 | SS-ZAM-NJR1001 | المثني بن حارثة الابتائية بنين | Al-Muthanna ibn Haritha al-Ibta'iyya Banu | Primary | Boys | Najran | Najran | 17°32'53.7"N 44°15'08.2"E | HLY2020627049386 | 10052885233 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Primary | Boys | Not Started
| 2 | SS-ZAM-NJR1002 | بلال ابن رباح الابتدائية | Bilal Ibn Rabah Elementary School | Primary | Boys | Najran | Najran | 17°31'12.0"N 44°16'31.7"E | SXE2120627091079 | 10052454478 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Intermediate | Girls | In Progress
| 3 | SS-ZAM-NJR1003 | الشرفة المتوسطة بنات | The middle balcony for girls | Intermediate | Girls | Najran | Najran | 17.515808385721865, 44.27971549725874 | SXE2120627091033 | 10052930821 |  | 2026-04-14 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Secondary | NA | Completed
| 4 | SS-ZAM-NJR1004 | جمانه بنت ابي طالب للطفوله المبكره | Jumana bint Abi Talib for Early Childhood | Early Childhood | Girls | Najran | Najran | 17°30'58.7"N 44°16'46.8"E | SXE2120627091037 | 10052807003 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | KinderGarten |  | NA
| 5 | SS-ZAM-NJR1005 | مدرسة الإمام مسلم الإبتدائية | Imam Muslim Elementary School | Primary | Boys | Najran | Najran | 17.516446129960872, 44.281018622774525 | HLY2020627042703 | 10053051853 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started | Early Childhood
| 6 | SS-ZAM-NJR1006 | ابن الاثير الثانوية بنين | Ibn Al-Atheer Secondary School for Boys | Secondary | Boys | Najran | Najran | 17.56804866615516, 44.220248652183 | HLY2020627049388 | 10052805321 |  | 2026-04-14 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | NA
| 7 | SS-ZAM-NJR1007 | عبد الرحمن الداخل الابتدائية بنين | Abdul Rahman Al-Dakhil Primary School for Boys | Primary | Boys | Najran | Najran | 17.546787146795022, 44.26245775463659 | HLY2020627051042 | 10052805152 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 8 | SS-ZAM-NJR1008 | العرباض بن سارية الثانوية بنين | Al-Arbad Bin Sariya Secondary School for Boys | Secondary | Boys | Najran | Najran | 17.58283179738222, 44.235805615389786 | HLY2020627051496 | 10052805466 |  | 2026-04-20 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 9 | SS-ZAM-NJR1009 | عبد الله بن رواحة المتوسطة بنين | Abdullah bin Rawaha Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17.562527415912324, 44.3240732976294 | HLY2020627051498 | 10052574931 |  | 2026-04-20 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 10 | SS-ZAM-NJR1010 | مدرسة المركب الابتدائية بنين | Al-Murakkab Primary School for Boys | Primary | Boys | Najran | Najran | 17.56299673728043, 44.3184469527873 | SXE2120627091060 | 10052741538 |  | 2026-04-19 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 11 | SS-ZAM-NJR1011 | مدرسة متوسطة ريمان للبنات (المتوسطة العاشرة) | Reeman Intermediate School for Girls (Tenth Intermediate School) | Intermediate | Girls | Najran | Najran | 17.533583459075132, 44.33449181676425 | HLY2020627049414 | 10053049013 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 12 | SS-ZAM-NJR1012 | العريسة الابتدائية بنين | Al-Arisa Elementary School for Boys | Primary | Boys | Najran | Najran | 17.547263068330036, 44.38611703626818 | SMR2320621019086 | 10052494473 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 13 | SS-ZAM-NJR1013 | ريمان الابتدائية بنات | Riman Elementary Girls | Primary | Girls | Najran | Najran | 17.557610692991435, 44.30444430558722 | SXE2020627018216 | 10052445924 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 14 | SS-ZAM-NJR1014 | بن ماجة الثانوية بنين | Ibn Majah Secondary School for Boys | Secondary | Boys | Najran | Najran | 17.547263068330036, 44.38611703626818 | SXE2120627091075 | 10052892256 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 15 | SS-ZAM-NJR1015 | ثانويه المركب بنات | Al-Murakkab Girls' Secondary School | Secondary | Girls | Najran | Najran | 17.527288021514792, 44.32555054053518 | HLY2020627049401 | 10053005485 |  | 2026-04-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 16 | SS-ZAM-NJR1016 | متوسطة المركب بنات | Al-Murakab Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17.529228461931286, 44.32678448948463 | HLY2020627049354 | 10052741799 |  | 2026-04-19 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 17 | SS-ZAM-NJR1017 | المدرسه الثانيه والثلاثون للطفوله المبكره | The thirty-second school for early childhood | Early Childhood | Girls | Najran | Najran | 17.533776157437277, 44.33605576112488 | HLY2020627051548 | 10095085800 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 18 | SS-ZAM-NJR1018 | ام عمار للطفوله المبكره | Umm Ammar for Early Childhood | Early Childhood | Girls | Najran | Najran | 17.562992935342113, 44.255814403391184 | HLY2020627052033 | 10102470716 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 19 | SS-ZAM-NJR1019 | المدرسة الواحد والأربعون الابتدائية بنات | The Forty-First Girls' Elementary School | Primary | Girls | Najran | Najran | 17°33'33.9"N 44°18'07.2"E | SXE2120627106550 | 10052929679 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 20 | SS-ZAM-NJR1020 | الابتدائية الرابعة والثلاثون بنات | The thirty-fourth girls' elementary school | Primary | Girls | Najran | Najran | 17°34'28.6"N 44°14'42.1"E | SXE2120627106569 | 10053050159 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 21 | SS-ZAM-NJR1021 | الروضة الواحدة والعشرون بنات | The twenty-first kindergarten for girls | KinderGarten | Girls | Najran | Najran | 17.563843400330217, 44.312963417236055 | SXE2020627015665 | 10082489358 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 22 | SS-ZAM-NJR1022 | الحديبية الثانوية بنين | Al-Hudaybiyah Secondary School for Boys | Secondary | Boys | Najran | Najran | 17.56389900025158, 44.3127284122738 | HLY2020627049622 | 10052702370 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 23 | SS-ZAM-NJR1023 | المدرسة الواحده والعشرون للطفوله المبكره | The Twenty-First Early Childhood School | Early Childhood | Girls | Najran | Najran | 17.75908944290501, 44.45877815767236 | HLY2020627049448 | 10052374493 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 24 | SS-ZAM-NJR1024 | المدرسة المتوسطة الثانيه والعشرون | Twenty-second Intermediate School | Intermediate | Girls | Najran | Najran | 17.578583773018966, 44.23307967142225 | HLY2020627051049 | 10084789193 |  | 2026-04-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 25 | SS-ZAM-NJR1025 | مصعب بن عمير | Mus'ab ibn 'Umair | Primary | Boys | Najran | Najran | 17.578952843371024, 44.233397555708855 | HLY2020627049356 | 10052743201 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 26 | SS-ZAM-NJR1026 | الخامسه عشر المتوسطه بنات | Fifteenth Intermediate Girls | Intermediate | Girls | Najran | Najran | 17.600413551942243, 44.45979927116382 | HLY2020627051555 | 10052736467 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 27 | SS-ZAM-NJR1027 | ام كعب الأنصارية للطفوله المبكره | Umm Ka'b Al-Ansariyah for Early Childhood | Early Childhood | Girls | Najran | Najran | 17.544119764838396, 44.28499866674047 | HLY2020627051553 | 10052783298 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 28 | SS-ZAM-NJR1028 | ام القرى المتوسطة | Umm al-Qura al-Mutawassita | Intermediate | Boys | Najran | Najran | 17.544424480587235, 44.284493999999995 | HLY2020627049422 | 10052781506 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 29 | SS-ZAM-NJR1029 | ثانوية شرحبيل بن حسنه بنين | Sharhabil Bin Hasna Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°30'05.3"N 44°19'44.4"E | HLY2020627050267 | 10053051227 |  | Saturday 9 May 2026 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 30 | SS-ZAM-NJR1030 | العباس بن عبد المطلب الثانويه | Al-Abbas ibn Abd al-Muttalib Secondary School | Secondary | Boys | Najran | Najran | 17°34'48.8"N 44°32'39.0"E | HLY2020627046673 | 10096688630 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 31 | SS-ZAM-NJR1031 | الحايرة للطفوله المبكره | The Confused One for Early Childhood | Early Childhood | Girls | Najran | Najran | 17.530636016296626, 44.68072073510088 | HLY2020627047212 | 10052971501 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 32 | SS-ZAM-NJR1032 | عبد الله بن الزبير الابتدائية بنين | Abdullah bin Al-Zubair Elementary School for Boys | Primary | Boys | Najran | Najran | 17°34'30.9"N 44°30'33.9"E | HLY2020627051942 | 10052738864 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 33 | SS-ZAM-NJR1033 | خولة بنت عمرو للطفولة المبكرة بنات | Khawla Bint Amr for Early Childhood Girls | Early Childhood | Girls | Najran | Najran | 17.58556065491332, 44.35656954047437 | HLY2020627046761 | 10053091133 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 34 | SS-ZAM-NJR1034 | الخباش الابتدائية بنين | Al-Khabash Primary School for Boys | Primary | Boys | Najran | Najran | 17.55475979840392, 44.70933505767237 | SXE2020627043078 | 10053045220 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 35 | SS-ZAM-NJR1035 | ابو فراس الحمداني الابتدائية بنين | Abu Firas Al-Hamdani Elementary School for Boys | Primary | Boys | Najran | Najran | 17.628578087743843, 44.474731299999995 | HLY2020627047184 | 10052932791 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 36 | SS-ZAM-NJR1036 | مدرسة خباش الابتدائية بنات | Khabash Primary School for Girls | Primary | Girls | Najran | Najran | 17.555718555579396, 44.70867357116382 | HLY2020627044914 | 10052736618 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 37 | SS-ZAM-NJR1037 | متوسطة الخباش بنات | Al-Khabash Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17.603002368942192, 44.52851142883618 | HLY2020627046762 | 10053054256 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 38 | SS-ZAM-NJR1038 | خباب بن الإرث الثانويه | Khabbab bin Al-Arth Secondary School | Secondary | Boys | Najran | Najran | 17.5510587732835, 44.70845228650853 | HLY2020627051470 | 10052736289 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 39 | SS-ZAM-NJR1039 | متوسطة بئر عسكر بنات | Bir Askar Girls' Intermediate School | Intermediate | Girls | Najran | Najran | 17.550721579635713, 44.70859001349146 | HLY2020627051477 | 10052374359 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 40 | SS-ZAM-NJR1040 | جعفر الطيار المتوسطة | Jaafar Al-Tayyar Intermediate School | Intermediate | Boys | Najran | Najran | 17°35'09.8"N 44°04'25.9"E | HLY2020627051469 | 10052528286 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 41 | SS-ZAM-NJR1041 | سايلة غزال الابتدائية بنين | Sayla Ghazal Elementary School for Boys | Primary | Boys | Najran | Najran | 17°34'27.5"N 44°02'47.5"E | HLY2020627049507 | 10052932066 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 42 | SS-ZAM-NJR1042 | الروضة الثامنة بسايلة غزال / عاتكة | The eighth kindergarten in Sayla Ghazal / Atika | KinderGarten | Girls | Najran | Najran | 17.582062359332564, 44.07091915630106 | SXE2020627018137 | 10052608691 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 43 | SS-ZAM-NJR1043 | ثانوية ابن القيم وبرنامج التربية الفكرية | Ibn Al-Qayyim High School and the Intellectual Education Program | Secondary | Boys | Najran | Najran | 17.83172254246467, 44.33595375767236 | HLY2020627044474 | 10052704472 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 44 | SS-ZAM-NJR1044 | ابتدائية حبونا الثانية بنات | Habuna Second Girls' Elementary School | Primary | Girls | Najran | Najran | 17.832661820662594, 44.336045242327636 | HLY2020627044405 | 10095382359 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 45 | SS-ZAM-NJR1045 | المنتشر الابتدائية بنات | Al-Muntashir Primary School for Girls | Primary | Girls | Najran | Najran | 17.850970115659383, 44.0268537558191 | HLY2020627049611 | 10052932271 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 46 | SS-ZAM-NJR1046 | ابتدائية المجمع بنين | Al-Mujamma'a Elementary School for Boys | Primary | Boys | Najran | Najran | 17.852561537031335, 44.02812897823784 | HLY2020627044453 | 10052779811 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 47 | SS-ZAM-NJR1047 | المجمع المتوسطة | Intermediate Complex | Intermediate | Girls | Najran | Najran | 17.877817477885134, 44.15929947116383 | HLY2020627049579 | 10053116420 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 48 | SS-ZAM-NJR1048 | سعد بن الربيع الابتدائية | Saad bin Al-Rabee Elementary School | Primary | Boys | Najran | Najran | 17°45'19.0"N 43°57'42.8"E | HLY2020627047208 | 10052529167 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 49 | SS-ZAM-NJR1049 | ثانوية جابر بن حيان | Jaber Bin Hayyan High School | Secondary | Boys | Najran | Najran | 17°45'24.3"N 43°57'41.8"E | SXE2120627106504 | 10083402511 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 50 | SS-ZAM-NJR1050 | متوسطة الاحنف بن قيس | Al-Ahnaf bin Qais Intermediate School | Intermediate | Boys | Najran | Najran | 17°46'24.6"N 43°55'36.7"E | HLY2020627051451 | 10052848409 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 51 | SS-ZAM-NJR1051 | متوسطة هاشم بن عبدالملك بنين | Hashim Bin Abdulmalik Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°46'47.1"N 43°55'11.5"E | HLY2020627044475 | 10052806104 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 52 | SS-ZAM-NJR1052 | حبونا الابتدائية بنين | Habona Elementary School for Boys | Primary | Boys | Najran | Najran | 17.574017760421984, 44.243627 | HLY2020627049522 | 10052605779 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 53 | SS-ZAM-NJR1053 | حبونا المتوسطة بنات | Habuna Intermediate Girls | Intermediate | Girls | Najran | Najran | 17.849725066514637, 44.0227807558191 | HLY2020627044445 | 10052452188 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 54 | SS-ZAM-NJR1054 | بني هميم بنات | Bani Hamim girls | Primary | Girls | Najran | Najran | 17.85007930322615, 44.022250355819104 | HLY2020627049374 | 10053010073 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 55 | SS-ZAM-NJR1055 | الخانق الابتدائية بنات | Al-Khanq Primary School for Girls | Primary | Girls | Najran | Najran | 17.84516837084512, 44.01703777116383 | HLY2020627044463 | 10052532421 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 56 | SS-ZAM-NJR1056 | هدادة المتوسطة بنات | Haddada Intermediate Girls | Intermediate | Girls | Najran | Najran | 17.81643827893347, 44.001069898146746 | HLY2020627044424 | 10052450049 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 57 | SS-ZAM-NJR1057 | الوليد بن عبدالملك المتوسطة - بنين | Al-Walid bin Abdulmalik Intermediate School - Boys | Intermediate | Boys | Najran | Najran | 17.732523491578256, 43.75852035581908 | HLY2020627044422 | 10052527645 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 58 | SS-ZAM-NJR1058 | ابا الطحين للطفولة المبكرة - بنات | Abu Al-Tahin for Early Childhood - Girls | Early Childhood | Girls | Najran | Najran | 17.605442614308277, 43.75631082580592 | HLY2020627042708 | 10052697851 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 59 | SS-ZAM-NJR1059 | الحرشف الإبتدائية - بنات | Al-Harshaf Primary School - Girls | Primary | Girls | Najran | Najran | 17°43'53.8"N 43°45'27.0"E | HLY2020627044468 | 10052931631 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 60 | SS-ZAM-NJR1060 | الجفة للطفولة المبكره | Early childhood care | Early Childhood | Girls | Najran | Najran | 17.696783188492493, 43.9508024358676 | HLY2020627044447 | 10052894312 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 61 | SS-ZAM-NJR1061 | هدادة الابتدائية للطفولة المبكرة | Haddada Primary School for Early Childhood | Primary | Girls | Najran | Najran | 17°40'27.9"N 43°53'15.1"E | HLY2020627044421 | 10052487998 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 62 | SS-ZAM-NJR1062 | فرع الجبل للطفولة المبكرة بنات | Al Jabal Branch for Early Childhood Girls | Early Childhood | Girls | Najran | Najran | 17°46'38.1"N 43°54'59.6"E | HLY2020627044528 | 10053048348 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 63 | SS-ZAM-NJR1063 | روضة البيان بهدادة | Rawdat Al-Bayan Bahdada | KinderGarten | Girls | Najran | Najran | 17°36'19.1"N 43°45'20.9"E | SXE2020627018227 | 10084661061 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 64 | SS-ZAM-NJR1064 | صهيب بن سنان الثانوية | Suhaib Bin Sinan High School | Secondary | Boys | Najran | Najran | 17.669815023526564, 43.766224713491454 | HLY2020627044530 | 10052527897 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 65 | SS-ZAM-NJR1065 | هدادة الابتدائية بنين | Haddada Primary School for Boys | Primary | Boys | Najran | Najran | 17.605060371849444, 43.756467213491455 | HLY2020627044527 | 10052614849 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 66 | SS-ZAM-NJR1066 | زيد بن الخطاب بعاكفة المتوسطة بنين | Zaid bin Al-Khattab Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17.60818708880408, 43.76154699814675 | SXE2120627103359 | 10052937723 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 67 | SS-ZAM-NJR1067 | عاكفة الابتدائية بنات | Akifa Primary School for Girls | Primary | Girls | Najran | Najran | 17.60845222227498, 43.7610282883618 | SXE2120627095472 | 10052858531 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 68 | SS-ZAM-NJR1068 | الرويكه الابتدائية بنين | Al-Ruwaika Primary School for Boys | Primary | Boys | Najran | Najran | 17.497863066964545, 43.74761962698291 | HLY2020627049357 | 10053090735 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 69 | SS-ZAM-NJR1069 | الواحد والعشرون المتوسطة بنات | Twenty-one Intermediate Girls | Intermediate | Girls | Najran | Najran | 17.48537571236985, 43.75675301349147 | HLY2020627047215 | 10052776829 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 70 | SS-ZAM-NJR1070 | الروضه الثانيه والعشرون بنات | The twenty-second kindergarten for girls | KinderGarten | Girls | Najran | Najran | 17.558387743752597, 44.45695910384853 | SXE2020627043518 | 10084466998 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 71 | SS-ZAM-NJR1071 | الروضة الثالثة والعشرون | The twenty-third kindergarten | KinderGarten | Girls | Najran | Najran | 17°31'46.1"N 44°33'59.7"E | HLY2020627018175 | 10085615921 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 72 | SS-ZAM-NJR1072 | مدرسة ريمان الابتدائية بنين | Riman Elementary School for Boys | Primary | Boys | Najran | Najran | 17.5870125241696, 44.489420440474376 | SXE2120627091023 | 10052971421 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 73 | SS-ZAM-NJR1073 | الغزالي الثانوية بنين | Al-Ghazali Secondary School for Boys | Secondary | Boys | Najran | Najran | 17.75703279207404, 44.46469105767236 | ALH2020807393935 | 30130650039 |  | 2026-04-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 74 | SS-ZAM-NJR1074 | الثالثة الابتدائية | Third grade | Primary | Girls | Najran | Najran | 17.544559501818735, 44.38687211534472 | HLY2020627042655 | 10052780189 |  | Saturday 9 May 2026 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 75 | SS-ZAM-NJR1075 | مدرسة اسماء بنت الحارث للطفولة المبكرة | Asma Bint Al-Harith School for Early Childhood | Early Childhood | Girls | Najran | Najran | 17°29'50"N 44°13'11"E | HLY2020627042674 | 10052932629 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 76 | SS-ZAM-NJR1076 | الروضة الحاديه عشره | Eleventh Kindergarten | KinderGarten | Girls | Najran | Najran | 17°29'40.6"N 44°08'58.8"E | HLY2020627042683 | 10083318506 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 77 | SS-ZAM-NJR1077 | المدرسة الاولى المتوسطة بنات | First Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17°34'11.2"N 44°13'46.1"E | HLY2020627042702 | 10052743031 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 78 | SS-ZAM-NJR1078 | مدرسة موسى بن نصير الابتدائية | Musa Bin Nusair Elementary School | Primary | Boys | Najran | Najran | 17°33'28.0"N 44°12'59.4"E | HLY2020627042720 | 10052854569 |  | 2026-02-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 15 | Completed
| 79 | SS-ZAM-NJR1079 | الروضة التاسعة عشر | The nineteenth kindergarten | KinderGarten | Girls | Najran | Najran | 17°32'53.3"N 44°13'18.1"E | HLY2020627042721 | 10052571269 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 80 | SS-ZAM-NJR1080 | الروضة السادسة عشر | Sixteenth Kindergarten | KinderGarten | Girls | Najran | Najran | 17°33'53.4"N 44°13'02.8"E | HLY2020627042726 | 10052606810 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 81 | SS-ZAM-NJR1081 | زيد بن الحارثة الابتدائية بنين | Zaid bin Haritha Elementary School for Boys | Primary | Boys | Najran | Najran | 17°29'26"N 44°06'08"E | HLY2020627042733 | 10052570440 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 82 | SS-ZAM-NJR1082 | الابتدائية الثانية بالمشعلية بنات | Second Elementary School for Girls in Al-Mash'aliyah | Primary | Girls | Najran | Najran | 17°31'04.5"N 44°09'17.8"E | HLY2020627044426 | 10053047331 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 83 | SS-ZAM-NJR1083 | حسان بن ثابت الابتدائية | Hassan Bin Thabit Elementary School | Primary | Boys | Najran | Najran | 17°43'25.2"N 43°54'17.5"E | HLY2020627044500 | 10052847448 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 84 | SS-ZAM-NJR1084 | الحرشف الابتدائية بنين | Al-Harshaf Primary School for Boys | Primary | Boys | Najran | Najran | 17.756469810343233, 44.463850913491456 | HLY2020627044509 | 10052526961 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 85 | SS-ZAM-NJR1085 | المدرسة الحادية عشر الثانوية بنات | Eleventh Girls' High School | Secondary | Girls | Najran | Najran | 17.81511227190264, 44.001823840433495 | HLY2020627047136 | 10052966396 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 86 | SS-ZAM-NJR1086 | الرابعة والعشرون الابتدائية بنات | Twenty-fourth Elementary School for Girls | Primary | Girls | Najran | Najran | 17°40'13.5"N 43°53'07.0"E | HLY2020627047213 | 10052810116 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 87 | SS-ZAM-NJR1087 | الثالثة عشر المتوسطة بنات | Thirteenth Intermediate Girls | Intermediate | Girls | Najran | Najran | 17.567489856215204, 44.3195123197357 | HLY2020627047242 | 10052741055 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 88 | SS-ZAM-NJR1088 | حطين المتوسطة بنين | Hittin Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°32'08.5"N 44°13'03.2"E | HLY2020627047243 | 10053094350 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 89 | SS-ZAM-NJR1089 | ابتدائية شرق الحمر بنين | East Al-Hamr Boys' Primary School | Primary | Boys | Najran | Najran | 17°35'06.0"N 44°29'09.7"E | HLY2020627047244 | 10052805591 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 90 | SS-ZAM-NJR1090 | السابعة للطفولة المبكرة | Seventh for early childhood | Early Childhood | Girls | Najran | Najran | 17°28'14"N 44°09'27"E | HLY2020627048199 | 10052487209 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 91 | SS-ZAM-NJR1091 | معاذ بن جبل الابتدائية بنين | Mu'adh ibn Jabal Elementary School for Boys | Primary | Boys | Najran | Najran | 17°28'19"N 44°11'06"E | HLY2020627048214 | 10052741986 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 92 | SS-ZAM-NJR1092 | عمر بن الخطاب الابتدائية بنين | Omar Ibn Al-Khattab Elementary School for Boys | Primary | Boys | Najran | Najran | 17°32'07.3"N 44°12'18.8"E | HLY2020627048256 | 10053049121 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 93 | SS-ZAM-NJR1093 | ابن حزم الثانوية بنين | Ibn Hazm Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°31'51"N 44°12'17"E | HLY2020627048276 | 10052740227 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 94 | SS-ZAM-NJR1094 | مدرسة الخليف الابتدائية بنين | Al-Khalif Primary School for Boys | Primary | Boys | Najran | Najran | 17°31'08"N 44°09'36"E | HLY2020627049352 | 10052701096 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 95 | SS-ZAM-NJR1095 | ثانوية الملك عبدالعزيز بنين | King Abdulaziz Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°31'04"N 44°09'37"E | HLY2020627049423 | 10053009401 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 96 | SS-ZAM-NJR1096 | طارق بن زياد الابتدائية | Tariq Bin Ziyad Elementary School | Primary | Boys | Najran | Najran | 17.533618930285105, 44.40325052392379 | HLY2020627049433 | 10052606506 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 97 | SS-ZAM-NJR1097 | المدرسة الثانوية الثالثة بنات | Third Girls' High School | Secondary | Girls | Najran | Najran | 17°34'10"N 44°13'22"E | HLY2020627049443 | 10052925938 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 98 | SS-ZAM-NJR1098 | المدرسة الثامنة للطفولة المبكره بنات | Eighth Early Childhood School for Girls | Early Childhood | Girls | Najran | Najran | 17°28'13"N 44°09'31"E | HLY2020627049444 | 10052574636 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 99 | SS-ZAM-NJR1099 | الروضة الثالثة والثلاثون | The thirty-third kindergarten | KinderGarten | Girls | Najran | Najran | 17°34'41.0"N 44°13'36.3"E | HLY2020627049449 | 10052929070 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 100 | SS-ZAM-NJR1100 | الابتدائية الرابعة عشر للطفولة المبكرة | The Fourteenth Elementary School for Early Childhood | Primary | Girls | Najran | Najran | 17°34'18.2"N 44°13'49.7"E | HLY2020627049461 | 10052574313 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 101 | SS-ZAM-NJR1101 | المدرسة الثانية عشر المتوسطة بنات | Twelfth Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17°34'40.5"N 44°13'38.1"E | HLY2020627049476 | 10052929356 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 102 | SS-ZAM-NJR1102 | ابتدائية فاطمة الزهراء للطفولة المبكرة | Fatima Al-Zahra Primary School for Early Childhood | Primary | Girls | Najran | Najran | 17°32'08.2"N 44°13'03.4"E | HLY2020627049487 | 10052452099 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 103 | SS-ZAM-NJR1103 | المدرسة الثانية عشر الثانوية بنات | Twelfth Girls' High School | Secondary | Girls | Najran | Najran | 17°33'23.6"N 44°13'47.0"E | HLY2020627049496 | 10052929202 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 104 | SS-ZAM-NJR1104 | ابتدائية المغيره بن شعبة الابتدائية وبرنامج ضعاف السمع | Al-Mughirah Bin Shu'bah Primary School and the Hearing Impaired Program | Primary | Boys | Najran | Najran | 17°33'47.2"N 44°13'14.1"E | HLY2020627049499 | 10052851665 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 105 | SS-ZAM-NJR1105 | الضيقة الثانوية بنات | Al-Nadiqa Secondary Girls | Secondary | Girls | Najran | Najran | 17°33'23.6"N 44°13'47.0"E | HLY2020627049576 | 10053045300 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 106 | SS-ZAM-NJR1106 | مدرسة قراء الابتدائية بنين | Quraa Primary School for Boys | Primary | Boys | Najran | Najran | 17°33'10.5"N 44°14'22.3"E | HLY2020627049608 | 10052893281 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 107 | SS-ZAM-NJR1107 | الروضة السابعه بالمنتشر / مدرسة حبيبة الانصارية | Seventh Kindergarten in Al Muntashir / Habiba Al Ansariyah School | KinderGarten | Girls | Najran | Najran | 17.844406280802573, 44.27098647433125 | HLY2020627049636 | 10053007327 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 108 | SS-ZAM-NJR1108 | رجلاء الابتدائية بنين | Rajlaa Primary School for Boys | Primary | Boys | Najran | Najran | 17.8129089119017, 44.29693155767236 | HLY2020627050269 | 10053050195 |  | 2026-04-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 109 | SS-ZAM-NJR1109 | ابتدائية الحمر للطفولة المبكرة | Al-Hamr Primary School for Early Childhood | Primary | Girls | Najran | Najran | 17.884163513553244, 44.177590226982915 | HLY2020627050366 | 10053092284 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 110 | SS-ZAM-NJR1110 | نهاوند المتوسطه بنين | Nahawand Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°29'51"N 44°13'15"E | HLY2020627050367 | 10052448837 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 111 | SS-ZAM-NJR1111 | القابل الثانوية بنات | Al-Qabil Secondary Girls | Secondary | Girls | Najran | Najran | 17°28'26.5"N 44°11'02.7"E | HLY2020627050368 | 10052485026 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 112 | SS-ZAM-NJR1112 | الروضة الثانية عشرة بنات | Twelfth Kindergarten for Girls | KinderGarten | Girls | Najran | Najran | 17°29'49.2"N 44°13'15.5"E | HLY2020627050893 | 10082475817 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 113 | SS-ZAM-NJR1113 | الاولى للطفولة المبكره | First for early childhood | Early Childhood | Girls | Najran | Najran | 17°29'30"N 44°11'04"E | HLY2020627050954 | 10053093675 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 114 | SS-ZAM-NJR1114 | ثانوية الملك فهد بنين | King Fahd Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°34'09.0"N 44°13'45.7"E | HLY2020627051020 | 10052892695 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 115 | SS-ZAM-NJR1115 | مدرسة ابن كثير الابتدائية لتحفيظ القران الكريم | Ibn Kathir Primary School for Memorizing the Holy Quran | Primary | Boys | Najran | Najran | 17°29'04.2"N 44°07'29.3"E | HLY2020627051027 | 10052606195 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 116 | SS-ZAM-NJR1116 | ابن تيمية المتوسطه بنين | Ibn Taymiyyah Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°32'28.9"N 44°12'53.1"E | HLY2020627051036 | 10052528114 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 117 | SS-ZAM-NJR1117 | نجران الثانوية بنين | Najran Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°32'30.5"N 44°12'55.1"E | HLY2020627051037 | 10052892111 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 118 | SS-ZAM-NJR1118 | خالد بن الوليد الابتدائية بنين | Khalid Bin Al-Walid Elementary School for Boys | Primary | Boys | Najran | Najran | 17°31'34"N 44°11'49"E | HLY2020627051040 | 10052737830 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 119 | SS-ZAM-NJR1119 | مدرسة القدس الابتدائية وبرنامج دمج المكفوفين | Jerusalem Elementary School and the Blind Integration Program | Primary | Boys | Najran | Najran | 17°31'26"N 44°11'49"E | HLY2020627051054 | 10052741832 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 120 | SS-ZAM-NJR1120 | المدرسة التاسعة والثلاثون للطفولة المبركة | The thirty-ninth school for blessed childhood | Early Childhood | Girls | Najran | Najran | 17°31'31"N 44°11'44"E | HLY2020627051066 | 10052849630 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 121 | SS-ZAM-NJR1121 | مدرسة احد المتوسطة وبرنامج التربية الفكرية | Uhud Intermediate School and the Intellectual Education Program | Intermediate | Boys | Najran | Najran | 17°32'26.5"N 44°12'46.7"E | HLY2020627051072 | 10052493331 |  | 2026-04-25 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 122 | SS-ZAM-NJR1122 | الروضة الاولى بنات | First Kindergarten for Girls | KinderGarten | Girls | Najran | Najran | 17°33'29.1"N 44°13'14.9"E | HLY2020627051073 | 10052574799 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 123 | SS-ZAM-NJR1123 | مدرسة متوسطة الاندلس بنين | Al-Andalus Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°34'35.4"N 44°13'51.1"E | HLY2020627051110 | 10052886240 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 124 | SS-ZAM-NJR1124 | حفصة السديري للطفولة المبكرة بنات | Hafsa Al-Sudairi for Early Childhood Girls | Early Childhood | Girls | Najran | Najran | 17°34'22.8"N 44°13'51.9"E | HLY2020627051114 | 10052854424 |  | 2026-04-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 125 | SS-ZAM-NJR1125 | احمد بن حنبل الابتدائية وبرنامج التربيه الفكرية | Ahmad Ibn Hanbal Elementary School and the Intellectual Education Program | Primary | Boys | Najran | Najran | 17°31'47.8"N 44°11'55.7"E | HLY2020627051145 | 10052606041 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 126 | SS-ZAM-NJR1126 | ابتدائيه الملك عبدالله | King Abdullah Elementary School | Primary | Boys | Najran | Najran | 17°33'52"N 44°12'59"E | HLY2020627051473 | 10052374143 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 127 | SS-ZAM-NJR1127 | الشيخ محمد بن عبدالوهاب الابتدائية بنين | Sheikh Muhammad bin Abdul Wahhab Elementary School for Boys | Primary | Boys | Najran | Najran | 17°32'44"N 44°13'22"E | HLY2020627051485 | 10052697832 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 128 | SS-ZAM-NJR1128 | ابتدائيه بئر عسكر للطفوله المبكره | Bir Askar Primary School for Early Childhood | Primary | Boys | Najran | Najran | 17°32'29"N 44°13'54"E | HLY2020627051506 | 10052743336 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 129 | SS-ZAM-NJR1129 | مدرسة طيبة المتوسطة بنين | Tayba Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17.58250316573724, 44.48398598406019 | HLY2020627051911 | 10053012505 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 130 | SS-ZAM-NJR1130 | الجربة الابتدائية بنات | Al-Jarba Primary School for Girls | Primary | Girls | Najran | Najran | 17°32'05.5"N 44°11'33.8"E | HLY2020627051927 | 10053046531 |  | 2026-04-01 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 131 | SS-ZAM-NJR1131 | متوسطة مسلمة بن عبدالملك | Muslimah Bin Abdulmalik Intermediate School | Intermediate | Boys | Najran | Najran | 17°34'27.3"N 44°02'20.3"E | HLY2020627051960 | 10052528750 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 132 | SS-ZAM-NJR1132 | المدرسة السابعة المتوسطة بنات | Seventh Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17°28'40"N 44°10'28"E | HLY2020627051972 | 10052735700 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 133 | SS-ZAM-NJR1133 | مدرسة عموريه المتوسطة | Ammourieh Intermediate School | Intermediate | Boys | Najran | Najran | 17°27'42"N 44°09'43"E | HLY2020627051975 | 10052493181 |  | 2026-04-27 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 134 | SS-ZAM-NJR1134 | رجلاء الابتدائية بنات | Rajlaa Elementary Girls | Primary | Girls | Najran | Najran | 17°29'14.6"N 44°11'30.0"E | HLY2020627051985 | 10052448102 |  | 2026-04-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 135 | SS-ZAM-NJR1135 | الابتدائية العاشرة بنات | Tenth Girls' Elementary School | Primary | Girls | Najran | Najran | 17°34'04"N 44°13'35"E | HLY2020627052000 | 10052741959 |  | 2026-04-27 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 136 | SS-ZAM-NJR1136 | ابي الدرداء المتوسطة بنين | Abi Al-Darda Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°33'44.6"N 44°13'28.1"E | HLY2020627052025 | 10052735666 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 137 | SS-ZAM-NJR1137 | السعودية للطفولة المبكرة | Saudi Arabia for Early Childhood | Early Childhood | Girls | Najran | Najran | 17°29'40.5"N 44°12'50.8" | HLY2020627052029 | 10052891974 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 138 | SS-ZAM-NJR1138 | المدرسة السادسة عشر الثانوية بنات | Sixteenth Girls' High School | Secondary | Girls | Najran | Najran | 17°34'03.4"N 44°13'03.5"E | HLY2020627052032 | 10084971467 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 139 | SS-ZAM-NJR1139 | الروضة الثانية بالجربة | The second kindergarten in Al-Jarba | KinderGarten | Girls | Najran | Najran | 17.528263751595215, 44.32587407306151 | HLY2020627052038 | 10053054381 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 140 | SS-ZAM-NJR1140 | جواهر بنت عبدالعزيز للطفولة المبكرة | Jawahir Bint Abdulaziz for Early Childhood | Early Childhood | Girls | Najran | Najran | 17°29'32.3"N 44°08'07.3"E | HLY2020627052043 | 10052740076 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 141 | SS-ZAM-NJR1141 | شعب رير الابتدائية بنات | Reer Elementary School for Girls | Primary | Girls | Najran | Najran | 17°33'52.9"N 44°13'26.0"E | SMR2220621011146 | 10052572551 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 142 | SS-ZAM-NJR1142 | متوسطة ابي بن كعب لتحفيظ القران الكريم | Abi Bin Kaab Intermediate School for Memorizing the Holy Quran | Intermediate | Boys | Najran | Najran | 17°27'43.9"N 44°09'41.4"E | SMR2320621019001 | 10052779901 |  | 2026-04-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 143 | SS-ZAM-NJR1143 | الجوهرة بنت مساعد للطفولة المبكرة | Al-Jawhara Bint Musaed for Early Childhood | Early Childhood | Girls | Najran | Najran | 17°34'12.0"N 44°13'35.3"E | SMR2320621019136 | 10052742393 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 144 | SS-ZAM-NJR1144 | ثانوية ابن خلدون | Ibn Khaldoun High School | Secondary | Boys | Najran | Najran | 17°27'55.7"N 44°10'03.8"E | SMR2320621019146 | 10052695364 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 145 | SS-ZAM-NJR1145 | المتوسطة الثامنة عشر بنات | Eighteenth Intermediate Girls | Intermediate | Girls | Najran | Najran | 17°29'02.0"N 44°07'45.2"E | SMR2320621019148 | 10052776856 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 146 | SS-ZAM-NJR1146 | المدرسة الثانوية الثانية | Second High School | Secondary | Girls | Najran | Najran | 17°32'54.9"N 44°15'17.6"E | SMR2320621019150 | 10095226229 |  | 2026-04-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 147 | SS-ZAM-NJR1147 | عثمان بن عفان الابتدائية | Uthman ibn Affan Elementary School | Primary | Boys | Najran | Najran | 17°29'06"N 44°07'47"E | SXE2020627015559 | 10052611829 |  | 2026-04-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 148 | SS-ZAM-NJR1148 | الامام البخاري الابتدائية | Imam Bukhari Elementary School | Primary | Boys | Najran | Najran | 17°33'27.9"N 44°13'10.3"E | SXE2020627015571 | 10052736707 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 149 | SS-ZAM-NJR1149 | القابل المتوسطة بنات | Intermediate Girls | Intermediate | Girls | Najran | Najran | 17°33'25.2"N 44°13'42.0"E | SXE2020627015572 | 10052928582 |  |  | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 150 | SS-ZAM-NJR1150 | الحسن بن هيثم المتوسطة | Al-Hassan Ibn Al-Haytham Intermediate School | Intermediate | Boys | Najran | Najran | 17°28'55"N 44°07'16"E | SXE2020627015676 | 10052784802 |  | 2026-04-25 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 151 | SS-ZAM-NJR1151 | الابتدائية الثانية للطفولة المبكرة | Second Primary School for Early Childhood | Primary | Girls | Najran | Najran | 17°29'25.1"N 44°10'53.6"E | SXE2020627016221 | 10052702558 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 152 | SS-ZAM-NJR1152 | هجرة بن حجاب الابتدائية بنات | Hijra Bin Hijab Primary School for Girls | Primary | Girls | Najran | Najran | 17°29'30.0"N 44°11'04.3"E | SXE2020627018158 | 10052783654 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 153 | SS-ZAM-NJR1153 | هلال بن أمية المتوسطة بنين (الضيقة المتوسطة سابقا) | Hilal Bin Umayya Intermediate School for Boys (formerly Al-Dhayqa Intermediate School) | Intermediate | Boys | Najran | Najran | 17°32'20.8"N 44°13'10.1"E | SXE2020627018159 | 10052526586 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 154 | SS-ZAM-NJR1154 | علي بن ابي طالب الابتدائية بنين | Ali Bin Abi Talib Elementary School for Boys | Primary | Boys | Najran | Najran | 17°31'47.0"N 44°11'55.7"E | SXE2020627018163 | 10052534659 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 155 | SS-ZAM-NJR1155 | ابن سينا المتوسطة بنين | Ibn Sina Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17.85552301684753, 44.24429835405135 | SXE2020627018168 | 10052568460 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 156 | SS-ZAM-NJR1156 | الحضن المتوسطة بنات | The middle school girls' hug | Intermediate | Girls | Najran | Najran | 17.842348662790226, 44.28283565767236 | SXE2020627018186 | 10052738452 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 157 | SS-ZAM-NJR1157 | مدرسة متوسطة المشعلية بنات | Al-Mash'aliyah Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17°27'22.0"N 44°06'55.9"E | SXE2020627018196 | 10052741609 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 158 | SS-ZAM-NJR1158 | مدرسة المشعلية الثانوية بنات | Al-Mash'aliyah Secondary School for Girls | Secondary | Girls | Najran | Najran | 17°27'24.8"N 44°06'59.9"E | SXE2020627041063 | 10052741734 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 159 | SS-ZAM-NJR1159 | مدرسة النواس بن سمعان الابتدائية بنين | Al-Nawas Bin Sam'an Elementary School for Boys | Primary | Boys | Najran | Najran | 17°27'22.2"N 44°07'31.6"E | SXE2020627041097 | 10053088291 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 160 | SS-ZAM-NJR1160 | الشيخ محمد بن صالح بن عثيمين الثانوية | Sheikh Muhammad bin Saleh bin Uthaymeen High School | Secondary | Boys | Najran | Najran | 17.764574854072283, 44.46076565767236 | SXE2120627090920 | 10052605044 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 161 | SS-ZAM-NJR1161 | الرويكبة للطفوله المبكره | Al-Ruwaikiba for Early Childhood | Early Childhood | Girls | Najran | Najran | 17.764559519534053, 44.46108625581909 | SXE2120627106470 | 10090637698 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 162 | SS-ZAM-NJR1162 | الاخدود الابتدائية بنات | Al-Akhdoud Primary School for Girls | Primary | Girls | Najran | Najran | 17.76227055677093, 44.46638361349146 | SXE2120627106472 | 10052784938 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 163 | SS-ZAM-NJR1163 | اليرموك الثانويه بنين | Yarmouk Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°28'12.0"N 44°09'27.4"E | SXE2120627106562 | 10052808941 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 164 | SS-ZAM-NJR1164 | مدرسة شرق رجلاء الابتدائية الطفولة المبكرة | East Rajlaa Primary School Early Childhood | Primary | Girls | Najran | Najran | 17.565546370488285, 44.45222623696156 | SXE2120627112970 | 10053010654 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 165 | SS-ZAM-NJR1165 | القادسية المتوسطة بنين | Al-Qadisiyah Intermediate School for Boys | Intermediate | Boys | Najran | Najran | 17°28'36.3"N 44°10'28.3"E | SMR2420628011623 | 10052741681 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 166 | SS-ZAM-NJR1166 | الروضة السابعة عشر | Seventeenth Kindergarten | KinderGarten | Girls | Najran | Najran | 17.562168404175043, 44.357263992092236 | HLY2020627042632 | 10052741430 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 167 | SS-ZAM-NJR1167 | مجمع الكنتوب روضة | Al-Kuntub Kindergarten Complex | KinderGarten | Girls | Najran | Najran | 17°29'04.2"N 44°14'59.9"E | HLY2020627051104 | 10052611088 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 168 | SS-ZAM-NJR1168 | المدرسة الثانية المتوسطة | Second Intermediate School | Intermediate | Girls | Najran | Najran | 17°29'20"N 44°06'09"E | SXE2020627015543 | 10053087838 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 169 | SS-ZAM-NJR1169 | الروضه الاولى بالجربه | The first kindergarten in Al-Jarba | KinderGarten | Girls | Najran | Najran | 17°29'26"N 44°06'08"E | HLY2020627049474 | 10052780797 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 170 | SS-ZAM-NJR1170 | ثانوية الجربه بنات | Al-Jarba Girls' Secondary School | Secondary | Girls | Najran | Najran | 17°31'34.9"N 44°12'32.9"E | HLY2020627051928 | 10053046639 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 171 | SS-ZAM-NJR1171 | ثانوية الصويقطة بنات | Al-Suwaiqah Girls' Secondary School | Secondary | Girls | Najran | Najran | 17°29'06.0"N 44°07'32.0"E | HLY2020627051922 | 10053054514 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 172 | SS-ZAM-NJR1172 | المتوسطة العشرون | Twentieth Intermediate | Intermediate | Girls | Najran | Najran | 17°27'42"N 44°09'43"E | HLY2020627047246 | 10090193528 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 173 | SS-ZAM-NJR1173 | شيخه بنت عبدالعزيز للطفولة المبكرة | Sheikha Bint Abdulaziz for Early Childhood | Early Childhood | Girls | Najran | Najran | 17°27'43.9"N 44°09'41.4"E | SXE2020627012809 | 10052489590 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 174 | SS-ZAM-NJR1174 | المدرسة الثانوية الثالثة عشر | Thirteenth High School | Secondary | Girls | Najran | Najran | 17°28'24"N 44°11'01"E | HLY2020627051482 | 10052446888 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 175 | SS-ZAM-NJR1175 | الثانوية الثامنة مقررات بنات | Eighth Secondary School for Girls (Curriculum) | Secondary | Girls | Najran | Najran | 17°30'39.3"N 44°10'52.1"E | HLY2020627051474 | 10052965693 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 176 | SS-ZAM-NJR1176 | رجلاء الثانوية بنات | Girls' High School Men | Secondary | Girls | Najran | Najran | 17°31'52"N 44°11'27"E | SXE2020627043179 | 10052485661 |  | 2026-04-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 177 | SS-ZAM-NJR1177 | المدرسة المتوسطة الرابعة عشر | Fourteenth Intermediate School | Intermediate | Girls | Najran | Najran | 17°31'52"N 44°11'30"E | HLY2020627051996 | 10052853211 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 178 | SS-ZAM-NJR1178 | الثانوية الخامسة | Fifth Secondary | Secondary | Girls | Najran | Najran | 17°33'45.4"N 44°15'19.8"E | HLY2020627051115 | 10052485170 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 179 | SS-ZAM-NJR1179 | المتوسطة الاولى لتحفيظ القران الكريم | The First Intermediate School for Memorizing the Holy Quran | Intermediate | Girls | Najran | Najran | 17°29'42.0"N 44°12'50.6"E | HLY2020627049464 | 10052610090 |  | 2026-04-15 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 180 | SS-ZAM-NJR1180 | متوسطة الجزيرة | Al Jazeera Middle | Intermediate | Boys | Najran | Najran | 17°34'02.2"N 44°13'02.1"E | SXE2120627112912 | 10053047734 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 181 | SS-ZAM-NJR1181 | المتوسطة التاسعة عشر للبنات | Nineteenth Intermediate School for Girls | Intermediate | Girls | Najran | Najran | 17°32'46.7"N 44°13'21.6"E | HLY2020627051067 | 10052928742 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 182 | SS-ZAM-NJR1182 | الروضة السابعه والعشرون بنات | The twenty-seventh kindergarten for girls | KinderGarten | Girls | Najran | Najran | 17°32'55.0"N 44°13'17.5"E | HLY2020627052034 | 10053088058 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 183 | SS-ZAM-NJR1183 | ثانوية المغيره بن شعبه بنين | Al-Mughira Bin Shu’ba Secondary School for Boys | Secondary | Boys | Najran | Najran | 17°29'27.3"N 44°14'43.0"E | HLY2020627049500 | 10052851816 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 184 | SS-ZAM-NJR1184 | المتوسطة الثانية لتحفيظ القران الكريم | Second Intermediate School for Memorizing the Holy Quran | Intermediate | Girls | Najran | Najran | 17°33'27.9"N 44°13'10.3"E | HLY2020627042718 | 10052814133 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 185 | SS-ZAM-NJR1185 | متوسطة الملك عبدالله | King Abdullah Intermediate | Intermediate | Boys | Najran | Najran | 17°34'04.3"N 44°13'01.1"E | HLY2020627051472 | 10052374241 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 186 | SS-ZAM-NJR1186 | ابتدائيه الإمام ابي حنيفه | Imam Abu Hanifa Elementary School | Primary | Boys | Najran | Najran | 17°33'56.0"N 44°13'24.4"E | SXE2120627106563 | 10052453864 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 187 | SS-ZAM-NJR1187 | الشيخ عبد العزيز بن باز المتوسطه | Sheikh Abdul Aziz bin Baz Intermediate School | Intermediate | Boys | Najran | Najran | 17°33'12.1"N 44°14'22.3"E | SMR2220621011119 | 10052494339 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 188 | SS-ZAM-NJR1188 | المنتشر الابتدائية بنين | Al-Muntasher Primary School for Boys | Primary | Boys | Najran | Najran | 17°32'54.5"N 44°13'17.2"E | HLY2020627049566 | 10052526853 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 189 | SS-ZAM-NJR1189 | متوسطة الخانق بنات | Al-Khanq Intermediate Girls | Intermediate | Girls | Najran | Najran | 17.58250316573724, 44.48398598406019 | HLY2020627044462 | 10052491524 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 190 | SS-ZAM-NJR1190 | الثانوية العشرون | 20th High School | Secondary | Girls | Najran | Najran | 17.560622414213576, 44.35697960927854 | HLY2020627051990 | 10052739164 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 191 | SS-ZAM-NJR1191 | مدرسة الملك فيصل الابتدائية | King Faisal Elementary School | Primary | Boys | Najran | Najran | 17.559668977894678, 44.45702596368954 | SXE2020627015558 | 10052854756 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 192 | SS-ZAM-NJR1192 | مدرسة الزبير بن العوام المتوسطة | Al-Zubair Ibn Al-Awam Intermediate School | Intermediate | Boys | Najran | Najran | 17.87646839002829, 44.16200067301708 | HLY2020627042602 | 10052528491 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 193 | SS-ZAM-NJR1193 | مدرسة انس بن مالك الابتدائية | Anas Ibn Malik Elementary School | Primary | Boys | Najran | Najran | 17.732523491578256, 43.75852035581908 | HLY2020627051063 | 10052775939 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 194 | SS-ZAM-NJR1194 | مدرسة المعتصم الابتدائية | Al-Mu'tasim Elementary School | Primary | Boys | Najran | Najran | 17°29'03.2"N 44°15'01.5"E | HLY2020627042724 | 10052605911 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 195 | SS-ZAM-NJR1195 | مدرسة محمد بن القاسم الابتدائية | Muhammad Ibn Al-Qasim Elementary School | Primary | Boys | Najran | Najran | 17.457188268855216, 44.11027381483723 | HLY2020627042634 | 10053049238 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 196 | SS-ZAM-NJR1196 | ابتدائية ومتوسطة بدر الجنوب | Badr Al-Janoub Elementary and Intermediate School | Intermediate | Girls | Najran | Najran | 17.8790611048747, 43.71716257487458 | HLY2020627049649 | 10052809536 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 197 | SS-ZAM-NJR1197 | مدرسة الفارابي الثانوية | Al-Farabi Secondary School | Secondary | Boys | Najran | Najran | 17.45667482960641, 44.11804944241546 | SXE2020627018166 | 10052737929 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| 198 | SS-ZAM-NJR1198 | توبان الابتدائية بنين | Thawban Elementary School for Boys | Primary | Boys | Najran | Najran | 17.628578087743843, 44.474731299999995 | HLY2020627051984 | 1088707051 |  | 2026-04-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 199 | SS-ZAM-NJR1199 | اميمة بنت الحارث للطفولة المبكرة | Ummaymah Bint Al- Harith for Early Childhood | Early Childhood | Girls | Najran | Najran |  | HLY2020627046723 | 10103123751 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| 200 | SS-ZAM-NJR1200 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
Total | [11 empty] | Total | Completed | 71 | 71 | 71 | 71 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 19.6667
[13 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Not Started | 129 | 129 | 129 | 129 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199
Note on M4: 4/2/2025
Note on N4: 4/2/2025
Note on N22: 4/2/2025
Note on N81: 4/2/2025
Note on N136: 4/2/2025

## Jazan Schools -1
| Report Date | 2026-05-10
Project | Schools Information | [10 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level | School Gender (Boys / Girls) | Region | City | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Jazan-1 | SS-ZAM-JAZ1001 | متوسطة الشيخ ابن باز | Sheikh Ibn Baz Intermediate School | Intermediate | Boys | Jazan | Jazan | 16°57'34.5"N 42°50'16.9"E | HLY2020627040036 | 10052664288 |  | 2026-04-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Primary | Boys | Not Started
| SS-ZAM-JAZ1002 | ابتدائية الفاروق | Al-Farouq Primary School | Primary | Boys | Jazan | Jazan | 16.963276080801855, 42.830122240074836 | SXE2120627097783 | 10093334011 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Intermediate | Girls | In Progress
| SS-ZAM-JAZ1003 | ابتدائية زيد بن الخطاب | Zaid Bin Al-Khattab Elementary School | Primary | Boys | Jazan | Jazan | 16.968889161325276, 42.8181238175016 | SXE2120627106659 | 10103302279 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Secondary | NA | Completed
| SS-ZAM-JAZ1004 | ابتدائية الحسن بن الهيثم | Al-Hassan Ibn Al-Haytham Elementary School | Primary | Boys | Jazan | Jazan | 16.969862951868087, 42.823870078845026 | SMR2320621019322 | 10053066005 |  | 2026-04-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | Early Childhood |  | NA
| SS-ZAM-JAZ1005 | الروضة الثانية بأبو عريش | The second kindergarten in Abu Arish | KinderGarten | Girls | Jazan | Jazan | 16.97062165629924, 42.83634174417771 | HLY2020627000587 | 10052504373 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | KinderGarten
| SS-ZAM-JAZ1006 | روضة حسناء بنت معاوية بأبو عريش | Rawda Hasnaa Bint Muawiya in Abu Arish | KinderGarten | Girls | Jazan | Jazan | 16.95768920830115, 42.83256802479369 | HLY2020627010412 | 10086279724 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress | NA
| SS-ZAM-JAZ1007 | الابتدائية الخامسة بأبو عريش | Fifth Elementary School in Abu Arish | Primary | Girls | Jazan | Jazan | 16.95778127115714, 42.832999732459136 | HLY2020627011616 | 10086280421 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1008 | المتوسطة الرابعة بأبو عريش | Fourth Intermediate School in Abu Arish | Intermediate | Girls | Jazan | Jazan | 16.957627785924853, 42.8334138 | HLY2020627011617 | 10086285196 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1009 | ثانوية محمد سالم العطاس | Mohammed Salem Al-Attas High School | Secondary | Boys | Jazan | Jazan | 16°58'28"N 42°50'51"E | SXE2120627107035 | 10052700221 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1010 | ابتدائية أسماء بنت الحارث بأبو عريش | Asma Bint Al-Harith Elementary School in Abu Arish | Primary | Girls | Jazan | Jazan | 16°58'28.6"N 42°50'41.9"E | SXE2120627106988 | 10102374424 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1011 | ابتدائية تحفيظ القران الكريم بأبي عريش | Primary School for Memorizing the Holy Quran in Abu Arish | Primary | Girls | Jazan | Jazan | 16.974251383986015, 42.83288656269455 | SXE2120627106653 | 10052868045 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1012 | متوسطة عقبه بن نافع | Aqaba Bin Nafeh Intermediate School | Intermediate | Boys | Jazan | Jazan | 16.966761855623282, 42.83614311899491 | SXE2120627106998 | 10091627598 |  | 2026-04-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1013 | ابتدائية الإمام مسلم بأبي عريش | Imam Muslim Primary School in Abu Arish | Primary | Boys | Jazan | Jazan | 16.97511682018834, 42.847448269310554 | SXE2120627107033 | 10052700375 |  | 2026-04-08 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1014 | متوسطة حاكمة أبوعريش | Abu Arish Intermediate School | Intermediate | Boys | Jazan | Jazan | 17.006131029737695, 42.83644619840216 | SMR2320621014866 | 10106328303 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1015 | ابتدائية رديس | Redis Primary School | Primary | Boys | Jazan | Jazan | 17.05641898652797, 42.78366228124587 | SXE2120627100743 | 10052610401 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1016 | ثانوية حاكمة أبي عريش - مسارات | Abu Arish High School - Pathways | Secondary | Boys | Jazan | Jazan | 17.00460746288444, 42.830342066754724 | SXE2120627107023 | 10052664134 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1017 | الابتدائية الأولى بالبديع والقرفي | The First Elementary School in Al-Badi' and Al-Qurfi | Primary | Girls | Jazan | Jazan | 16.997283396305757, 42.77936471925454 | SXE2120627107049 | 10052715663 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1018 | ابتدائية عبدالله بن مسعود | Abdullah bin Masoud Elementary School | Primary | Boys | Jazan | Jazan | 16°59'36.3"N 42°46'27.6"E | SXE2120627107113 | 10052834557 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1019 | ابتدائية الملك عبد العزيز بالمحلة والواسط | King Abdul Aziz Elementary School in Al-Mahalla and Al-Wasit | Primary | Boys | Jazan | Jazan | 17.042082189616675, 42.75748071767517 | HLY2020627002257 | 10053029718 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1020 | ابتدائية محلة ضمد | Mahalla Damad Elementary School | Primary | Boys | Jazan | Jazan | 17.044868168401106, 42.76000007301708 | SXE2120627096732 | 10052569691 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1021 | روضة محلة ضمد | Rawda Mahalla Damad | KinderGarten | Girls | Jazan | Jazan | 17.04017982291694, 42.76037703043037 | SXE2120627096733 | 10052909166 |  | 2026-04-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1022 | روضة خضيرة ضمد | Rawdat Khadira Damad | Early Childhood | Girls | Jazan | Jazan | 17.080740513460572, 42.749020090048006 | SXE2120627107085 | 10052624587 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1023 | مدرسة ثانوية خضيرة | Hadera High School | Secondary | Boys | Jazan | Jazan | 17°04'48.5"N 42°44'56.8"E | SXE2120627107086 | 10053068691 |  | 2026-04-11 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1024 | مدرسة المتوسطة بخضيرة ضمد | Khadera Intermediate School in Damad | Intermediate | Boys | Jazan | Jazan | 17°04'39.5"N 42°44'48.0"E | SXE2120627107087 | 10052971931 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1025 | متوسطة الظبية الاولى | Al-Dhabiya First Intermediate School | Intermediate | Girls | Jazan | Jazan | 17.11430607941305, 42.661367403287855 | SXE2120627097490 | 10052798281 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1026 | ثانوية صبيا الثانية | Sabya Secondary School | Secondary | Girls | Jazan | Jazan | 17.154344460007977, 42.6501683558191 | SXE2020627018060 | 10052461187 |  | 2026-04-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1027 | الابتدائية الثانية بضمد | Second Elementary School in Damad | Primary | Girls | Jazan | Jazan | 17°06'15.8"N 42°46'36.0"E | SEX2120627106771 | 10103198653 |  | 2026-05-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1028 | ثانوية ضمد الثانية | Damad Secondary School II | Secondary | Girls | Jazan | Jazan | 17°06'38.9"N 42°46'41.4"E | SXE2120627106705 | 10091847706 |  | 2026-04-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1029 | متوسطة ضمد الاولى | Damad First Intermediate School | Intermediate | Girls | Jazan | Jazan | 17.109998802448473, 42.780488743525936 | HLY2020627000473 | 10052694410 |  | 2026-04-13 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1030 | الابتدائية الاولى بضمد | The First Elementary School in Damad | Primary | Girls | Jazan | Jazan | 17°06'36.1"N 42°46'51.1"E | SXE2120627106680 | 10052359844 |  | 2026-04-13 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1031 | مدرسة عثمان بن عفان المتوسطة | Othman Bin Affan Intermediate School | Intermediate | Boys | Jazan | Jazan | 17.11361050622295, 42.77371599945647 | HLY2020627000598 | 10052715823 |  | 2026-04-15 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1032 | مدرسة ثانوية السليل | Al-Salil High School | Secondary | Girls | Jazan | Jazan | 17.130356619606985, 42.769546386508544 | SXE2120627106660 | 10096317794 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1033 | مدرسة الملك خالد الابتدائية بضمد | King Khalid Elementary School in Damad | Primary | Boys | Jazan | Jazan | 17°06'24.3"N 42°47'05.1"E | SXE2120627106772 | 10052580482 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1034 | الابتدائية الرابعة بضمد | Fourth Elementary School in Damad | Primary | Girls | Jazan | Jazan | 17.113052669151006, 42.77050929999771 | SXE2120627106774 | 10052700526 |  | 2026-05-09 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1035 | متوسطة القويعية | Al-Quway'iyah Intermediate School | Intermediate | Boys | Jazan | Jazan | 16.97493321888257, 42.7927063944747 | SXE2120627097616 | 10052971805 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1036 | متوسطة سـلامة الدراج | Safety of the Cyclist Intermediate School | Intermediate | Boys | Jazan | Jazan | 16.973326184148895, 42.75285668334347 | HLY2020627000141 | 10053066140 |  | 2026-05-06 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1037 | ثانوية حاكمة أبو عريش - مقررات | Abu Arish High School - Curriculum | Secondary | Boys | Jazan | Jazan | 17.006718945904325, 42.824927 | SXE2120627097728 | 10052812756 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1038 | ابتدائية أسماء بنت زيد بقنبورة | Asma Bint Zaid Primary School in Qanboura | Primary | Girls | Jazan | Jazan | 16.99452209503264, 42.855987567673104 | SMR2420628001449 | 10091905425 |  | 2026-04-07 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1039 | روضة الريان | Rawdat Al Rayyan | KinderGarten | Girls | Jazan | Jazan | 16°58'30.8"N 42°40'58.6"E | SXE2120627090085 | 10052798568 |  | 2026-03-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1040 | ابتدائية بحرة بنين | Bahra Boys' Primary School | Primary | Boys | Jazan | Jazan | 16.933887959125236, 42.76675604418091 | SXE2120627106985 | 10052992073 |  | 2026-04-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1041 | ابتدائية ومتوسطة بحرة بنات | Bahra Girls' Elementary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.93674599511486, 42.77257233434316 | SXE2120627107091 | 10052885879 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1042 | ابتدائية الخضراء الجنوبية بنين | Al-Khadraa Al-Janoubia Elementary School for Boys | Primary | Boys | Jazan | Jazan | 17.038445655915556, 42.81451968465527 | SXE2120627107061 | 10052541439 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1043 | روضة جميلة بنت عمر بن الخطاب بالمجصص | Beautiful kindergarten, daughter of Omar Ibn Al-Khattab, in Al-Majass | KinderGarten | Girls | Jazan | Jazan | 17.04146651095394, 42.87739364603415 | HLY2020627000509 | 10053009887 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1044 | مدرسة ابتدائية طارق بن زياد | Tariq Bin Ziyad Elementary School | Primary | Boys | Jazan | Jazan | 17.138381707866845, 42.61926791349146 | SXE2120627106739 | 10052886562 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1045 | ابتدائية البيض الأسفل بنين | Lower Al-Bayd Primary School for Boys | Primary | Boys | Jazan | Jazan | 17.046201133867385, 42.83025084047438 | SXE2120627097776 | 10102835192 |  | 2026-04-23 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1046 | الابتدائية السادسة بأبو عريش | Sixth Elementary School in Abu Arish | Primary | Boys | Jazan | Jazan | 16.97535627432318, 42.83577970000001 | SXE2120627106996 | 10052569402 |  | 2026-03-17 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1047 | ابتدائية صنبة | Sanba Primary School | Primary | Boys | Jazan | Jazan | 17°01'41.4"N 42°41'44.6"E | SXE2120627106846 | 10052645424 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1048 | ابتدائية صفوة بأم حجل | Safwa Primary School in Umm Hajal | Primary | Boys | Jazan | Jazan | 16.864896681915724, 42.90960631163819 | SMR2320621019280 | 10102490728 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1049 | ثانوية زبارة رشيد | Zubara Rashid High School | Secondary | Girls | Jazan | Jazan | 16.940152738135236, 42.908290055819094 | SXE2120627106663 | 10052622125 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1050 | ثانوية حطين - مسارات | Hattin High School - Pathways | Secondary | Boys | Jazan | Jazan | 16.786382654143058, 42.951104457672365 | SXE2120627096065 | 10052578420 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1051 | متوسطة الخضراء الجنوبية بنات | Al-Khadraa Al-Janoubia Intermediate School for Girls | Intermediate | Boys | Jazan | Jazan | 17°02'29.4"N 42°48'44.5"E | SXE2120627107060 | 10101210061 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1052 | ابتدائية الخشابية | Al-Khashabiyah Primary School | Primary | Boys | Jazan | Jazan | 16.949380199156835, 42.73067848280202 | SXE2120627106933 | 10052454398 |  | 2026-04-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1053 | روضة ضمد الاولى | First Dhamad Kindergarten | KinderGarten | Girls | Jazan | Jazan | 17.104133354833646, 42.774664968498655 | SXE2120627106775 | 10052692246 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1054 | مدرسة خضيرة الابتدائية | Hadera Elementary School | Primary | Boys | Jazan | Jazan | 17°04'38.5"N 42°44'53.2"E | SXE2120627106710 | 10052723576 |  | 2026-04-12 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1055 | الثانوية الرابعة بأبو عريش - مقررات | Fourth Secondary School in Abu Arish - Curriculum | Secondary | Girls | Jazan | Jazan | 16°58'30.1"N 42°50'09.4"E | HLY2020627011725 | 10052571349 |  | 2026-03-17 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1056 | مدرسة ابتدائية الاثلة | Al-Athla Elementary School | Primary | Girls | Jazan | Jazan | 17.170256984100686, 42.52023845952562 | SXE2120627090741 | 10052830011 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1057 | مدرسة متوسطة أبو السلع بنات بصبيا | Abu Al-Sila'a Intermediate School for Girls in Sabya | Intermediate | Girls | Jazan | Jazan | 17.244857300692964, 42.607372740474375 | SXE2020627018008 | 10052543602 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1058 | ابتدائية المخشلية بنات | Al-Makhshaliya Girls' Primary School | Primary | Girls | Jazan | Jazan | 16.78649595240109, 42.94595895767236 | SXE2120627096069 | 10052696890 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1059 | ابتدائية الجربة | Al-Jarba Primary School | Primary | Girls | Jazan | Jazan | 16.786434322465112, 42.9459375 | HLY2020627000540 | 10086073407 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1060 | ابتدائية الحكمة طفولة مبكرة | Al-Hikma Elementary School - Early Childhood | Primary | Girls | Jazan | Jazan | 16.89454305146105, 42.5570755 | SXE2120627089314 | 10052985758 |  | 2026-03-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1061 | ثانوية السادلية | Al-Sadliya Secondary School | Secondary | Girls | Jazan | Jazan | 16°55'23.5"N 42°49'29.4"E | SXE2120627106786 | 10098811302 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1062 | روضة سلافة بنت البراء بالسادلية | Rawda Salafa Bint Al-Bara’a in Al-Sadliya | KinderGarten | Girls | Jazan | Jazan | 16.923553673414382, 42.82522457658706 | SXE2120627106785 | 10098808871 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1063 | ابتدائية الفيصلية | Al-Faisaliah Elementary School | Primary | Boys | Jazan | Jazan | 16.932079579434205, 42.559014342327636 | SXE2020627013645 | 10053065625 |  | 2026-03-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1064 | ابتدائية المثنى بن حارثة | Al-Muthanna Bin Haritha Elementary School | Primary | Boys | Jazan | Jazan | 16.89497465105003, 42.55653295767237 | SXE2120627097895 | 10053013191 |  | 2026-03-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1065 | ابتدائية علي بن أبي طالب | Ali Bin Abi Talib Elementary School | Primary | Boys | Jazan | Jazan | 16.898312282273935, 42.54881429444022 | SXE2120627106960 | 10052606103 |  | 2026-04-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1066 | ابتدائية عبدالله بن عباس | Abdullah bin Abbas Elementary School | Primary | Boys | Jazan | Jazan | 16.889715488189506, 42.57970028465529 | SXE2120627097884 | 10053026298 |  | 2026-03-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1067 | ابتدائية عمير والخرادلة | Omair and Al-Kharadla Elementary School | Primary | Boys | Jazan | Jazan | 16.93079556901566, 42.632841967480445 | SXE2120627106959 | 10053050346 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1068 | الابتدائية الاولى بجازان | First Elementary School in Jazan | Primary | Girls | Jazan | Jazan | 16.882816782103745, 42.563681213812735 | SXE2120627097805 | 10052951419 |  | 2026-03-16 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1069 | ابتدائية المضايا الأولى | Al-Madaya First Primary School | Primary | Boys | Jazan | Jazan | 16.75534887007164, 42.730054094461615 | SXE2120627090650 | 10052759130 |  | 2026-04-25 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1070 | ثانوية قرطبة | Cordoba High School | Secondary | Boys | Jazan | Jazan | 16.626799284734247, 42.862743371164825 | SXE2120627097620 | 10052690091 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1071 | ابتدائية محلية | Local primary school | Primary | Boys | Jazan | Jazan | 16.94134163758386, 42.64094050184612 | SXE2120627096463 | 10052455500 |  | 2026-04-15 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1072 | عبد الملك بن مروان بصامطة | Abdul Malik bin Marwan in Samtah | NA | Boys | Jazan | Jazan | 16.549758023413865, 42.9777391558242 | SXE2120627096154 | 10052991451 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1073 | مجمع مدارس الخالدية / متوسط | Al-Khalidiyah Schools Complex / Intermediate | Intermediate | Boys | Jazan | Jazan | 17.14953133361827, 42.61282215038133 | SXE2120627105382 | 10053067432 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1074 | مدرسة صبيا المتوسطة بنين | Sabya Intermediate School for Boys | Intermediate | Girls | Jazan | Jazan | 17.158682386154855, 42.65150739630776 | SXE2120627106619 | 10052914406 |  | 2026-04-20 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1075 | ثانوية كرامة الأحمر | Karama Al-Ahmar High School | Secondary | Girls | Jazan | Jazan | 17.159158392380636, 42.65287785582418 | SXE2120627106777 | 10052504570 |  | 2026-04-20 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1076 | متوسطة صبيا الاولى | Sabya First Intermediate School | Intermediate | Girls | Jazan | Jazan | 17.15236265578818, 42.63867834232967 | SXE2120627106616 | 10091698633 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1077 | الابتدائية السادسة بصبيا | Sixth Elementary School in Sabya | Primary | Girls | Jazan | Jazan | 17.15390279946398, 42.6502813558242 | SXE2020627018056 | 10053047841 |  | 2026-04-14 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1078 | مجمع صبيا الابتدائية الخامسة | Sabya Fifth Elementary Complex | Primary | Girls | Jazan | Jazan | 17.15722135362705, 42.6309806558242 | SXE2120627107170 | 10052892981 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1079 | مجمع صبيا _ الثانوية الرابعة مقررات | Sabya Complex - Fourth Secondary School (Curriculum) | Secondary | Girls | Jazan | Jazan | 17.157744007157877, 42.63071789815387 | SXE2120627106621 | 10052739217 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1080 | الثانوية الخامسة بصبيا | Fifth Secondary School in Sabya | Secondary | Girls | Jazan | Jazan | 17.152597484061687, 42.65067057301098 | SXE2020627018053 | 10052831635 |  | 2026-04-14 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1081 | روضة سيرين القبطية بالسر + ابتدائية السر بنين + ابتدائية السر بنات | Sirin Coptic Kindergarten + Sirr Boys' Primary School + Sirr Girls' Primary School | KinderGarten | Girls | Jazan | Jazan | 16.732563 42.902365 | HLY2020627042892 | 10052913294 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1082 | ثانوية مزهرة | Blossom High School | Secondary | Girls | Jazan | Jazan | 16.8362325 42.7348711 | SXE2120627096239 | 10086616889 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1083 | مدرسة التيسير للطفولة المبكرة بالحصامة | Al-Taysir Early Childhood School in Al-Hasama | Early Childhood | Boys | Jazan | Jazan | 16.6846120 42.9233640 | SXE2120627101568 | 10052449100 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1084 | متوسطة مزهرة | Medium flowering | Intermediate | Boys | Jazan | Jazan | 16.833814 42.736811 | SXE2120627096233 | 10052452956 |  | 2026-05-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1085 | ابتدائية ومتوسطة تحفيظ القرآن الكريم بالأحد + الثانوية الثالثة بالأحد | Al-Ahad Primary and Intermediate School for Quran Memorization + Third Secondary School in Al-Ahad | Intermediate | Boys | Jazan | Jazan | 16.7112347 42.9583902 | SXE2120627105321 | 10089848466 |  | 2026-05-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1086 | المتوسطة والثانوية الثانية بالاحد | Second Intermediate and Secondary School in Al-Ahad | Intermediate | Girls | Jazan | Jazan | 16.718043 42.957032 | SXE2120627106440 | 10052452366 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1087 | الروضة الأولى بالأحد | Kindergarten 1 on Sunday | Intermediate | Girls | Jazan | Jazan | 16.7108758 42.9656098 | HLY2020627041271 | 10084394039 |  | 2026-04-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1088 | روضة وابتدائية البيطارية والعوق السمعي | Al-Baytariyah Kindergarten and Primary School for the Hearing Impaired | KinderGarten | Girls | Jazan | Jazan | 16.721047 42.974121 | SXE2120627096745 | 10052992529 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1089 | اروى بنت مالك الابتدائية | Arwa Bint Malik Elementary School | Primary | Girls | Jazan | Jazan | 16.5788133 42.9478677 | SXE2020627041722 | 10104460245 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1090 | متوسطة وثانوية الراحة + ابتدائية ام التراب | Al-Raha Intermediate and Secondary School + Umm Al-Turab Primary School | Intermediate | Girls | Jazan | Jazan | 16.736953 43.158418 | SMR2320621014758 | 10098628050 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1091 | ابتدائية صقر الجزيرة | Saqr Al Jazeera Elementary School | Primary | Boys | Jazan | Jazan | 16.713739 42.964098 | SXE2120627096025 | 10053050490 |  | 2026-04-27 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1092 | ابتدائية ومتوسطة الحامضة | Al-Hamda Primary and Intermediate | Intermediate | Boys | Jazan | Jazan | 16.765862 42.923650 | HLY2020627042818 | 10052577899 |  | 2026-04-26 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1093 | ابتدائية ومتوسطة وثانوية جحا | Juha Elementary, Intermediate and Secondary | Intermediate | Boys | Jazan | Jazan | 16.674437 42.899902 | HLY2020627040299 | 10052811599 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1094 | متوسطة وثانوية جعفر الطيار بالمضايا | Jaafar Al-Tayyar Intermediate and Secondary School in Al-Madaya | Intermediate | Boys | Jazan | Jazan | 16.751893 42.730989 | SXE2120627090652 | 10052780859 |  | 2026-04-25 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1095 | متوسطة وثانوية المرابي | Al-Murabi Intermediate and Secondary School | Intermediate | Boys | Jazan | Jazan | 16.653664 42.778111 | SXE2120627089584 | 10052493387 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1096 | ابتدائية ومتوسطة وثانوية تحفيظ القرآن الكريم بأحد المسارة + ابتدائية الغصينية | Elementary, intermediate and secondary Quran memorization schools in Ahad Al-Masarah + Al-Ghusainiyah Elementary School | Intermediate | Boys | Jazan | Jazan | 16.713304 42.964203 | SXE2120627096026 | 10053050355 |  | 2026-04-27 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1097 | ابتدائية الزاوية بصامطة | Al-Zawiya Primary School in Samtah | Primary | Boys | Jazan | Jazan | 16.639663 42.902580 | SXE2120627096737 | 10089507583 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1098 | ثانوية الطوال الثانية + مدرسة شعب الذيب الابتدائية والمتوسطة | Al-Tawal Secondary School 2 + Shaab Al-Dheeb Primary and Intermediate School | Secondary | Boys | Jazan | Jazan | 16.547193 42.979889 | SXE2120627089538 | 10086129020 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1099 | الروضة والطفولة المبكرة وابتدائية الشمهانية + الابتدائية الاولي بالطوال | Al-Rawda, Early Childhood and Primary School, Al-Shamaniya + Al-Tawal First Primary School | KinderGarten | Girls | Jazan | Jazan | 16.5377333 42.9263896 | SXE2120627096152 | 10052968318 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1100 | ابتدائية ومتوسطة جمانة الهاشمية + روضة ام عمار بنت عميس + الابتدائية الثانية بالطوال | Jumana Al-Hashimiya Elementary and Intermediate School + Umm Ammar Bint Umays Kindergarten + Al-Tawal Second Elementary School | KinderGarten | Girls | Jazan | Jazan | 16.5462227 42.9786665 | SXE2120627089521 | 10084996072 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1101 | متوسطة وثانوية الجرادية بنات | Al-Jaradiyah Intermediate and Secondary School for Girls | Intermediate | Girls | Jazan | Jazan | 16.5810448 42.911870 | SXE2120627096133 | 10052723361 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1102 | الابتدائية الثانية بالجرادية والروضة الاولي بالجرادية | The second primary school in Al-Jaradiyah and the first kindergarten in Al-Jaradiyah | KinderGarten | Girls | Jazan | Jazan | 16.586286 42.911744 | SXE2120627101498 | 10084992064 |  | 2026-04-28 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1103 | الابتدائية الأولى بالجرادية + روضة الجردية | First Elementary School in Al-Jaradiyah + Al-Jaradiyah Kindergarten | Primary | Girls | Jazan | Jazan | 16.589681 42.926568 | SXE2120627089491 | 10052656277 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1104 | ابتدائية النجامية ورضة درة بنت ابي سفيان | Al-Najamiyah Primary School and Durrat Bint Abi Sufyan Kindergarten | KinderGarten | Boys | Jazan | Jazan | 16.562745 42.945337 | SXE2120627096052 | 10104460218 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1105 | الثانوية الثالثة بصامطة - مقررات | Third Secondary School in Samtah - Curriculum | Secondary | Girls | Jazan | Jazan | 16.6043018 42.9501566 | SXE2120627106723 | 10052485133 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1106 | الثانوية الاولي بصامطة + الروضة الاولي بصامطة | First Secondary School in Samtah + First Kindergarten in Samtah | Secondary | Girls | Jazan | Jazan | 16.596432 42.946904 | SXE2120627097789 | 10052866953 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1107 | الابتدائية الرابعة والروضة الثانية | Fourth Elementary and Second Kindergarten | Primary | Girls | Jazan | Jazan | 16.6038404 42.9501295 | SXE2120627106721 | 10052454871 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1108 | برنامج العوق الفكري بثانوية مجعر | Intellectual Disability Program at Majar High School | Secondary | Girls | Jazan | Jazan | 16.614087 42.988118 | HLY2020627000111 | 10052719303 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1109 | روضة وابتدائية مجعر | Majar Kindergarten and Elementary School | KinderGarten | Boys | Jazan | Jazan | 16.614580 42.989560 | HLY2020627000127 | 10052689106 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1110 | الثانوية الثانية بصامطة - مقررات | Second Secondary School in Samtah - Curriculum | Secondary | Girls | Jazan | Jazan | 16.591879 42.936831 | SXE2120627097787 | 10053072728 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1111 | الابتدائية الثالثة والمتوسطة الثانية | Third Elementary and Second Intermediate | Primary | Girls | Jazan | Jazan | 16.6067442 42.9334240 | SXE2020627018784 | 10052966467 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1112 | الابتدائية الثانية بصامطة | Second Elementary School in Samtah | Primary | Girls | Jazan | Jazan | 16.6067899 42.9335460 | SXE2020627018777 | 10052966592 |  | 2026-04-18 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1113 | الروضة الثالثة بصامطة | The third kindergarten in Samtah | KinderGarten | Girls | Jazan | Jazan | 16.607059 42.933585 | SXE20206270187781 | 10082636097 |  | 2026-04-19 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1114 | ابتدائية و متوسطة تحفيظ القرآن | Elementary and middle school Quran memorization | Primary | Girls | Jazan | Jazan | 16.607182 42.934143 | SXE2020627018783 | 10052966313 |  | 2026-04-19 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1115 | روضة أسماء بنت ابي بكر بالجاضع + ابتدائية الجاضع | Asma Bint Abi Bakr Kindergarten in Al-Jadhe' + Al-Jadhe' Elementary School | KinderGarten | Girls | Jazan | Jazan | 16.644138 42.992464 | SXE2120627096684 | 10052871247 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1116 | ابتدائية ومتوسطة الدغارير | Al-Daghareer Primary and Intermediate School | Primary | Girls | Jazan | Jazan | 16.674227 42.957659 | SXE2120627106724 | 10053065634 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1117 | روضة سارة عبد العزيز + ابتدائية الركوبة | Sarah Abdul Aziz Kindergarten + Al-Rukuba Elementary School | KinderGarten | Girls | Jazan | Jazan | 16.617515 42.967031 | SXE2120627097854 | 10053072263 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1118 | روضة ومتوسطة حاكمة الدغارير | Rawda and Intermediate School of Hakamah Al-Daghareer | KinderGarten | Girls | Jazan | Jazan | 16.680374 42.977194 | SXE2120627096764 | 10053067011 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1119 | ابتدائية حاكمة الدغارير | Al-Daghareer Primary School | Primary | Boys | Jazan | Jazan | 16.680374 42.977194 | SXE2120627089526 | 10052697341 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1120 | روضة ام كلثوم بنت ابي بكر + ابتدائية ومتوسطة الحجفار | Umm Kulthum Bint Abi Bakr Kindergarten + Al-Hajfar Elementary and Intermediate School | Intermediate | Girls | Jazan | Jazan | 16.543078 42.844517 | SXE2120627107160 | 10052571821 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1121 | متوسطة وثانوية ديحمة | Dihma Intermediate and Secondary School | Intermediate | Boys | Jazan | Jazan | 16.5163364 42.7964308 | SXE2120627107156 | 10052659152 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1122 | ابتدائية ومتوسطة وثانوية تحفيظ القرآن الكريم بدحيمة | Primary, intermediate and secondary school for memorizing the Holy Quran in Dahima | Primary | Boys | Jazan | Jazan | 16.5283091 42.7916146 | SXE2120627096022 | 10052948039 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1123 | ابتدائية ومتوسطة وثانوية العباس بن عبد المطلب | Al-Abbas Bin Abdul Muttalib Elementary, Intermediate and Secondary School | Secondary | Boys | Jazan | Jazan | 16.5313208 42.9501935 | SXE2120627096091 | 10052871686 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1124 | ابتدائية ومتوسطة وثانوية زمزم | Zamzam Elementary, Intermediate and Secondary | Primary | Boys | Jazan | Jazan | 16.433222 42.840497 | SXE2120627096650 | 10053086330 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1125 | متوسطة وثانوية الحضرور | Al-Hadhrur Intermediate and Secondary School | Intermediate | Boys | Jazan | Jazan | 16.5405809 42.8662152 | SXE2120627107072 | 10052698651 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1126 | ابتدائية الجرادية | Al-Jaradiyah Primary School | Primary | Boys | Jazan | Jazan | 16.5868427 42.9062365 | SXE2120627095992 | 10089085519 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1127 | متوسطة وثانوية الجرادية | Al-Jaradiyah Intermediate and Secondary School | Intermediate | Boys | Jazan | Jazan | 16.5787905 42.9018299 | SXE2120627101595 | 10086390718 |  | 2026-04-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1128 | مدرسة الموسم الابتدائية | Season Elementary School | Primary | Girls | Jazan | Jazan | 16.4248133 42.8282653 | SXE2120627096743 | 10053087927 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1129 | ابتدائية الملك خالد بن عبد العزيز + متوسطة صامطة | King Khalid bin Abdul Aziz Elementary School + Samtah Intermediate School | Primary | Boys | Jazan | Jazan | 16.5981437 42.9416949 | SXE2120627098903 | 10088904168 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1130 | ثانوية الشيخ عبدالله القرعاوي | Sheikh Abdullah Al-Qarawi High School | Secondary | Boys | Jazan | Jazan | 16.629796 42.907999 | SXE2120627089571 | 10090506168 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1131 | ابتدائية الملك سعود + ابتدائية ومتوسطة مجعر | King Saud Elementary School + Majar Elementary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.6085483 42.9579263 | HLY2020627039848 | 10089849230 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1132 | ابتدائية عثمان بن عفان بصامطة | Othman Bin Affan Elementary School in Samtah | Primary | Boys | Jazan | Jazan | 16.6271927 42.9108837 | SXE2120627106752 | 10089779565 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1133 | ابتدائية ومتوسطة الجاضع | Al-Jadha'a Elementary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.6424431 42.9905705 | SXE2120627096687 | 10052502154 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1134 | ابتدائية ومتوسطة حاكمة الدغارير | Al-Daghareer Primary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.683592 42.982267 | HLY2020800425046 | 30130649753 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1135 | ابتدائية قائم العتنة | Qaim Al-Atna Primary School | Primary | Boys | Jazan | Jazan | 16.6751732 43.0009543 | SXE2120627107042 | 10085784791 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1136 | ابتدائية ومتوسطة وثاونوية الدغارير | Al-Daghareer Primary, Intermediate and Secondary School | Primary | Boys | Jazan | Jazan | 16.6690428 42.9537830 | SMR2420628012389 | 10052947873 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1137 | ابتدائية ومتوسطة الحجفار | Al-Hajfar Primary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.54186503 42.85045854 | SXE2120627107152 | 10052914371 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1138 | الثانوية الرابعة | Fourth Secondary School | Secondary | Girls | Jazan | Jazan | 16.930624 42.562888 | SXE2020627013646 | 10052989461 |  | 2026-04-01 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1139 | الابتدائية الرابعة | Fourth Elementary School | Primary | Girls | Jazan | Jazan | 16.925657 42.556166 | SXE2120627089265 | 10052989069 |  | 2026-03-31 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1140 | الروضة الثالثة والابتدائية الثالثة | Third Kindergarten and Third Elementary School | Primary | Girls | Jazan | Jazan | 16.930549 42.561700 | SXE2020627013648 | 10052989354 |  | 2026-03-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1141 | الابندائية العاشرة والمتوسطة الرابعة | Tenth Elementary and Fourth Intermediate | Primary | Girls | Jazan | Jazan | 16.926498 42.556190 | SXE2120627089241 | 30062691521 |  | 2026-04-01 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1142 | ابتدائية المغارية | Al-Maghariah Primary School | Primary | Girls | Jazan | Jazan | 16.926495 42.557315 | SXE2120627089244 | 10053076610 |  | 2026-03-31 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1143 | الابتدائية السادسة والمتوسطة الثالثة | Sixth Elementary and Third Intermediate | Primary | Girls | Jazan | Jazan | 16.931136 42.561683 | SXE2120627101535 | 10052908721 |  | 2026-03-29 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1144 | ابتدائية السويس ومتوسطة معاذ بن جبل وثانوية الأمير فيصل بن عبد الله | Suez Elementary School, Mu'adh ibn Jabal Intermediate School, and Prince Faisal ibn Abdullah Secondary School | Primary | Boys | Jazan | Jazan | 16.877771 42.574784 | SXE2120627089185 | 10086885439 |  | 2026-04-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1145 | ثانوية الروضة | Al-Rawda High School | Secondary | Boys | Jazan | Jazan | 16.9206979 42.5606261 | SXE2120627106911 | 10053049944 |  | 2026-05-05 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1146 | ابتدائية خالد بن الوليد + ابتدائية ومتوسطة دار التوحيد | Khalid Bin Al-Walid Elementary School + Dar Al-Tawhid Elementary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.914993 42.568620 | SXE2120627106909 | 10095203215 |  | 2026-04-02 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1147 | المعهد العلمي بجازان + ثانوية الرازي | Jazan Scientific Institute + Al-Razi High School | Secondary | Boys | Jazan | Jazan | 16.8819097 42.5453265 | SXE2120627096559 | 10052796797 |  | 2026-04-04 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1148 | ثانوية الخوارزمي وابتدائية الفيصلية | Al-Khwarizmi Secondary School and Al-Faisaliyah Primary School | Secondary | Boys | Jazan | Jazan | 16.9322892 42.5585199 | SXE2020627013647 | 10053065751 |  | 2026-03-30 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1149 | ابتدائية سوق الليل | Souq Al-Layl Primary School | Primary | Boys | Jazan | Jazan | 16.7184350 42.9942377 | HLY2020627010085 | 10052990239 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1150 | ابتدائية ومتوسطة البيطارية | Al-Bitariya Primary and Intermediate School | Primary | Boys | Jazan | Jazan | 16.718656 42.975013 | SXE2120627096751 | 10090524630 |  | 2026-05-03 | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 11 | 0 | 4 | In Progress
| SS-ZAM-JAZ1151 | مدرسة وروضة وابتدائية فكري البطيخ | Fikri Al-Battikh Kindergarten and Primary School | KinderGarten | Boys | Jazan | Jazan | 17.12392487115642, 42.48596779999999 | HLY2020627010611 | 10052946212‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1152 | مدرسة الغراء الابتدائية والمتوسطة | Al-Gharaa Primary and Intermediate School | Intermediate | Boys | Jazan | Jazan | 16.949380199156835, 42.73067848280202 | SXE2120627097493 | 10053026224‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1153 | ابتدائية العرضة | Al-Ardah Primary School | Primary | Boys | Jazan | Jazan | 17.247806310148682, 42.611034184658806 | SMR2420628001425 | 10052868528‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1154 | مدرسة ابوالسلع الابتدائية والمتوسطة بنين | Abu AlSila Primary and Intermediate School | Intermediate | Boys | Jazan | Jazan | 17.296092474636197, 42.75200704676873 | SXE2020627018002 | 10052532814‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1155 | متوسطة وثانوية ابو السلع للبنات | Abu AlSila Intermediate and Secondary School | Intermediate | Boys | Jazan | Jazan | 17.252877810121436, 42.75447981608179 | SXE2120627106909 | 10095203215‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1156 | ابتدائية ومتوسطة بحرة | Bahrah Primary and Intermediate School | Intermediate | Boys | Jazan | Jazan | 16.987548567934102, 42.849456780358025 | SXE2120627106985 | 10052992073‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1157 | مدرسة الفيصل الابتدائية بنين | Al-Faisal Primary School - Boys | Primary | Boys | Jazan | Jazan | 17.156799679777272, 42.6363276404922 | HLY2020627010628 | 10053034315‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1158 | مدرسة الحسينية المتوسطة والثانوية | Al-Husayniyah Intermediate and Secondary School | Intermediate | Boys | Jazan | Jazan | 17.36964072784007, 42.52918987861999 | SXE2020627018009 | 10052693637‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1159 | ابتدائية قنبورة و متوسطة قنبورة | Qanbura Intermediate School | Intermediate | Boys | Jazan | Jazan | 17.316238472415105, 42.523981604398344 | SXE2120627096676 | 10052992654‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1160 | ابتدائية صبيا الثامنة للبنات | Sabya Eighth Primary School - Girls | Primary | Girls | Jazan | Jazan | 17.379123695865346, 42.53734628396789 | SXE2020627018004 | 10052449594‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1161 | مدرسة ابوهريرة الابتدائية | Abo Hurairah primary | Primary | Boys | Jazan | Jazan | 16.903783619918542, 42.59797102154037 | SXE2120627090696 | 10052460770‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1162 | مدرسة النقاش الابتدائية | Alnagash primary | Primary | Boys | Jazan | Jazan | 16.91598740730388, 42.67129805653441 | SXE2120627089989 | 10052905194‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1163 | ثانوية بيش الاولي | Baish first high school | Secondary | Girls | Jazan | Jazan | 16.94355630459715, 42.69492362167121 | SXE2120627090608 | 10052827866‪ |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1164 | مدرسة الريان المتوسطة والثانوية بنين | Al‑Rayan Intermediate and Secondary School - Boys | Primary | Boys | Jazan | Jazan | 16.979833030684986, 42.69366300168897 | SXE2120627106886 | 10052953039 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1165 | ابتدائية علي بن أبي طالب | Ali Bin Abi Talib Elementary School | Primary | Boys | Jazan | Jazan | 16.898206725469915, 42.5488962346085 | SXE2120627106960 | 10052606103 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1166 | مدرسة الامير محمد بن ناصر بن عبدالعزيز | Mohammed bin Nasser bin Abdulaziz School |  |  | Jazan | Jazan | 16.87718668127097, 42.63469912928091 | SXE2120627089711 | 10052801449 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1167 | ثانوية الكربوس بنين | Al‑Karboos Secondary School - Boys | Secondary | Boys | Jazan | Jazan | 16.876699959785967, 42.63560014462911 | SXE2120627089753 | 10053050239 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1168 | ابتدائية ومتوسطة وثانوية الاساملة بنين | Alasamilah Primary Intermediate and Secondary School | Primary |  | Jazan | Jazan | 16.877056222650502, 42.749272687649004 | SXE2120627106987 | 10089945989 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1169 | متوسطة وثانوية مزهرة بنين | Mazharah Intermediate and Secondary School - Boys | Intermediate | Boys | Jazan | Jazan | 16.81801913788841, 42.73757735756474 | SXE2120627101298 | 10085677226 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1170 | مدرسة السبخة الابتدائية | Al‑Sabkha Primary School | Primary |  | Jazan | Jazan | 17.07816729945585, 42.52827534881189 | SXE2120627097492 | 10089967529 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1171 | ابتدائية ومتوسطة جريبة | Jareebah Primary and Intermediate Schoo | Primary |  | Jazan | Jazan | 17.11120423121248, 42.54845414673346 | SXE2120627097573 | 10087366421 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1172 | مدرسة الجديين | Al‑Jadiyeen School |  |  | Jazan | Jazan | 17.11339980272827, 42.57500157734841 | SXE2120627106741 | 10052825244 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1173 | مجمع الباحر التعليمي | Al‑Baher Educational Complex |  |  | Jazan | Jazan | 17.125357853951087, 42.603054626969524 | SXE2120627097669 | 10097361911 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1174 | ابتدائية الظبية الاولي | Al‑Dhabyah First Primary School | Primary |  | Jazan | Jazan | 17.1153352274889, 42.66680476887286 | SXE2120627097450 | 10090292651 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1175 | العريش الابتدائية والمتوسطة | Al‑Areesh Primary and Intermediate School | Primary |  | Jazan | Jazan | 17.140444377933726, 42.71710193081111 | SXE2120627097419 | 10052865571 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1176 | ابتدائية ابن خلدون | Ibn Khaldun Primary School | Primary |  | Jazan | Jazan | 17.152216638318624, 42.638015080148904 | SXE2120627106763 | 10091555434 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1177 | ثانوية صبيا ا الثانية | Sabya Second Secondary School | Secondary |  | Jazan | Jazan | 17.151915384888458, 42.63915443832309 | SXE2120627106623 | 10091700482 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1178 | مدرسة الجمالة الابتدائية والمتوسطة | Al‑Jamalah Primary and Intermediate School | Primary |  | Jazan | Jazan | 17.181664393135556, 42.57668245261395 | SXE2120627097668 | 10052535119 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1179 | مدرسة ابوالقعائد الابتدائية والمتوسطة | Abu Al‑Qa’aid Primary and Intermediate School | Primary |  | Jazan | Jazan | 17.268271036148075, 42.60168829775256 | SXE2120627106762 | 10052537866 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1180 | مدرسة نخلان الابتدائية والمتوسطة | Nakhlan Primary and Intermediate School | Primary |  | Jazan | Jazan | 17.206500360273285, 42.65262910404406 | SXE2120627097431 | 10052945162 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1181 | مدرسةالحسيني الابتدائية والمتوسطة | Al‑Husaini Primary and Intermediate School | Primary |  | Jazan | Jazan | 17.15360150987553, 42.68468383737506 | HLY2020627045588 | 10053031912 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1182 | مدرسة ثانوية الحسيني مسارات | Al‑Husaini Tracks Secondary School | Secondary |  | Jazan | Jazan | 17.153314685623805, 42.68826215158078 | ALH2020807077233 | 10049073308 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1183 | المجمع التعليمي لمدارس جخيرة والجر الاعلي | Jukhayrah and Al‑Jar Al‑A‘la Schools Educational Complex |  |  | Jazan | Jazan | 17.16587655618579, 42.71737121348731 | SXE2120627097514 | 10053048393 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1184 | مدرسة المحلة الابتدائية | Al‑Mahallah Primary School | Primary |  | Jazan | Jazan | 17.292081793589833, 42.59998317019321 | HLY2020627010413 | 10090986142 |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1185 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1186 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1187 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1188 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1189 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1190 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1191 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1192 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1193 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1194 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1195 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1196 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1197 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1198 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1199 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
| SS-ZAM-JAZ1200 | [11 empty] | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 15 | 0 | 0 | Not Started
Total | [10 empty] | Total | Completed | 90 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
[12 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Not Started | 110 | 110 | 110 | 110 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
Note on L4: 4/2/2025

## Al Hasa Schools -1
|  | Report Date | 2026-02-23
Project | Schools Information | [12 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordinates |  | School Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Al Hasa-1 | SS-ZAM-HASA1001 | الابتدائية الأولى بالجبيل | First Elementary School in Jubail | Primary | Girls | Al Hasa | Al Hasa | 25.4064 | 49.6594 | 25.4063891,49.6594054 | KFM2020660221795 | 10083527097 | [18 empty] | 0 | 0 | 0 | Not Started | Primary | Boys | Not Started
| SS-ZAM-HASA1002 | ابتدائية المنذر بن ساوى بالرميلة للطفولة المبكرة | Al-Mundhir Bin Sawa Elementary School in Al-Rumailah for Early Childhood Education | Secondary | Girls | Al Hasa | Al Hasa | 25.4253 | 49.7147 | 25.4253412,49.7146884 | SMR2220661015002 | 10104714632 | [18 empty] | 0 | 0 | 0 | Not Started | Intermediate | Girls | In Progress
| SS-ZAM-HASA1003 | ابتدائية البيان للطفولة المبكرة | Al-Bayan Elementary School for Early Childhood Education | Primary | Girls | Al Hasa | Al Hasa | 25.3859 | 49.6679 | 25.3858819,49.6678631 | KFM2120655000125 | 10104816356 | [18 empty] | 0 | 0 | 0 | Not Started | Secondary | NA | Completed
| SS-ZAM-HASA1004 | الابتدائية الثانية بالعمران | Second Elementary School in Al-Umran | Primary | Girls | Al Hasa | Al Hasa | 25.4183 | 49.7282 | 25.4182594,49.7281729 | KFM2020660228697 | 10006352727 | [18 empty] | 0 | 0 | 0 | Not Started | NA |  | NA
| SS-ZAM-HASA1005 | المتوسطة الأولى بالعمران | First Intermediate School in Al-Umran | Intermediate | Girls | Al Hasa | Al Hasa | 25.4226 | 49.7217 | 25.4226359,49.7217487 | KFM2120660239960 | 10006320840 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1006 | المتوسطة الأولى بالجفر | First Intermediate School in Al-Jafar | Intermediate | Girls | Al Hasa | Al Hasa | 25.3823 | 49.7233 | 25.3823043,49.7233134 | KFM2020660228706 | 10006353804 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1007 | الثانوية الأولى بالعمران مقررات | First Secondary School in Al-Umran (Curriculum-Based) | Secondary | Girls | Al Hasa | Al Hasa | 25.4229 | 49.7212 | 25.4228827,49.721177 | KFM2120660239955 | 10006321687 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1008 | الثانوية الأولى بالجبيل | First Secondary School in Jubail | Secondary | Girls | Al Hasa | Al Hasa | 25.4094 | 49.6565 | 25.4093649,49.6565469 | SMR2220661009279 | 10105272114 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1009 | الثانوية الاولى بالجفر | First Secondary School in Al-Jafar | Secondary | Girls | Al Hasa | Al Hasa | 25.3782 | 49.7206 | 25.3781986,49.7205621 | KFM2120660260916 | 10083210852 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1010 | الابتدائية الأولى بالمركز للطفولة المبكرة | First Elementary School in the Early Childhood Center | Primary | Girls | Al Hasa | Al Hasa | 25.3973 | 49.7298 | 25.3973154,49.7298476 | KFM2120660255167 | 10006353395 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1011 | الابتدائية الأولى بالرميلة للطفولة المبكرة | First Elementary School in Al-Rumaila for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.4174 | 49.7326 | 25.4174354,49.7326063 | SMR2420661042201 | 10099268263 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1012 | مبنى ب 1 بنى معن سابقا ( الايمان للطفولة المبكرة) | Building B1, formerly known as Bani Ma'an (Al-Iman Early Childhood) | Primary | Girls | Al Hasa | Al Hasa | 25.3857 | 49.6365 | 25.3857272,49.6365077 | KFM2020660032117 | 10006349365 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1013 | الابتدائية الأولى بالشهارين | First Elementary School in Al-Shaharin | Primary | Girls | Al Hasa | Al Hasa | 25.3904 | 49.6578 | 25.3904057,49.6578095 | KFM2120660255145 | 10006349061 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1014 | المتوسطة الأولى بالرميلة | Al-Rumailah First Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.4176 | 49.7313 | 25.4176467,49.7313379 | KFM2120660255224 | 10006348617 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1015 | الروضة الأولى بمريبطة | Al-Ruwaidah First Kindergarten |  | Girls | Al Hasa | Al Hasa | 25.2785 | 49.7794 | 25.2784757,49.7794349 | SMR2220661015105 | 10104231135 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1016 | الثانوية الأولى بالرميلة | Al-Rumailah First Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.4178 | 49.7324 | 25.4177601,49.7323934 | KFM2120660239924 | 10006353789 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1017 | متوسطة جويرية بنت الحارث بالشهارين | Juwairiyah Bint Al-Harith Intermediate School in Al-Shaharin | Intermediate | Girls | Al Hasa | Al Hasa | 25.3903 | 49.6591 | 25.3903191,49.6591362 | KFM2020660221791 | 10018968158 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1018 | الابتدائية الجشة (الإحسان) للطفولة المبكرة | Al-Jishah (Al-Ihsan) Primary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3931 | 49.7514 | 25.3931053,49.7513536 | KFM2120660271335 | 10083515873 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1019 | ابتدائية الجشة الأولى للطفولة المبكرة | Al-Jishah First Elementary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3915 | 49.7508 | 25.391504,49.7507517 | KFM2120660241662 | 10006348475 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1020 | ابتدائية جعفر بن أبي طالب بالجفر | Jaafar bin Abi Talib Elementary School in Al-Jafar | Primary | Girls | Al Hasa | Al Hasa | 25.3833 | 49.7224333 | 25.3832939,49.7224333 | KFM2120660283619 | 10006346612 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1021 | ابتدائية أبي أيوب الأنصاري بالطرف | Abu Ayyub Al-Ansari Elementary School in Al-Taraf | Primary | Boys | Al Hasa | Al Hasa | 25.3492 | 49.7245 | 25.3491555,49.7245124 | KFM21206660260950 | 10006352413 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1022 | العمران الابتدائية بنين | Al-Umran Elementary School for Boys | Primary | Boys | Al Hasa | Al Hasa | 25.4146 | 49.7178 | 25.4145683,49.7177918 | KFM2120660239906 | 10006347647 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1023 | الابتدائية الثانية بالجبيل للطفولة المبكرة | Al-Jubail Second Elementary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3987 | 49.6553 | 25.3986992,49.6552842 | KFM2120660255114 | 10006321103 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1024 | ابتدائية الغويبة | Al-Ghuwaiba Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.2651 | 49.6947 | 25.2650712,49.6946785 | KFM2020660224272 | 10006306161 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1025 | ابتدائية المركز | Al-Markaz Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.393 | 49.7285 | 25.3930387,49.7284767 | KFM2120660255169 | 10006347807 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1026 | متوسطة الجشة | Al-Jishah Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3858 | 49.7468 | 25.3857962,49.7467764 | KFM2120660241737 | 10006344126 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1027 | ابتدائية الإمام الشوكاني (تق) بالطرف | Imam Al-Shawkani Primary School (Taq) in Al-Taraf | Primary | Boys | Al Hasa | Al Hasa | 25.3452 | 49.7231 | 25.3452293,49.7230616 | KFM2120660291651 | 10006321284 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1028 | ابتدائية الإمام السيوطي(تق) بالجشة | Imam Al-Suyuti Primary School (Taq) in Al-Jishah | Primary | Boys | Al Hasa | Al Hasa | 25.3899 | 49.7593 | 25.3899117,49.7592946 | KFM2120660239925 | 10006349347 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1029 | ابتدائية الشهارين | Al-Shuharin Primary School | Primary | Boys | Al Hasa | Al Hasa | 25.3879 | 49.6568 | 25.3878562,49.6567836 | KFM2120660255221 | 10006349131 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1030 | ابتدائية العرامية | Al-Aramiyah Primary School | Primary | Boys | Al Hasa | Al Hasa | 25.4128 | 49.7077 | 25.4127609,49.7077026 | KFM2120660239883 | 10006364881 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1031 | ثانوية الجبيل | Al-Jubail Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4002 | 49.6633 | 25.4001866,49.6633094 | KFM2120660255136 | 10006354365 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1032 | ثانوية مزدلفة بالشهارين | Muzdalifah Secondary School in Al-Shuharin | Secondary | Boys | Al Hasa | Al Hasa | 25.3895 | 49.6564 | 25.3894819,49.6563584 | KFM2120660255154 | 10006354230 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1033 | متوسطة الجفر | Al-Jafar Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3745 | 49.7253 | 25.3744974,49.7252644 | KFM2120660255112 | 10083066919 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1034 | ثانوية العمران مقررات | Al-Umran Secondary School (Curriculum-Based) | Secondary | Boys | Al Hasa | Al Hasa | 25.4092 | 49.7198 | 25.4092319,49.7197649 | KFM2120660290879 | 10006349599 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1035 | الأقصى الثانوية مقررات بالمنيزلة | Al-Aqsa Secondary School (Curriculum-Based) in Al-Munizlah | Secondary | Boys | Al Hasa | Al Hasa | 25.379 | 49.6712 | 25.3789965,49.6712393 | KFM2120660255092 | 10006321140 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1036 | ثانوية عرفات بالجشة | Arafat Secondary School in Al-Jishah | Secondary | Boys | Al Hasa | Al Hasa | 25.3857 | 49.7534 | 25.3856514,49.7533632 | KFM2120660240021 | 10006321829 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1037 | ثانوية الجفر مقررات | Al-Jafar Secondary School (Curriculum-Based) | Secondary | Boys | Al Hasa | Al Hasa | 25.3803 | 49.7217 | 25.3802512,49.7217058 | KFM2120660283618 | 10006344019 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1038 | متوسطة المزاوي بالساباط | Al-Mazawi Intermediate School in Al-Sabat | Intermediate | Boys | Al Hasa | Al Hasa | 25.3898 | 49.708 | 25.3898381,49.7079889 | KFM2120660260953 | 10006352217 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1039 | ثانوية أم مالك الأنصارية | Umm Malik Al-Ansariyah Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.4058 | 49.5915 | 25.4057782,49.5914849 | KFM2020660181078 | 10018828211 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1040 | متوسطة رقية بنت محمد | Ruqayyah Bint Muhammad Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.4381 | 49.5975 | 25.4380755,49.5974964 | KFM2120660241939 | 10103366614 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1041 | المتوسطة التاسعة بالمبرز | Al-Mubarraz Ninth Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.4532 | 49.6117 | 25.4532322,49.6117127 | KFM2120660240013 | 10006352235 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1042 | المتوسطة الحادية عشر بالمبرز | Al-Mubarraz Eleventh Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.4058 | 49.5781 | 25.4057949,49.5780862 | KFM2020660228929 | 10006367274 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1043 | المتوسطة الثانية عشر بالمبرز | Al-Mubarraz Twelfth Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.4187 | 49.5885 | 25.4186666,49.5884841 | KFM2020660181057 | 10006332519 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1044 | متوسطة الشيماء بنت الحارث بمريبطة | Al-Shayma Bint Al-Harith Intermediate School in Muraibitah | Intermediate | Girls | Al Hasa | Al Hasa | 25.2794 | 49.7805 | 25.279398,49.7804881 | SMR2320661027409 | 10105505889 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1045 | الثانوية الرابعة بالمبرز مقررات | Al-Mubarraz Fourth Secondary School (Curriculum-Based) | Secondary | Girls | Al Hasa | Al Hasa | 25.4078 | 49.5798 | 25.4077819,49.5797515 | KFM2020660181084 | 10006367121 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1046 | الثانوية السادسة بالمبرز | Al-Mubarraz Sixth Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.4627 | 49.6143 | 25.4627116,49.6142632 | KFM2120660271250 | 10006353214 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1047 | الثانوية الثامنة بالمبرز | Al-Mubarraz Eighth Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.4598 | 49.607 | 25.4598313,49.607039 | KFM2020660224840 | 10006334961 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1048 | الثانوية العاشرة بالمبرز | Al-Mubarraz Tenth Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.4405 | 49.574 | 25.4405274,49.5739861 | KFM2020660003483 | 10091712161 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1049 | الابتدائية الخامسة والعشرون بالمبرز للطفولة المبكرة | Al-Mubarraz Twenty-Fifth Elementary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.4379 | 49.5966 | 25.4378884,49.5966038 | KFM2120660241808 | 10103366632 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1050 | الابتدائية الخامسة بالمبرز للطفولة المبكرة | Fifth Elementary School in Al-Mubarraz for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.406 | 49.5787 | 25.4059503,49.5787179 | KFM2020660223163 | 10006365224 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1051 | الابتدائية السادسة بالمبرز للطفولة المبكرة | Sixth Elementary School in Al-Mubarraz for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.4078 | 49.5788 | 25.407804,49.5787739 | KFM2020660181081 | 10006365879 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1052 | الابتدائية الثانية عشر بالمبرز للطفولة المبكرة | Twelfth Elementary School in Al-Mubarraz for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.4588 | 49.6033 | 25.4587736,49.6032872 | KFM2120660283556 | 10006334999 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1053 | ابتدائية زينب بنت محمد | Zainab Bint Muhammad Elementary School | Primary | Girls | Al Hasa | Al Hasa | 25.4375 | 49.5975249 | 25.4375296,49.5975249 | KFM2120660241805 | 10103356322 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1054 | الابتدائية الرابعة بالمبرز | Fourth Elementary School in Al-Mubarraz | Primary | Girls | Al Hasa | Al Hasa | 25.4194 | 49.5793 | 25.419424,49.5793475 | KFM2020660181110 | 10018910016 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1055 | الابتدائية الثامنة والعشرون بالمبرز | Twenty-Eighth Elementary School in Al-Mubarraz | Primary | Girls | Al Hasa | Al Hasa | 25.4191 | 49.5518 | 25.4190655,49.5518076 | KFM2020660220766 | 10006333937 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1056 | ابتدائية حطين | Hattin Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4098 | 49.576 | 25.4097649,49.5759901 | KFM2020660180422 | 10006331834 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1057 | ابتدائية حمزة بن عبدالمطلب | Hamza Bin Abdul-Muttalib Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4116 | 49.5798 | 25.4116434,49.579825 | KFM2020660180485 | 10006330981 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1058 | ابتدائية الحسن بن علي | Al-Hasan bin Ali Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4211 | 49.5836 | 25.4211131,49.5836283 | KFM2020660180489 | 10006364835 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1059 | ابتدائية الحارث بن هشام المخزومي | Al-Harith bin Hisham Al-Makhzoumi Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4172 | 49.5512 | 25.4171541,49.5511981 | KFM2020660217041 | 10006366393 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1060 | متوسطة هجر | Hajar Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.4452 | 49.5787 | 25.4451687,49.5787216 | KFM2120660255291 | 10006363201 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1061 | ابتدائية الإمام القرطبي | Imam Al-Qurtubi Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4018 | 49.5996854 | 25.4017772,49.5996854 | KFM2020660180472 | 10006366606 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1062 | ثانوية المبرز | Al-Mubarraz Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4049 | 49.5957 | 25.4048982,49.5956554 | KFM2120660255321 | 10006365046 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1063 | ثانوية الملك سعود بالمبرز | King Saud Secondary School in Al-Mubarraz | Primary | Boys | Al Hasa | Al Hasa | 25.4291 | 49.5782 | 25.4291383,49.5781831 | KFM2120660283562 | 10091575419 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1064 | ثانوية أجنادين | Ajnadin Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4213 | 49.5843 | 25.4212585,49.5843109 | KFM2120660271377 | 10092419633 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1065 | ثانوية سعيد بن زيد | Saeed Bin Zaid Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4439 | 49.5780557 | 25.4439467,49.5780557 | KFM2120660255310 | 10006330711 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1066 | ثانوية عبدالله بن سلام | Abdullah Bin Salam Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4511 | 49.5954 | 25.4510652,49.5953925 | KFM2120660255343 | 10006333857 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1067 | متوسطة جبل النور | Jabal Al-Nour Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.4478 | 49.5958991 | 25.4478274,49.5958991 | KFM2120660255286 | 10006334157 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1068 | متوسطة طلحة بن عبيد الله | Talha Bin Ubaid Allah Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.4157 | 49.5614 | 25.4157069,49.5613834 | KFM2120660242316 | 10006331549 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1069 | الابتكار للطفولة المبكرة | Al-Ibtikar for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.4561 | 49.6003 | 25.4560997,49.6003325 | KFM2120660283559 | 10089612669 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1070 | ثانوية طارق بن زياد | Tariq Bin Ziyad Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4055 | 49.5985 | 25.4054503,49.5985381 | KFM2020660180423 | 10006333211 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1071 | ابتدائية عبدالله بن عباس | Abdullah Bin Abbas Primary School | Primary | Boys | Al Hasa | Al Hasa | 25.3944 | 49.5967 | 25.3944417,49.5966974 | KFM2120660285645 | 10006290562 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1072 | ابتدائية أبوبكر الرازي | Abu Bakr Al-Razi Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.3952 | 49.6030790 | 25.3951855,49.6030790 | KFM2020660181093 | 10006330908 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1073 | متوسطة الحديبية | Al-Hudaybiyah Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3943 | 49.5978 | 25.3942578,49.597837 | KFM2120660255231 | 10006324114 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1074 | ثانوية الفيصلية | Al-Faisaliyah Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.3967 | 49.6053 | 25.3966975,49.6052865 | KFM2020660180478 | 10006335323 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1075 | متوسطة أم المؤمنين أم حبيبة | Umm Al-Mu'minin Umm Habibah Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.3579 | 49.5562 | 25.3578963,49.5561773 | KFM2120660240076 | 10097181298 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1076 | الابتدائية الثانية بالهفوف للطفولة المبكرة | Second Elementary School in Al-Hofuf (Early Childhood) | Primary | Girls | Al Hasa | Al Hasa | 25.3664 | 49.5493440 | 25.3664295,49.5493440 | KFM2120655000123 | 10194821599 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1077 | الابتدائية الأولى لتحفيظ القرآن بالهفوف | First Elementary School for Quran Memorization in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.35 | 49.6054 | 25.3499603,49.6053552 | KFM2120660240653 | 10006307811 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1078 | المتوسطة السادسة عشر بالهفوف | Sixteenth Intermediate School in Al-Hofuf | intermediat | Girls | Al Hasa | Al Hasa | 25.3366 | 49.5888 | 25.3366118,49.5888154 | KFM2020660216690 | 10006307768 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1079 | المتوسطة الثانية والعشرون بالهفوف | Twenty-Second Intermediate School in Al-Hofuf | intermediat | Girls | Al Hasa | Al Hasa | 25.3596 | 49.6122854 | 25.3595926,49.6122854 | KFM2020660228913 | 10006307104 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1080 | الابتدائية الثانية والأربعون بالهفوف | Forty-Second Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3117 | 49.6004297 | 25.3116596,49.6004297 | KFM2020660216805 | 10006305594 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1081 | الثانوية الأولى بالهفوف مقررات | First Secondary School in Al-Hofuf (Curriculum-Based) | Secondary | Girls | Al Hasa | Al Hasa | 25.3491 | 49.5803 | 25.3491189,49.5802615 | KFM2120660244407 | 10006298776 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1082 | الثانوية الثانية بالهفوف مقررات | Second Secondary School in Al-Hofuf (Curriculum-Based) | Secondary | Girls | Al Hasa | Al Hasa | 25.3931 | 49.5899 | 25.3930975,49.5898547 | KFM2120660255283 | 10006281741 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1083 | الثانوية الثالثة بالهفوف مقررات | Third Secondary School in Al-Hofuf (Curriculum-Based) | Secondary | Girls | Al Hasa | Al Hasa | 25.3631 | 49.6279 | 25.3630725,49.6279005 | KFM2120660239862 | 10006326173 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1084 | ابتدائية مارية القبطية للطفولة المبكرة | Mariya Al-Qibtiya Elementary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3647 | 49.5638 | 25.3646566,49.5638239 | KFM2120660245032 | 10006289329 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1085 | الابتدائية الثامنة بالهفوف للطفولة المبكرة | Eighth Elementary School in Al-Hofuf for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3585 | 49.5707 | 25.3585128,49.5707058 | KFM2120660291568 | 10006330631 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1086 | المتوسطة الثانية بالهفوف | Second Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3803 | 49.5967215 | 25.3802981,49.5967215 | KFM2120660255260 | 10006323995 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1087 | الابتدائية الرابعة عشر بالهفوف للطفولة المبكرة | Fourteenth Elementary School in Al-Hofuf for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3779 | 49.5925 | 25.3778908,49.5924997 | KFM2120660291571 | 10006281554 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1088 | الابتدائية الرابعة بالهفوف للطفولة المبكرة | Fourth Elementary School in Al-Hofuf for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3681 | 49.5905 | 25.3680621,49.590467 | KFM2120660241827 | 10006304971 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1089 | الابتدائية الخامسة بالهفوف | Fifth Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3743 | 49.5998 | 25.374329,49.5998215 | KFM2120660241818 | 10006307552 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1090 | الابتدائية الثانية والثلاثون بالهفوف للطفولة المبكرة | Thirty-Second Elementary School in Al-Hofuf for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.3709 | 49.557 | 25.3708767,49.5570406 | KFM2020660136639 | 10006305530 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1091 | الابتدائية الأربعون بالهفوف | The 40th Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3629 | 49.6277637 | 25.3628949,49.6277637 | KFM2120660244381 | 10006308513 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1092 | الابتدائية العاشرة بالهفوف | The 10th Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3214 | 49.5879 | 25.3214126,49.587878 | KFM2120660244608 | 10006326261 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1093 | المتوسطة الثامنة عشر بالهفوف | The 18th Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3622 | 49.6321 | 25.3622342,49.6320606 | KFM2120660239848 | 10006308531 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1094 | المتوسطة السادسة والعشرون بالهفوف | The 26th Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3544 | 49.6474 | 25.3543996,49.6474203 | KFM2120660239811 | 10101743695 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1095 | المتوسطة الرابعة والعشرون بالهفوف | The 24th Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3665 | 49.5485 | 25.3665428,49.5484931 | KFM2120660244997 | 10006307006 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1096 | المتوسطة الثانية لتحفيظ القرآن بالهفوف | The 2nd Intermediate School for Quran Memorization in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3429 | 49.5548 | 25.3428558,49.5548009 | SMR2220661015244 | 10103013006 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1097 | الثانوية السادسة بالهفوف | The 6th Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3799 | 49.597 | 25.3798546,49.597032 | KFM2120660255258 | 10006323986 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1098 | ثانوية آمنة بنت الارقم | Amina Bint Al-Arqam Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.3102 | 49.586 | 25.3101915,49.586049 | KFM2120660275468 | 10103782001 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1099 | الثانوية السابعة بالهفوف | Seventh Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3358 | 49.5885 | 25.3358021,49.5884908 | KFM2020660228839 | 10006307786 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1100 | الثانوية الثامنة بالهفوف | Eighth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3611 | 49.6087 | 25.3610902,49.6086802 | KFM2120660244527 | 10006323190 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1101 | الثانوية الحادية عشر بالهفوف مقررات | Eleventh Secondary School in Al-Hofuf (Curriculum-Based) | Secondary | Girls | Al Hasa | Al Hasa | 25.359 | 49.6057354 | 25.358977,49.6057354 | KFM2120660240130 | 10006322700 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1102 | الثانوية الثانية عشر بالهفوف | Twelfth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3907 | 49.5981 | 25.3906698,49.5981176 | KFM2120660244992 | 10006305315 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1103 | الثانوية الرابعة عشر بالهفوف | Fourteenth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3477 | 49.5574 | 25.3477005,49.5573832 | KFM2120660240049 | 10006307276 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1104 | الثانوية الخامسة عشر بالهفوف | Fifteenth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3557 | 49.5885 | 25.3556921,49.5885019 | KFM2120660244453 | 10006306054 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1105 | الثانوية السادسة عشر بالهفوف | Sixteenth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3592 | 49.6117 | 25.3592266,49.6117483 | KFM2020660228914 | 10006307122 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1106 | الثانوية السابعة عشر بالهفوف | Seventeenth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3673 | 49.549 | 25.3672999,49.5489625 | KFM2120660245028 | 10006307042 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1107 | المتوسطة الخامسة بالهفوف | Fifth Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3551 | 49.588 | 25.3551444,49.5880265 | KFM2120660244521 | 10006305262 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1108 | جرير الابتدائية بالمبرز | Jarir Elementary School in Al-Mubarraz | Primary | Boys | Al Hasa | Al Hasa | 25.4564 | 49.6115 | 25.4564342,49.611478 | KFM2020660223483 | 10006321767 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1109 | الثانوية السابعة بالمبرز | Seventh Secondary School in Al-Mubarraz | Secondary | Girls | Al Hasa | Al Hasa | 25.4069 | 49.5989 | 25.4069248,49.5988579 | KFM2020660180428 | 10018995873 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1110 | الابتدائية الحادية عشر بالمبرز | Eleventh Elementary School in Al-Mubarraz | Primary | Girls | Al Hasa | Al Hasa | 25.4268 | 49.5786 | 25.4268298,49.578624 | SMR2220661015259 | 10105429034 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1111 | ابتدائية هارون الرشيد طفولة مبكرة | Harun Al-Rashid Elementary School (Early Childhood) | Primary | Girls | Al Hasa | Al Hasa | 23.2593246 | 48.9846839 | 23.2593246,48.9846839 | KFM2020660000963 | 10006307697 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1112 | الابتدائية السادسة عشر بالهفوف | 16th Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3678836 | 49.5812751 | 25.3678836,49.5812751 | KFM2020660223120 | 10006307534 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1113 | الابتدائية السابعة والعشرون بالهفوف | 27th Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3472354 | 49.5694113 | 25.3472354,49.5694113 | KFM2120660239809 | 10006323233 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1114 | الابتدائية الخامسة والأربعون بالهفوف | 45th Elementary School in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3497661 | 49.6049774 | 25.3497661,49.6049774 | KFM2020660226150 | 10006308255 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1115 | الابتدائية السابعة والأربعون بالهفوف للطفولة المبكرة | 47th Elementary School in Al-Hofuf (Early Childhood) | Primary | Girls | Al Hasa | Al Hasa | 25.3497564 | 49.6049559 | 25.3497564,49.6049559 | KFM2120660240696 | 30129136432 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1116 | المتوسطة الثامنة بالهفوف | 8th Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 25.3512398 | 49.5714605 | 25.3512398,49.5714605 | KFM2120660244364 | 10006306564 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1117 | ثانوية أسماء بنت أبي بكر | Asma Bint Abi Bakr Secondary School | Secondary | Girls | Al Hasa | Al Hasa | 25.3901519 | 49.5980787 | 25.3901519,49.5980787 | KFM2020660223118 | 10083173249 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1118 | ابتدائية أم المؤمنين صفية بنت حيي بن أخطب | Umm Al-Mu'minin Safiyya Bint Huyayy Ibn Akhtab Elementary School | Primary | Girls | Al Hasa | Al Hasa | 25.321296 | 49.58697 | 25.321296,49.58697 | KFM2120660255276 | 10006322826 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1119 | المتوسطة الثانية عشر بالهفوف | Twelfth Intermediate School in Al-Hofuf | Intermediate | Girls | Al Hasa | Al Hasa | 23.302372 | 48.972517 | 23.302372,48.972517 | KFM2020660002392 | 10006326235 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1120 | ابتدائية الإمام عاصم (تق) | Imam Asim Elementary School (Taq) | Primary | Boys | Al Hasa | Al Hasa | 24.135791 | 49.054298 | 24.135791,49.054298 | KFM2120660239736 | 10006309118 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1121 | ابتدائية الإمام حمزة الزيات (تق) | Imam Hamza Al-Zayyat Elementary School (Taq) | Primary | Boys | Al Hasa | Al Hasa | 25.3474778 | 49.5683706 | 25.3474778,49.5683706 | KFM2020660005653 | 30091096585 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1122 | ابتدائية وادي طوى | Wadi Tuwa Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.359393 | 49.625625 | 25.359393,49.625625 | KFM2120660244607 | 10083669744 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1123 | إبتدائية أنس بن مالك | ANAS IBN MALIK ELEMENTARY SCHOOL | Primary | Boys | Al Hasa | Al Hasa | 25.349317 | 49.63552 | 25.349317,49.63552 | KFM2120660245008 | 10006290553 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1124 | ابتدائية المروة طفولة مبكرة | Al-Marwa Early Childhood Elementary School | Primary | Girls | Al Hasa | Al Hasa | 25.3748367 | 49.5566869 | 25.3748367,49.5566869 | KFM2120660239795 | 10006322441 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1125 | ابتدائية الإمام الرافعي | Imam Al-Rafi'i Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.3579393 | 49.6361339 | 25.3579393,49.6361339 | KFM2020660223489 | 10006299915 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1126 | ابتدائية عثمان بن عفان | Uthman ibn Affan Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.359339 | 49.574434 | 25.359339,49.574434 | KFM2020660025101 | 10006278915 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1127 | ابتدائية سراقة بن مالك | Suraqa ibn Malik Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.36959 | 49.607566 | 25.36959,49.607566 | KFM2120660241874 | 10006290581 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1128 | ابتدائية سيبويه | Sibawayh Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.36959 | 49.607566 | 25.36959,49.607566 | KFM2020660228837 | 10006322272 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1129 | ابتدائية الإمام الشافعي | Imam Shafi'i Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.388546 | 49.592683 | 25.388546,49.592683 | KFM2120660255380 | 10005902911 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1130 | ابتدائية بلال بن رباح | Bilal ibn Rabah Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.360778 | 49.557327 | 25.360778,49.557327 | KFM2120660241863 | 10006323331 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1131 | ابتدائية زيد بن ثابت | Zayd ibn Thabit Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.353901 | 49.56342 | 25.353901,49.56342 | KFM2120660240033 | 10006306546 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1132 | ابتدائية عبادة بن الصامت بالرقيقة | Ubadah ibn al-Samit Elementary School in al-Ruqayqah | Primary | Boys | Al Hasa | Al Hasa | 25.365464 | 49.570944 | 25.365464,49.570944 | KFM2120660261642 | 10006307374 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1133 | ابتدائية الأمير نايف بن عبدالعزيز | Prince Nayef ibn Abdulaziz Elementary School | Intermediate | Boys | Al Hasa | Al Hasa | 25.346671 | 49.549165 | 25.346671,49.549165 | KFM2120660240071 | 10006307688 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1134 | ابتدائية الملك فيصل | King Faisal Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.360524 | 49.584142 | 25.360524,49.584142 | KFM2120660244441 | 10006291354 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1135 | ثانوية البندرية مقررات | Al-Bandariyah Secondary School (Curriculum-Based) | Secondary | Boys | Al Hasa | Al Hasa | 25.336824 | 49568915 | 25.336824,49568915 | KFM2020660223438 | 10006309038 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1136 | ثانوية الهفوف مقررات | Al-Hofuf Secondary School (Curriculum-Based) | Secondary | Boys | Al Hasa | Al Hasa | 25.365464 | 49.570944 | 25.365464,49.570944 | KFM2120660261637 | 10006307614 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1137 | متوسطة الأمين | Al-Amin Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.35318 | 49.563207 | 25.35318,49.563207 | SMR2420668002762 | 10006280708 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1138 | ثانوية حراء | Hira Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.3583368 | 49.5980465 | 25.3583368,49.5980465 | KFM2120660289170 | 10006291560 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1139 | متوسطة حذيفة بن اليمان | Hudhayfah ibn al-Yaman Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3585113 | 49.6340418 | 25.3585113,49.6340418 | KFM2120660239803 | 10006322138 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1140 | متوسطة الصالحية | Al-Salihiyah Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3706998 | 49.5921081 | 25.3706998,49.5921081 | KFM2020660032373 | 10088516828 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1141 | ابتدائية الشيخ عبدالرحمن السعدي | Sheikh Abdul Rahman al-Saadi Primary School | Primary | Boys | Al Hasa | Al Hasa | 25.352339 | 49.601925 | 25.352339,49.601925 | KFM2120660239715 | 10006308550 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1142 | إبتدائية التقدم للطفولة المبكرة | Al-Taqaddum Early Childhood Primary School |  | Boys | Al Hasa | Al Hasa | 25.3337088 | 49.5860195 | 25.3337088,49.5860195 | KFM2020660226468 | 10006322460 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1143 | متوسطة الإمام نافع لتحفيظ القرآن الكريم | Imam Nafi' Intermediate School for Quran Memorization | Primary | Boys | Al Hasa | Al Hasa | 25.3645657 | 49.574883 | 25.3645657,49.574883 | KFM2020660226496 | 10006322371 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1144 | متوسطة ابن زيدون | Ibn Zaydun Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3595002 | 49.6034646 | 25.3595002,49.6034646 | KFM2120660289173 | 10006305182 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1145 | متوسطة طليطلة | Toledo Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3287147 | 49.6172941 | 25.3287147,49.6172941 | KFM2020660224311 | 10006306967 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1146 | متوسطة البندرية | Al-Bandariyah Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.334549 | 49.577389 | 25.334549,49.577389 | KFM2120660285678 | 10082870779 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1147 | إبتدائية الطموح للطفولة المبكرة | Al-Tumooh Early Childhood Primary School | Primary | Girls | Al Hasa | Al Hasa | 25.3337666 | 49.6081876 | 25.3337666,49.6081876 | KFM2120660271365 | 10018853869 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1148 | ابتدائية الأمير سعود بن عبدالله بن جلوي | Prince Saud bin Abdullah bin Jalawi Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.3468185 | 49.596405 | 25.3468185,49.596405 | KFM2120660240651 | 10006306279 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1149 | متوسطة المأمون | Al-Ma'moun Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.3592433 | 49.6307695 | 25.3592433,49.6307695 | KFM2020660226248 | 10006290698 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1150 | سعد بن عبادة الثانوية بالسلمانية | Saad bin Ubadah Secondary School in Al-Salmaniyah | Secondary | Boys | Al Hasa | Al Hasa | 25.4530594 | 49.6403611 | 25.4530594,49.6403611 | KFM2120660241857 | 10006309136 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1151 | ابتدائية البراء بن عازب بالكلابية | Al-Bara' bin Azib Elementary School in Al-Kulabiyah | Primary | Boys | Al Hasa | Al Hasa | 25.4530594 | 49.6403611 | 25.4530594,49.6403611 | KFM2120660276759 | 10006345849 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1152 | الإمام جعفر الصادق الثانوية مقررات | Imam Ja'far Al-Sadiq Secondary School (Curriculum-Based) | Secondary | Boys | Al Hasa | Al Hasa | 25.361471 | 49.54293 | 25.361471,49.54293 | KFM2120660239717 | 10095576906 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1153 | ابتدائية الحليلة | Al-Halilah Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.610605 | 49.5634782 | 25.610605,49.5634782 | KFM2120660239896 | 10006347450 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1154 | ابتدائية الشعبة | Al-Sha'bah Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4326413 | 49.6269822 | 25.4326413,49.6269822 | KFM2120660240011 | 10006346971 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1155 | ابتدائية البطالية | Al-Bataliyah Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.4692451 | 49.6176508 | 25.4692451,49.6176508 | KFM2120660291602 | 10006321121 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1156 | ابتدائية الإمام الغزالي بالقرين | Imam Al-Ghazali Elementary School in Al-Qurain | Primary | Boys | Al Hasa | Al Hasa | 25.6182767 | 49.5666896 | 25.6182767,49.5666896 | KFM2120660259246 | 10006338291 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1157 | ابتدائية حي النسيم بالعيون | Al-Naseem Elementary School in Al-Uyun | Primary | Boys | Al Hasa | Al Hasa | 25.5982295 | 49.5637847 | 25.5982295,49.5637847 | KFM2020660215801 | 10006339752 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1158 | الابتدائية الاولى بالمطيرفي للطفولة المبكرة | First Elementary School in Al-Mutayrif for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.4806 | 49.558276 | 25.4806,49.558276 | KFM2020660221972 | 10006337909 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1159 | ابتدائية سمرة بن جندب بالشعبة | Samrah bin Jundub Elementary School in Al-Sha'bah | Primary | Boys | Al Hasa | Al Hasa | 25.4367349 | 49.6707451 | 25.4367349,49.6707451 | KFM2120660243701 | 10006352182 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1160 | ثانوية هوازن مقررات بالحليلة | Hawazen Secondary School (Curriculum-Based) in Al-Hulaylah | Secondary | Boys | Al Hasa | Al Hasa | 25.6044275 | 49.5678341 | 25.6044275,49.5678341 | KFM2120660290864 | 10006352825 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1161 | ثانوية الشعبة مقررات | Al-Sha'bah Secondary School (Curriculum-Based) | Secondary | Boys | Al Hasa | Al Hasa | 25.4279418 | 49.6561774 | 25.4279418,49.6561774 | KFM2120660260919 | 10006345947 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1162 | ثانوية أبي فراس الحمداني بالمراح | Abu Firas Al-Hamdani Secondary School in Al-Marah | Secondary | Boys | Al Hasa | Al Hasa | 25.468413 | 49.6257591 | 25.468413,49.6257591 | KFM2020660079441 | 10006341008 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1163 | ثانوية الجرن | Al-Jurn Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.4347777 | 49.6231606 | 25.4347777,49.6231606 | KFM2120660242366 | 10006339805 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1164 | ثانوية القرين | Al-Qurain Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.457351 | 49.611426 | 25.457351,49.611426 | KFM2020660220483 | 10006340083 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1165 | ابتدائية ابن المقرب | Ibn Al-Muqarrab Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.6212259 | 49.5606867 | 25.6212259,49.5606867 | KFM2020660148467 | 10006340495 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1166 | ثانوية ذات الصواري بالكلابية | Dhat Al-Sawari Secondary School in Al-Kulabiyah | Secondary | Boys | Al Hasa | Al Hasa | 25.5986164 | 49.5653219 | 25.5986164,49.5653219 | KFM2120660255182 | 10006353475 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1167 | متوسطة الشعبة | Al-Sha'bah Intermediate School | Intermediate | Boys | Al Hasa | Al Hasa | 25.5068322 | 49.5958954 | 25.5068322,49.5958954 | KFM2120660255151 | 10006364503 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1168 | أبوموسى الأشعري المتوسطة بالشعبة | Abu Musa Al-Ash'ari Intermediate School in Al-Sha'bah | Intermediate | Boys | Al Hasa | Al Hasa | 25.489166 | 49.565415 | 25.489166,49.565415 | KFM2120660239951 | 10006344289 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1169 | المتوسطة الثالثة بالعيون | Al-Ayoun Third Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.594758 | 49.558495 | 25.594758,49.558495 | KFM2020660215782 | 10006339654 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1170 | الابتدائية الاولى بالقرين للطفولة المبكرة | Al-Qurain First Primary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.617029 | 49.563795 | 25.617029,49.563795 | KFM2020660214672 | 10006339126 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1171 | الابتدائية الاولى بالبطالية | Al-Bataliyah First Primary School | Primary | Girls | Al Hasa | Al Hasa | 25.441108 | 49.657605 | 25.441108,49.657605 | KFM2120660279831 | 10006353312 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1172 | المتوسطة الثانية بالبطالية | Al-Bataliyah Second Intermediate School | Primary | Girls | Al Hasa | Al Hasa | 25.431464 | 49.627853 | 25.431464,49.627853 | KFM2120660271359 | 10006353321 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1173 | الابتدائية الاولى بجليجلة | Jalijlah First Primary School | Primary | Girls | Al Hasa | Al Hasa | 25.433045 | 49.626449 | 25.433045,49.626449 | KFM2120660291633 | 10006339162 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1174 | المتوسطة الاولى بالمطيرفي | Al-Mutairfi First Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.437106 | 49.670893 | 25.437106,49.670893 | KFM2020660215623 | 10006340520 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1175 | الابتدائية الاولى بالوزية للطفولة المبكرة | Al-Waziyah First Elementary School for Early Childhood | Intermediate | Girls | Al Hasa | Al Hasa | 25.440756 | 49.651997 | 25.440756,49.651997 | KFM2120660241656 | 10097405579 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1176 | متوسطة الوزية | Al-Waziyah Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.515266 | 49.55542 | 25.515266,49.55542 | SMR2220661009470 | 10105260409 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1177 | الابتدائية الاولى بالشعبة | The First Elementary School in Al-Sha'bah | Primary | Girls | Al Hasa | Al Hasa | 25.515066 | 49.553095 | 25.515066,49.553095 | KFM2020660221878 | 10006352191 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1178 | المتوسطة الاولى بالشعبة | The First Intermediate School in Al-Sha'bah | Intermediate | Girls | Al Hasa | Al Hasa | 25.516046 | 49.548723 | 25.516046,49.548723 | KFM2120660291649 | 10006362385 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1179 | متوسطة تحفيظ القرآن الكريم بالشعبة | The Intermediate School for Quran Memorization in Al-Sha'bah | Intermediate | Girls | Al Hasa | Al Hasa | 25.467887 | 49.616161 | 25.467887,49.616161 | KFM2120660239949 | 10006321300 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1180 | إبتدائية حي سلطانة للطفولة المبكرة بالعيون | The Sultana Neighborhood Elementary School for Early Childhood in Al-Uyun | Primary | Girls | Al Hasa | Al Hasa | 25.4183829 | 49.5759344 | 25.4183829,49.5759344 | KFM2120660291625 | 10087725046 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1181 | الثانوية الثالثة عشر بالهفوف | The Thirteenth Secondary School in Al-Hofuf | Secondary | Girls | Al Hasa | Al Hasa | 25.3097229 | 49.585513 | 25.3097229,49.585513 | KFM2020660224208 | 10006326253 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1182 | الروضة الأولى بالجشة | The First Kindergarten in Al-Jishah |  | Girls | Al Hasa | Al Hasa | 25.3683486 | 49.590538 | 25.3683486,49.590538 | KFM2120660283632 | 10006363177 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1183 | ابتدائية الأفق للطفولة المبكرة | Al-Ufuq Early Childhood Elementary School | Primary | Girls | Al Hasa | Al Hasa | 25.4155388 | 49.7193226 | 25.4155388,49.7193226 | KFM2120660239812 | 10101749474 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1184 | الروضة ملحقة بابتدائية الأفق للطفولة المبكرة | Kindergarten attached to Al-Ufuq Early Childhood Elementary School |  |  | Al Hasa | Al Hasa |  |  | , | [20 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1185 | الإمام علي بن أبي طالب الابتدائية | Imam Ali Bin Abi Talib Elementary School | Primary | Boys | Al Hasa | Al Hasa | 25.3261061 | 49.5726728 | 25.3261061,49.5726728 | KFM2120660291564 | 10006291201 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1186 | الثانوية الاولى بالشعبة | First Secondary School in Al-Sha'bah | Secondary | Girls | Al Hasa | Al Hasa | 25.2620091 | 49.6898416 | 25.2620091,49.6898416 | KFM2120660242282 | 10006339574 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1187 | الروضة الثانية عشر بالمبرز | Twelfth Kindergarten in Al-Mubarraz |  | Girls | Al Hasa | Al Hasa | 25.2620091 | 49.6898416 | 25.2620091,49.6898416 | KFM2120660240511 | 10093583723 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1188 | ثانوية الحليلة بالاحساء | AL HUAILA SECONDARY SCHOON IN ALAHSAA | Secondary | Girls | Al Hasa | Al Hasa | 25.419263 | 49.551057 | 25.419263,49.551057 | KFM2120660239890 | 10006352137 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1189 | الروضة الاولى بالعيون | Al-Uyun First Kindergarten |  | Girls | Al Hasa | Al Hasa | 25.6156067 | 49.5634696 | 25.6156067,49.5634696 | SMR2220661015043 | 10104415188 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1190 | المتوسطة الأولى بالجبيل | Al-Jubail First Intermediate School | Intermediate | Girls | Al Hasa | Al Hasa | 25.9331218 | 48.9638533 | 25.9331218,48.9638533 | SMR2220661009175 | 10105272179 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1191 | الثانوية التاسعة بالمبرز - مقررات | Al-Mubarraz Ninth Secondary School - Curriculum-Based | Secondary | Girls | Al Hasa | Al Hasa | 25.484703 | 49.59878 | 25.484703,49.59878 | SMR2220661015254 | 10105429043 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1192 | الابتدائية الثالثة بالجبيل للطفولة المبكرة | The Third Elementary School in Jubail for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 25.513752 | 49.620446 | 25.513752,49.620446 | SMR2220661009521 | 10105281122 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1193 | إبتدائية الواحة الأولى بالعقار - الساباط | The First Al-Waha Elementary School in Al-Aqar - Al-Sababat | Primary | Girls | Al Hasa | Al Hasa | 25.5308779 | 49.6039859 | 25.5308779,49.6039859 | SMR2220661015186 | 10105293750 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1194 | النايفية الأولى للطفولة المبكرة | The First Al-Naifiyah Elementary School for Early Childhood | Primary | Girls | Al Hasa | Al Hasa | 19.70696 | 53.9621187 | 19.70696,53.9621187 | SMR2220661014861 | 10105417599 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1195 | الابتدائية الثانية لتحفيظ القران الكريم بالهفوف | The Second Elementary School for Quran Memorization in Al-Hofuf | Primary | Girls | Al Hasa | Al Hasa | 25.3399523 | 49.5584052 | 25.3399523,49.5584052 | KFM2120660244399 | 10006279716 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1196 | ابتدائية الإمام الترمذي للطفولة المبكرة | Imam Al-Tirmidhi Elementary School for Early Childhood | Primary | Boys | Al Hasa | Al Hasa | 25.4474792 | 49.5953965 | 25.4474792,49.5953965 | KFM2020660180496 | 10006330828 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1197 | المتوسطة الاولى بجليجلة | First Intermediate School in Jalijah | Intermediate | Girls | Al Hasa | Al Hasa | 25.505995 | 49.601099 | 25.505995,49.601099 | KFM2120655003712 | 10006337945 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1198 | ثانوية الحرمين | Al-Haramain Secondary School | Secondary | Boys | Al Hasa | Al Hasa | 25.36443 | 49.5780641 | 25.36443,49.5780641 | KFM2120660285671 | 10006330541 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1199 | متوسطة الفاضلية | Al-Fadhiliyah Intermediate School | Primary | Boys | Al Hasa | Al Hasa | 49.59875 | 25.38302 | 49.59875,25.38302 | KFM2120660255261 | 10006291372 | [18 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-HASA1200 | متوسطة دار الهجرة | Dar Al-Hijrah Intermediate School | Secondary | Boys | Al Hasa | Al Hasa | 25.359985 | 49.630952 | 25.359985,49.630952 | KFM2120660239845 | 10006323341 | [18 empty] | 0 | 0 | 0 | Not Started
Total | [9 empty] | , |  |  | Total | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on N4: 4/2/2025
Note on O4: 4/2/2025

## Riyadh Schools -3
|  | Report Date | 2026-05-10
Project | Schools Information | [10 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | Schools Coordinates | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Riyadh- 3 | SS-ZAM-RYD1001 | مدرسة ابتدائية تحفيظ الخماسين | Ibtday Tahfez alquraan | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.467917724519168, 44.78055045396983 | KFM2020660234422 | 10041399860 | 23/02/2026 10:32:35 | [17 empty] | 0 | 0 | 0 | Not Started | Primary | Boys | Not Started
| SS-ZAM-RYD1002 | ابتدائية العقيق | Ibtday alaqeq | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.47128927450877, 44.7825351804188 | Kfm2020660212684 | 10041343621 | 23/02/2026 12:43:49 | [17 empty] | 0 | 0 | 0 | Not Started | Intermediate | Girls | In Progress
| SS-ZAM-RYD1003 | ابتدائية الإمام أحمد بن حنبل | Alamam Ahmed ibn hanbal | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.459649353412384, 44.81541427301509 | Kfm2020660174648 | 100416.233 | 26/02/2026 00:25:45 | [17 empty] | 0 | 0 | 0 | Not Started | Secondary | NA | Completed
| SS-ZAM-RYD1004 | ثانوية مجمع الأمير سلطان التعليمي - مسارات | mujmae al'amir sultan altaelimi, alqism althaanawia | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.466240200359696, 44.80167415952262 | Kfm2020660177804 | 10041765943 | 26/02/2026 01:53:41 | [17 empty] | 0 | 0 | 0 | Not Started | NA |  | NA
| SS-ZAM-RYD1005 | ابتدائية مجمع الأمير سلطان التعليمي | mujamae al'amir sultan altaelimi, alqism aliabtidayiyi | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.466220097129767, 44.801749261373544 | Kfm2020660177808 | 10041765818 | 26/02/2026 02:08:16 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1006 | ابتدائية علي بن أبي طالب | Ali ibn Abi Talib Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.47458527256921, 44.794443400000006 | Kfm2020660176051 | 10093027816 | 26/02/2026 02:24:15 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1007 | ثانوية المعتلى - مسارات | Thanawia almaatla | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.447525775578374, 44.82571510185094 | Kfm2020660172286 | 10041668851 | 26/02/2026 02:51:35 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1008 | ابتدائية الإمام الترمذي | Imam al trmidhi pramary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.452444980888604, 44.81890792698492 | Kfm202660193437 | 10041961195 | 26/02/2026 03:28:26 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1009 | ابتدائية أبوهريرة | Abu hrira | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.454870709168464, 44.78294137486601 | Kfm2020660212694 | 10042000892 | 26/02/2026 03:53:52 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1010 | ابتدائية الأندلس | Alandlus elementary | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.46101762352187, 44.78288805952263 | KFM2020660212756 | 10041681708 | 26/02/2026 04:34:23 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1011 | ابتدائية قرطبة | Qurtba elementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.471476330703947, 44.769193217194314 | Kfm2020660177875 | 10041821087 | 26/02/2026 04:44:53 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1012 | ابتدائية ابن القيم | Ibn alqaim | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.46498090679228, 44.77909786137357 | KFM2020660212760 | 10041343327 | 26/02/2026 05:04:30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1013 | متوسطة أحد | Ahud middle school | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.46615863579147, 44.78602333068678 | KFM2020660206216 | 10041337929 | 26/02/2026 06:52:12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1014 | متوسطة الخماسين | Khamasin middle school | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.472002076122163, 44.77719110185093 | Kfm2020660206106 | 10041694261 | 26/02/2026 14:19:42 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1015 | ثانوية الخماسين - مقررات | Khmasin High School | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.471738620152326, 44.77830770185092 | Kfm2020660206103 | 10041497280 | 26/02/2026 14:41:27 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1016 | ابتدائية الملك فيصل | King Faisal elementary | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.46707667032961, 44.79436241904525 | Kfm2020660212758 | 10041660351 | 2026-03-06 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1017 | ثانوية الولامين - مسارات | Al-walamin secondary | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.475008367776816, 44.77439945582076 | Kfm2020660174651 | 10041634754 | 2026-03-07 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1018 | متوسطة الفرعة | Al faraa middle school | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.484855758438883, 44.76778718835847 | Kfm2020660174726 | 10041630094 | 2026-03-08 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1019 | ثانوية الشيخ محمد بن عثيمين مقررات | Sheikh Mohammad bin othimeen | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.484622406647954, 44.76547493068679 | Kfm2020660177891 | 10095262726 | 2026-03-09 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1020 | ابتدائية القادسية | Alqadisiyah elementary | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.493710495065802, 44.75110800185093 | Kfm2020660174723 | 10041425487 | 2026-03-10 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1021 | ابتدائية الولامين | Walami elementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.480007763658154, 44.7761833693132 | Kfm2020660174678 | 10041292184 | 2026-03-11 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1022 | ابتدائية طويق | Tuwaiq elementary | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.433726197501556, 44.84347627301507 | Kfm2020660223668 | 10041694485 | 2026-03-12 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1023 | ابتدائية الصالحية | Alsalihia elementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.442057551232153, 44.851526319045256 | Kfm2020660247637 | 10041304392 | 2026-03-14 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1024 | ابتدائية النويعمة | Alnuwayimah elementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.44976341752288, 44.85445261534338 | Kfm2020660174714 | 10041252877 | 2026-03-15 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1025 | مدرسة ثانوية النويعمة للمقررات | Alnuwayimah secondary school | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.456629597256686, 44.856285888358464 | Kfm2020660206090 | 10041182020 | 2026-03-16 14:41 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1026 | مدرسة ابتدائية تحفيظ النويعمة | Alnuwayimah elementary tahfez al quran | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.44952727608582, 44.858778417194316 | Kfm2020660234471 | 10041497931 | 2026-04-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1027 | ابتدائية الملك سعود | King saud elementary and middle school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.440120039928825, 44.876970319045256 | Kfm2020660174694 | 10041862830 | 2026-04-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1028 | مدرسة عمرو بن العاص الثانوية - مسارات | Amr ibn alas secondary school | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.438537608352895, 44.90064157116415 | Kfm2020660174691 | 10041735318 | 2026-04-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1029 | ابتدائية الزويراء | Alzuwaira elementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.46415605636114, 44.8312998 | Kfm2020660177856 | 10041758831 | 2026-04-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1030 | ابتدائية القويز | AIquwaiz eiementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.454189353027445, 44.84741184603016 | KFM2020660174662 | 10041291768 | 2026-04-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1031 | ثانوية كمدة - مقررات | Kamdah high school | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.387811780926334, 45.0834741 | KFM2020660177865 | 10041924262 | 2026-04-07 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1032 | مدرسة المعتلا الابتدائية | Almaatla elementary school | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.448467502890725, 44.82579652883585 | Kfm2020660177978 | 10041251913 | 2026-04-07 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1033 | مدرسة ام سلمة بنت أبي أمية للطفولة المبكرة | umm salamah bint abi umayyah early childhood school | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.467416696350497, 45.56761865355024 | KFM2020660206011 | 10041924843 | 2026-04-07 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1034 | ابتدائية ومتوسطة وثانوية اًل ضويان | Al-Dhuwayan Primary, Intermediate and Secondary Schools | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.467416696350497, 45.56761865355024 | KFM2120660271395 | 10041473930 | 2026-04-07 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1035 | مدرسة الخماسين الرابعة الابتدائية للطفولة المبكرة | AL-KHAMASIN FOURTH ELEMENTARY SCHOOL | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.46383302587874, 44.77661308172574 | KFM2020660176032 | 10041260977 | 2026-04-07 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1036 | مدرسة الخماسين الأولى الثانوية | Al-Khamaseen First Secondary School | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.464097584729256, 44.776051791963944 | KFM2020660176031 | 10109290971 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1037 | ابتدائية الولامين الثانية للطفولة المبكرة | Al-Walamin Second Primary School for Early Childhood | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.45948438822131, 44.756335831031784 | KFM2120660249024 | 10041916421 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1038 | ثانوية اللدام الاولى | Al-Ladaam First Secondary School | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.46735320770259, 44.79582074308425 | KFM2020660206079 | 10041277114 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1039 | ابتدائية ومتوسطة نزوى | Nizwa Primary and Intermediate School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.458018867215284, 44.85683806481024 | kfm2020660206084 | 10041528751 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1040 | ابتدائية اللدام الرابعة و متوسطة اللدام الثالثة | Al-Ladam Fourth Primary School and Al-Ladam Third Intermediate School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.474105035684065, 44.79798679933438 | KFM2020660176055 |  | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1041 | ابتدائية الصالحية | Al-Salihia Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.443425525662878, 44.848424801375884 | kfm2020660212697 | 10041284404 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1042 | مدرسة ابتدائية تحفيظ المعتلا للطفولة المبكرة | Al-Mu'tala Primary School for Early Childhood Memorization | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.447932704463593, 44.8223451895018 | kfm2020660212722 | 10041694369 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1043 | مدرسة متوسطة و ثانوية القويز | Al-Quwaiz Intermediate and Secondary School | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.454896807140553, 44.84806069134327 | kfm2020660174669 | 10041822665 | 2026-04-08 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1044 | مدرسة ابتدائية موسى بن النصير | Musa Bin Nusair Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.505029883407786, 44.73411135952363 | kfm2020660174789 | 10041649532 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1045 | ثانوية بدر مقررات | Badr Secondary School (Curriculum) | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.467416696350497, 45.56761865355024 | KFM2020660206214 | 10042000570 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1046 | مدرسه الشرافاء الابتدائيه | Al-Shurafa Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.43753445155977, 44.898104597618214 | KFM2020660205957 | 10041303770 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1047 | مدرسه الشرافا الثانيه الابتدائيه للطفوله المبكره | Al-Shurafa Second Primary School for Early Childhood | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.435384219147906, 44.89168063068768 | KFM2020660174718 | 10041862348 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1048 | مدرسه الشرافاء الاوله الثانويه | Al-Shurafa First Secondary School | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.435930847368837, 44.891764599999995 | kfm2020660174711 | 10041682537 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1049 | مدرسة الفرعة الثانيه الابتدائية | Al-Fara'a Second Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.492959897162194, 44.74493507301576 | KFM2020660174682 | 10084436193 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1050 | مدرسه الفرعه الرابعه الابتدائيه | Al-Fara'a Elementary School No. 4 | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.49646794105015, 44.739060488359605 | KFM2020660206232 | 10041712574 | 2026-04-09 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1051 | مدرسه متوسطه وثانويه كمده | Kamda Middle and High School | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.38935975960722, 45.080318718835954 | KFM2120660247696 | 10041638431 | 2026-04-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1052 | مدرسه ابتدائيه المعتلا | Al-Mu'tala Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.448499002851577, 44.822663376719206 | KFM2020660212723 | 10041856968 | 2026-04-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1053 | ابتدائية الفرعه الاولي | Al-Far'ah First Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.481021653239075, 44.763788566930536 | kfm2020660177892 | 10041901544 | 2026-04-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1054 | متوسطة الفرعة الاولي | Al-Fara'a Al-Oula Intermediate School | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.481025557144868, 44.762797626984245 | KFM2020660177893 | 10041507091 | 2026-04-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1055 | مدرسة مقابل الابتدائية للطفولة المبكرة | School muqabil the primary school for early childhood | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.460242922540257, 44.81639091788483 | KFM2020660174604 | 10041713778 | 2026-04-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1056 | مدرسة متوسطة وثانوية الولامين | Al-Walamin Intermediate and Secondary School | /متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.4600769560206, 44.81635417378103 | kfm2020660205984 | 10041805271 | 2026-04-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1057 | مدرسة الولامين الاولى الابتدائية | Al-Walamin First Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.48127560632821, 44.77526968465616 | KFM2020660206128 | 10041394193 | 2026-04-13 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1058 | مدرسة الزويراء الابتدائية | Al-Zuwaira Primary School | المرحلة الدراسية | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.45981756877918, 44.83472231 | KFM2120660292715 | 10103861384 | 2026-04-13 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1059 | مدرسة حفصة بنت عمر بن الخطاب الابتدائية للطفولة المبكرة | Hafsa Bint Omar Bin Al-Khattab Primary School for Early Childhood | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.426420196449424, 44.709122515343836 | kfm2020660205979 | 10041924521 | 2026-04-14 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1060 | مدرسة الفرعة الثالثة الابتدائية | Al-Fara'a Third Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.486409256300963, 44.77379725343842 | kfm2020660206126 | 10041817001 | 2026-04-14 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1061 | ابتدائية السليل لتحفيظ القرآن الكريم | Al-Salil Primary School forTahfez alquraan | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.46545907170644, 45.5800548558202 | kfm2120660263530 | 10041460655 | 2026-04-15 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1062 | روضة السليل الثالثه | Rawdat Al-Salil Third | Kindergarten | girls | Riyadh region/ منطقة الرياض | Riyadh | 20.47540701835841, 45.59231984047636 | kfm2120660271538 | 10041997877 | 2026-04-15 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1063 | مدرسة حطين المتوسطه | Hattin Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.453505800000002, 45.58566438650788 | KFM2120660271433 | 10041706586 | 2026-04-15 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1064 | مدرسة حمزة بن عبد المطلب الابتدائية | Hamza Bin Abdul Muttalib Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.47933879975774, 45.58793518073971 | KFM2120660271490 | 10092726222 | 2026-04-15 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1065 | مدرسة سعد بن ابي وقاص الابتدائية | Saad Bin Abi Waqqas Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.464172326670415, 45.59263133766172 | KFM2120660271520 | 10041706666 | 2026-04-18 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1066 | مدرسة السليل الثانويه | Al-Salil Secondary School | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.457447626325866, 45.58139991534338 | KFM2120660263529 | 10041488951 | 2026-04-18 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1067 | مدرسة خالد بن الوليد الابتدائية | Khalid Bin Al-Walid Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.454381547942084, 45.57928835767169 | KFM2120660271397 | 10041300553 | 2026-04-18 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1068 | مدرسة ابن كثير الابتدائية لتحفيظ القران | Ibn Kathir Primary School tahfiz alquran | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Riyadh | 20.449911849717385, 45.58487931584191 | KFM2120660271427 | 10041632876 | 2026-04-18 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1069 | ثانوية ابن تيميه | Ibn Taymiyyah High School | ثانوية/High school | بنين/Boys | ثانوية/High school | Al-Salil | 20.462291722521044, 45.55960871534339 | KFM2120660271452 | 10041632750 | 2026-04-19 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1070 | مدرسه خيران الابتدائية | Khairan Primary School | ابتدائية/Elementary | بنين/Boys | ابتدائية/Elementary | Al-Salil | 20.405882755769593, 45.43111578835848 | closed Available |  | 2026-04-19 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1071 | مدرسه متوسطة خيران | Khairan Intermediate School | متوسطة/middle school | بنين/Boys | متوسطة/middle school | Al-Salil | 20.402344771767442, 45.42810802883584 | KFM2120660273202 | 10082285483 | 2026-04-19 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1072 | مدرسة تمره الابتدائية | Tamra Elementary School | ابتدائية/Elementary | بنين/Boys | ابتدائية/Elementary | Al-Salil | 20.398098397183624, 45.41464247301508 | Kfm2020660174723 | 10041304392 | 2026-04-19 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1073 | مدرسة عمر بن الخطاب الابتدائيه | Omar Bin Al-Khattab Elementary School | ابتدائية/Elementary | بنين/Boys | ابتدائية/Elementary | Al-Salil | 20.471443615330294, 45.56961773068678 | KFM2120660271403 | 10041300689 | 2026-04-20 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1074 | مدرسة عبد العزيز بن باز الثانويه | Abdul Aziz Bin Baz Secondary School | ثانوية/High school | بنين/Boys | ثانوية/High school | Al-Salil | 20.40030348301157, 45.41863386137356 | kfm2120660263501 | 10041318431 | 2026-04-20 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1075 | مدرسة ابتدائيه تمرة لتحفيظ القران الكريم | Tamra Elementary School for Quran Memorization | ابتدائية/Elementary | بنين/Boys | ابتدائية/Elementary | Al-Salil | 20.397555397750654, 45.413909617194314 | kfm2120660292701 | 10041961462 | 2026-04-20 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1076 | مدرسة السليل المتوسطة | Al-Salil Intermediate School | متوسطة/middle school | بنين/Boys | متوسطة/middle school | Al-Salil | 20.464148913369407, 45.58612135582076 | kfm2120660270776 | 10041780467 | 2026-04-21 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1077 | مدرسة ابتدائية ال حجي | Al Hajji Elementary School | ابتدائية/Elementary | girls | ابتدائية/Elementary | Al-Salil | 20.463112232850253, 45.56558062513399 | KFM2120660271389 | 10041940121 | 2026-04-21 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1078 | المدرسة الابتدائية الثانيه بال حنيش | Second Elementary School in Al-Hanish | ابتدائية/Elementary | girls | ابتدائية/Elementary | Al-Salil | 20.451253709863348, 45.58195658465661 | SMR2220661018222 | 10041941970 | 2026-04-21 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1079 | مدرسة متوسطة وثانويه السليل | Al-Salil Intermediate and Secondary School | متوسطة/middle school | girls | متوسطة/middle school | Al-Salil |  | KFM2120660271511 | 10041919754 | 2026-04-21 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1080 | مدرسة ابتدائية و متوسطة خيران | Khairan Elementary and Intermediate School | ابتدائية/Elementary | girls | ابتدائية/Elementary | Al-Salil | 20.414642524902074, 45.43937401534338 | kfm2120660263417 | 10041817404 | 2026-04-21 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1081 | مدرسة تمره الثانوية - مسارات | Tamrah Secondary School - Pathways | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Al-Salil | 20.392369416072754, 45.41021265582076 | KFM2120660263500 | 10041619481 | 2026-04-22 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1082 | مدرسة السليل الاولى للمقررات الثانوية | Al-Salil First Secondary School | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Al-Salil | 20.459831708140598, 45.58945399999999 | KFM2120660263528 | 10041148396 | 2026-04-22 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1083 | روضة الشفاء الأولى | First alshifa Kindergarten | Kindergarten | girls | Riyadh region/ منطقة الرياض | Al-Salil | 20.473251141929765, 45.584267519045255 | kfm2120660271500 | 10041940391 | 2026-04-22 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1084 | مدرسة ابتدائية تحفيظ القران الأولى بالسليل | The first Quran memorization primary school in Al-Sulayyil | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Salil | 20.469790233353983, 45.59163695582075 | KFM2120660271501 | 10041937028 | 2026-04-23 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1085 | ابتدائية الشيخ عبدالعزيز بن باز | Sheikh Abdulaziz bin Baz Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.297312705795765, 46.72825872883586 | KFM2020660170992 | 10041398361 | 2026-04-25 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1086 | متوسطة الخالدية | Al-Khalidiyah Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.312397494404514, 46.72492052698491 | KFM2020660213365 | 10084379471 | 2026-04-25 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1087 | ثانوية الملك فهد - مسارات | King Fahd High School - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.29954410278351, 46.719739844179244 | KFM2020660165143 | 10041719047 | 2026-04-25 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1088 | ابتدائية طارق بن زياد | Tariq Bin Ziyad Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.28938602717755, 46.71164863253772 | KFM2020660170205 | 10041601332 | 2026-04-26 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1089 | متوسطة أحد | Uhud Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.300293890468126, 46.711624901850946 | KFM2020660170945 | 10041724001 | 2026-04-26 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1090 | الثانوية الثانية بليلى - مسارات | Second Secondary School in Layla - Pathways | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.291957815978815, 46.71947229206034 | KFM2020660165141 | 10041042351 | 2026-04-26 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1091 | ابتدائية الأولى بليلى | First Elementary School in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.29146714890829, 46.71922154603016 | KFM2020660170240 | 10041694752 | 2026-04-26 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1092 | متوسطة الثالثة بليلى | Third Intermediate School in Layla | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.29531385495619, 46.72008995952262 | kfm2020660165142 | 10041869591 | 2026-04-26 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1093 | ابتدائية ابن كثير لتحفيظ القرآن بليلى | Ibn Kathir Primary School for Quran Memorization in Layla | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.311074207684467, 46.70327841719431 | kfm2020660176158 | 10041919567 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1094 | ابتدائية علي بن أبي طالب | Ali Bin Abi Talib Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.312642282949348, 46.69692596137355 | KFM2020660165116 | 10042008522 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1095 | ثانوية الملك عبدالله بن عبدالعزيز - مسارات | King Abdullah Bin Abdulaziz High School - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.303215559942952, 46.70405968835847 | KFM2020660169742 | 10084838073 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1096 | ثانوية ليلى - مسارات | Layla Secondary School - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.28250464367827, 46.72623480185093 | KFM2020660166849 | 10041396447 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1097 | الابتدائية الخامسه ليلي | Fifth Elementary School in Layli | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.295738547497127, 46.72727714603017 | KFM2020660165193 | 10041697404 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1098 | ابتدائية الرابعة بليلى | Fourth Elementary School in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.287351845923514, 46.72459679814906 | kfm2020660170198 | 10041285054 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1099 | الثانوية الأولى بليلى - مسارات | First Secondary School in Layla - Pathways | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.310308162545006, 46.70818936931322 | smr2320661030891 | 10087431806 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1100 | متوسطة الرابعة بليلى | Fourth Intermediate School in Layla | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.308460813240853, 46.707806973015074 | kfm2020660176153 | 10041944372 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1101 | متوسطة الفيصلية | Al-Faisaliah Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.27344779123905, 46.713923519581186 | kfm2020660213343 | 10042001559 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1102 | ابتدائية أحمد بن حنبل | Ahmad Ibn Hanbal Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.297677126975056, 46.73043102320697 | kfm2020660165189 | 10041607087 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1103 | ابتدائية خالد بن الوليد | Khalid Bin Al-Walid Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.29544970699159, 46.71813726322449 | kfm2020660165158 | 10041412925 | 2026-04-28 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1104 | ابتدائية تحفيظ القرآن الأولى بليلى | First Quran Memorization Primary School in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.299058050434034, 46.7162573423283 | kfm2020660170104 | 10041314808 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1105 | ابتدائية الثامنة بليلى | Eighth Elementary School in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.299463142621708, 46.71668578048688 | kfm2020660170101 | 10041998721 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1106 | متوسطة الثانية بليلى | Second Intermediate School in Layla | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.293103294443164, 46.7099872406559 | kfm2020660170107 | 10041601584 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1107 | متوسطة الأولى بليلى | First Intermediate School in Layla | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.301892894409736, 46.706814028835836 | kfm2020660176127 | 10086062181 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1108 | ابتدائية تحفيظ القرآن الكريم الثانية بليلى | Second Primary School for Quran Memorization in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.3035815402526, 46.7083249423283 | kfm2020660213347 | 10103251026 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1109 | ابتدائية السابعة بليلى | Seventh Elementary School in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.29295093862082, 46.70520431534339 | kfm2020660170208 | 10041162813 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1110 | ابتدائية عثمان بن عفان | Othman Bin Affan Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.048522597793454, 46.59186367116414 | kfm2020660211803 | 10041744424 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1111 | متوسطة حطين | Hattin Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.02311681975984, 46.574367940477366 | kfm2020660213361 | 10041868092 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1112 | ابتدائية أبوبكر الصديق | Abu Bakr Al-Siddiq Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.027704939291862, 46.56095769999999 | kfm2020660213428 | 10041754467 | 2026-04-30 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1113 | ثانوية البديع - مسارات | Al-Badi' Secondary School - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.026098383092158, 46.55820218465662 | kfm2020660211844 | 10041148430 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1114 | ابتدائية الثانية بالبديع الشمالي | Second Elementary School in Al-Badi' Al-Shamali | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.019765255626364, 46.5808651423283 | kfm2020660211808 | 10041744273 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1115 | ابتدائية الأولى بالبديع | Al-Badi'a First Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.025811848956014, 46.5548517423283 | KFM2020660213424 | 10041866481 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1116 | ثانوية البديع - مقررات | Al-Badi' Secondary School - Curriculum | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.025581866485645, 46.55420865582076 | kfm2020660211842 | 10041303395 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1117 | ابتدائية السادسة بليلى | Sixth Elementary School in Layla | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.29361852592434, 46.710325913492454 | kfm2020660169743 | 10041521349 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1118 | ابتدائية الثالثة بالبديع الشمالي | Third Elementary School in Al-Badi' Al-Shamali | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.047223330190675, 46.58788418465661 | kfm2020660211802 | 10041846738 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1119 | مدرسة عبد الله بن مسعود الابتدائية | Abdullah Bin Masoud Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Al-Aflaj | 22.220618880889916, 46.773252299999996 | kfm2020660177814 | 10041402179 | 2026-05-03 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1120 | مدرسة الابتدائية زيد بن ثابت | Zaid Bin Thabit Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.49686192763482, 46.8819748576717 | KFM2020660169777 | 10041659047 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1121 | متوسطة تحفيظ القرآن بحوطة بني تميم | Intermediate Quran Memorization School in Hawtat Bani Tamim | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.501478588832736, 46.88955212698491 | KFM2020660108315 | 10041635500 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1122 | ثانوية ابن باز (بنين) - مسارات | Ibn Baz High School (Boys) - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.490386375085805, 46.87713591349245 | SMR2420661040688 | 10041498911 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1123 | ابتدائية ابن القيم | Ibn Al-Qayyim Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.489235256154018, 46.8747672576717 | KFM2020660213798 | 10041477895 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1124 | متوسطة ابن تيمية | Ibn Taymiyyah Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.49254499101818, 46.87125215767169 | KFM2020660200906 | 10041941316 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1125 | المدرسة الابتدائية الاولي والمدرسة المتوسطة الاولي | The first primary school and the first intermediate school | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 22.234112535444222, 46.78284372883584 | KFM2020660177812 | 10041042501 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1126 | الابتدائية الحادية عشرة | Eleventh Elementary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.502746669777242, 46.88758876931322 | KFM2020660169773 | 10041789382 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1127 | المتوسطة الرابعة بالحوطة | Fourth Intermediate School in Al-Hawta | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.48257638803067, 46.87362504232829 | KFM2120660270888 | 10083698620 | 2026-05-04 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1128 | مدرسة الحوطه الاولي | Al-Houta First School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.49248577242187, 46.85442525767169 | KFM2020660205789 | 10041199475 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1129 | ابتدائية تحفيظ القران الكريم بحوطة بني تميم | Primary School for Memorizing the Holy Quran in Hawtat Bani Tamim | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.492999529864296, 46.85471781534338 | MMF2320601005250 | 10041435699 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1130 | ثانوية حوطة بني تميم (بنين) - مسارات | Hawtat Bani Tamim Secondary School (Boys) - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.49551340791454, 46.851703184656614 | KFM2020660213894 | 10041199878 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1131 | ابتدائية زياد | Ziad Elementary School | ابتدائية/Elementary | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.506201277941376, 46.83715858465661 | KFM2020660195488 | 10041674956 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1132 | مدرسة الثالثه عشر بنات | Thirteenth Girls' School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.48423958201387, 46.874526957671705 | KFM2020660205836 | 10041611544 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1133 | مدرسة الابتدائية الاولي | First Primary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.496998455124185, 46.852604379778164 | KFM2020660213784 | 10041292461 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1134 | ابتدائية التحفيظ الاولي بحوطة بني تميم | Primary Quran Memorization School in Hawtat Bani Tamim | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.496706602550898, 46.85289137301508 | KFM2020660213783 | 10089461546 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1135 | المدرسة الابتدائية الثامنة | Eighth Elementary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.493058844517947, 46.88363807584533 | KFM2020660169760 | 10041707691 | 2026-05-05 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1136 | الطفولة المبكرة بالروضة الثامنة | Early childhood at the eighth kindergarten | Kindergarten | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.493223806088963, 46.88414602698492 | KFM2020660169758 | 10097255918 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1137 | الابتدائية الثانية عشرة | Twelfth Elementary School | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.49369719194597, 46.86886297116415 | KFM2020660200904 | 10041778235 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1138 | ثانوية الحلوة (بنين) - مسارات | Al-Hilwa Secondary School (Boys) - Pathways | ثانوية/High school | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.44694683015593, 46.80374263068677 | KFM2020660234497 | 10041970532 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1139 | متوسطة الحلوة | Al-Hilwa Intermediate School | متوسطة/middle school | بنين/Boys | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.43742740421875, 46.77538718650753 | KFM2020660193216 | 10097257322 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1140 | متوسط الحلوه بنات | Al-Hilwa Intermediate School for Girls | متوسطة/middle school | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.4443826923025, 46.8016645846566 | SMR2420661040564 | 10041849346 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1141 | الابتدائية التاسعة بالحلوة | The Ninth Elementary School in Al-Hilwa | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.450726410719607, 46.80580928650754 | KFM2020660230810 | 10041657230 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1142 | الابتدائية الرابعة بالحلوة | Fourth Elementary School in Al-Hilwa | ابتدائية/Elementary | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.432955715879668, 46.78852816746229 | KFM2020660172219 | 10041801011 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1143 | ثانوية الحلوة (بنات) - مسارات | Al-Hilwa Secondary School (Girls) - Tracks | ثانوية/High school | girls | Riyadh region/ منطقة الرياض | Hawtat Bani Tamim | 23.452065510362136, 46.80266370834573 | KFM2020660232738 | 10041654416 | 2026-05-06 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1144 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1145 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1146 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1147 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1148 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1149 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1150 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1151 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1152 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1153 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1154 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1155 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1156 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1157 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1158 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1159 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1160 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1161 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1162 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1163 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1164 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1165 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1166 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1167 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1168 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1169 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1170 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1171 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1172 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1173 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1174 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1175 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1176 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1177 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1178 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1179 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1180 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1181 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1182 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1183 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1184 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1185 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1186 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1187 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1188 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1189 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1190 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1191 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1192 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1193 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1194 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1195 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1196 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1197 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1198 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1199 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-RYD1200 | [27 empty] | 0 | 0 | 0 | Not Started
Total | [28 empty] | 0 | 0 | 0 | 0
Note on L4: 4/2/2025
Note on M4: 4/2/2025

## Makkah Schools -2
|  | Report Date | 2026-04-12
Project | Schools Information | [10 empty] | Installation Start date | Mechanical |  |  |  | Electrcical | [8 empty] | Energized | COC signed | Installation Completion Date | Not Started | In Progress | Completed | School Status
| School ID | School Name (Arabic) | School Name (English) | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Region | City | School Coordination | SEC Meter NO. | SEC Account NO. | Survey Completion Date |  | Completion of Foundation | PV Mounting Structure | PV Module Installation | Completion for Earthing | Cable Tray Installation | Extension DC Cables | Completion of LV AC Cables | Inverters Installation | SMDB panel installation | Data Logger installation | DIGITAL METER | Breaker | C T | [7 empty] | School Level (Primary / Intermediate / Secondary) | School Gender (Boys / Girls) | Stage
Makkah-2 | SS-ZAM-MAK-2-1001 | صقر الجزيرة - مسارات | Saqr Al-Jazira - Masarat |  | B | Makkah Region | Makkah | 21.45136846603668, 39.53979894964285 | HLY2020627009766 | 10053680901 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started | Primary | Boys | Not Started
| SS-ZAM-MAK-2-1002 | عبدالملك بن مروان المتوسطة | Abdul Malik bin Marwan Intermediate School |  | B | Makkah Region | Makkah | 21.46763901326242, 39.95535222491324 | SXE2020627069715 | 10053403080 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started | Intermediate | Girls | In Progress
| SS-ZAM-MAK-2-1003 | قباء الثانوية | Quba High School |  | B | Makkah Region | Makkah | 21.551074918360477, 39.78280928271348 | SXE202062700152 | 10053376376 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started | Secondary | NA | Completed
| SS-ZAM-MAK-2-1004 | القاسم بن محمد الثانوية | Al-Qasim bin Mohammed High School |  | B | Makkah Region | Makkah | 21.400430376245765, 39.778217185566774 | KFM2120655995662 | 10105126018 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started | NA |  | NA
| SS-ZAM-MAK-2-1005 | مدرسة قرطبة الثانوية | Cordoba High School |  | B | Makkah Region | Makkah | 21.608913866965437, 39.69461653121545 | HLY2020627055320 | 10053617390 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1006 | عبد الله لن عمر المتوسطة | Abdullah bin Umar Intermediate School |  | B | Makkah Region | Makkah | 21.449758167976338, 39.822188393065574 | SXE2020627072939 | 10053328351 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1007 | الامام الذهبي المتوسطة | Imam Al-Dhahabi Intermediate School |  | B | Makkah Region | Makkah | 21.453139119485215, 39.96939791409704 | SXE2020627073168 | 10096127495 | 2025-12-11 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1008 | الحذيفات الابتدائية | Al-Hudhaifat Primary School |  | B | Makkah Region | Makkah | 21.411404462537096, 39.41049598477201 | HLY2020627012391 | 10053495143 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1009 | مدرسة ثانوية القيروان بمكة | Al-Qayrawan High School in Mecca |  | B | Makkah Region | Makkah | 21.46457377638942, 39.94816208571467 | LYE2020800096887 | 10053397625 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1010 | يزيد بن رومان القارىء المتوسطة لتحفيظ القرآن الكريم | Yazid bin Roman Al-Qari' Intermediate School for Quran Memorization |  | B | Makkah Region | Makkah | 21.468319194739443, 39.9553942923763 | LYE2020809717527 | 30130653406 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1011 | الخوارزمي الابتدائية | Al-Khwarizmi Primary School |  | B | Makkah Region | Makkah | 21.62719268178675, 39.67903118789279 | HLY2020627055234 | 1005344721 | 13-11-2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1012 | ابن رشد الثانوية - مسارات | Ibn Rushd High School - Masarat |  | B | Makkah Region | Makkah | 21.389707013726465, 39.44136567785869 | SMR2420628005442 | 10053563280 | 13-11-2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1013 | ابن قتيبة الابتدائية | Ibn Qutaiba Primary School |  | B | Makkah Region | Makkah | 21.462310509848948, 39.96310306570355 | SMR2420628005661 | 10105780481 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1014 | الإمام الشافعي الابتدائية | Imam Al-Shafi'i Primary School |  | B | Makkah Region | Makkah | 21.351384081894114, 39.827158409215095 | HLY2020627054561 | 10103688019 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1015 | زمزم الابتدائية | Zamzam Primary School |  | B | Makkah Region | Makkah | 21.569776417228443, 39.776035906072615 | HLY2020627012248 | 10096961525 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1016 | أبي بن كعب المتوسطة | Abi bin Ka'ab Intermediate School |  | B | Makkah Region | Makkah | 21.557728978514106, 39.77056053292044 | HLY2020627012284 | 10053656825 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1017 | أبي سعيد الخدري الابتدائية | Abi Saeed Al-Khudri Primary School |  | B | Makkah Region | Makkah | 21.529335089266045, 39.79498016635642 | HLY2020627036116 | 10053191863 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1018 | عمر الفاروق الثانوية - نظام مسارات | Omar Al-Farouq High School - Masarat System |  | B | Makkah Region | Makkah | 21.257858046763207, 39.83168191306601 | SXE2120627502831 | 10105372002 | 13/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1019 | البيروني الابتدائية | Al-Biruni Primary School |  | B | Makkah Region | Makkah | 21.46543120537429, 39.94261286235746 | SXE2020627071456 | 10053745040 | 16/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1020 | عبدالله بن أم مكتوم المتوسطة | Abdullah bin Umm Maktoum Intermediate School |  | B | Makkah Region | Makkah | 21.394361970230317, 39.442075162302494 | HLY2020627036358 | 10053615331 | 16/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1021 | عمير بن الحمام المتوسطة | Umair bin Al-Hammam Intermediate School |  | B | Makkah Region | Makkah | 21.469549046764673, 39.96058778333442 | SMR2320621013926 | 10105774241 | 16/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1022 | الثانوية السادسة و الخمسون بمكة المكرمة - مسارات | Fifty-Sixth High School in Mecca - Masarat |  | G | Makkah Region | Makkah | 21.462765439713852, 39.95991768358629 | HLY20206270108441 | 10053335112 | 17/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1023 | الثانوية السادسة لتحفيظ القرآن الكريم بمكة المكرمة - مسارات | Sixth High School for Quran Memorization in Mecca - Masarat |  | G | Makkah Region | Makkah | 21.443655526828323, 39.96995968239436 | SMR2420628005523 | 10053825285 | 17/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1024 | ثانوية مريم بنت عمران | Maryam bint Imran High School |  | G | Makkah Region | Makkah | 21.453071777452237, 40.01690508645412 | HLY2020627010679 | 10098976788 | 17/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1025 | ثانوية الجعرانة | Al-Ja'arana High School |  | G | Makkah Region | Makkah | 21.558962164482107, 39.95069487199849 | HLY2020627001899 | 10053643282 | 17/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1026 | المتوسطة الرابعة | Fourth Intermediate School |  | G | Makkah Region | Makkah | 21.559502369972908, 39.783612160779676 | SXE2020627006149 | 10086573683 | 17/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1027 | مدرسة الثانية والعشرين المتوسطة ممدرسة الرابعة والستون الابتدائية | Twenty-Second Intermediate School and Sixty-Fourth Primary School |  | G | Makkah Region | Makkah | 21.360926890710054, 39.82887896355301 | SXE2020627056749 | 10053273781 | 17/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1028 | ابتدائيه الرياض للطفوله المبكره | Riyadh Primary School for Early Childhood |  | G | Makkah Region | Makkah | 21.499579447245186, 39.94927844647362 | SXE2020627070543 | 10053268252 | 2025-04-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1029 | ثانوية خولة بنت اليمان | Khawla bint Al-Yaman High School |  | G | Makkah Region | Makkah | 21.309277109871196, 39.67952217488982 | SXE2120627502461 | 10105119560 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1030 | ابن ماجه للطفولة المبكرة | Ibn Majah for Early Childhood |  | G | Makkah Region | Makkah | 21.431128955122873, 39.787416755796954 | HLY2020627001261 | 10053333575 | 2025-03-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1031 | المتوسطة السادسة بمكة المكرمة | The Sixth Intermediate in Mecca |  | G | Makkah Region | Makkah | 21.44050907095445, 39.81963571094555 | SXE202062707908 | 10053485915 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1032 | التاسعة والثلاثون بعد المائة | The One Hundred Thirty-Ninth |  | G | Makkah Region | Makkah | 21.35030343597336, 39.8286163797635 | SXE2020627057603 | 10053119486 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1033 | الابتدائيه ١٠٤ | Primary 104 |  | G | Makkah Region | Makkah | 21.46052762200192, 39.95177747521121 | SXE2020627061695 | 10053267381 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1034 | ابتدائيه صفية بنت عبد المطلب | Safiyya bint Abdul Muttalib Primary |  | G | Makkah Region | Makkah | 21.533294013853716, 39.78653441632028 | SMR2220621004029 | 10105319711 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1035 | الابتدائية الخامسة والثمانون | The Eighty-Fifth Primary |  | G | Makkah Region | Makkah | 21.48761937888378, 39.93339842023651 | HLY2020627010777 | 10053339031 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1036 | الخليل بن احمد طفولة مبكرة | Khalil bin Ahmed Early Childhood |  | G | Makkah Region | Makkah | 21.34504633078294, 39.90900526393855 | sxe2020627059431 | 10053661880 | 20/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1037 | المتوسطة الرابعة والثلاثون بمكة المكرمة | The Thirty-Fourth Intermediate in Mecca |  | G | Makkah Region | Makkah | 21.35858834929687, 39.89461010325547 | SXE2020627071935, SXE20206227060916 | 10053775577 | 20/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1038 | جعفر بن الزبير الابتدائية - طفولة مبكرة | Jaafar bin Al-Zubair Primary - Early Childhood |  | G | Makkah Region | Makkah | 21.395763326798857, 39.77916387469575 | KFM2120655005659 | 10105126036 | 19/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1039 | أم العلاء الأنصارية الابتدائية | Umm Al-Alaa Al-Ansariyah Primary |  | G | Makkah Region | Makkah | 21.42696652108847, 39.783941117003465 | SXE2020627057610 | 10053378334 | 2025-01-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1040 | الابتدائية العشرون بمكة المكرمة | The Twentieth Primary in Mecca |  | G | Makkah Region | Makkah | 21.43457756994896, 39.81239060276834 | SMR2420628005721 | 10053281675 | 2025-01-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1041 | الابتدائية العشرون بمكة المكرمة | The Twentieth Primary in Mecca |  | G | Makkah Region | Makkah | 21.35884719592216, 39.89550103090238 | HLY2020627036008 | 10053776091 | 20/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1042 | عروة بن الزبير الابتدائية – طفولة مبكرة | Urwah bin Al-Zubair Primary - Early Childhood |  | G | Makkah Region | Makkah | 21.557965642214423, 39.771107328863984 | HLY2020627012279 | 10053656585 | 2025-01-12 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1043 | الإمام أحمد بن حنبل الابتدائية - طفولة مبكرة | Imam Ahmad bin Hanbal Primary - Early Childhood |  | G | Makkah Region | Makkah | 21.443949461961875, 39.83812364769366 | SMR2420628005818 | 10053425309 | 20/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1044 | المتوسطة التاسعة والعشرون بمكة المكرمة | The Twenty-Ninth Intermediate in Mecca |  | G | Makkah Region | Makkah | 21.495974653893505, 39.96587040245815 | HLY2020627001774 | 10053830472 | 19//11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1045 | جويرية بنت الحارث الابتدائية بمكة المكرمة | Juwayriya bint Al-Harith Primary in Mecca |  | G | Makkah Region | Makkah | 21.568955109500283, 39.76546290336363 | HLY2020627011972 | 10053601854 | 30/11/2025 | [17 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1046 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1047 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1048 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1049 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1050 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1051 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1052 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1053 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1054 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1055 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1056 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1057 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1058 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1059 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1060 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1061 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1062 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1063 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1064 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1065 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1066 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1067 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1068 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1069 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1070 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1071 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1072 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1073 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1074 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1075 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1076 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1077 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1078 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1079 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1080 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1081 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1082 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1083 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1084 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1085 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1086 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1087 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1088 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1089 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1090 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1091 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1092 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1093 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1094 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1095 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1096 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1097 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1098 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1099 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1100 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1101 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1102 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1103 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1104 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1105 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1106 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1107 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1108 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1109 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1110 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1111 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1112 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1113 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1114 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1115 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1116 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1117 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1118 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1119 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1120 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1121 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1122 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1123 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1124 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1125 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1126 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1127 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1128 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1129 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1130 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1131 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1132 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1133 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1134 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1135 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1136 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1137 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1138 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1139 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1140 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1141 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1142 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1143 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1144 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1145 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1146 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1147 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1148 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1149 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1150 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1151 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1152 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1153 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1154 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1155 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1156 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1157 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1158 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1159 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1160 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1161 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1162 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1163 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1164 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1165 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1166 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1167 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1168 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1169 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1170 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1171 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1172 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1173 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1174 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1175 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1176 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1177 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1178 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1179 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1180 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1181 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1182 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1183 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1184 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1185 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1186 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1187 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1188 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1189 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1190 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1191 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1192 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1193 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1194 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1195 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1196 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1197 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1198 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1199 | [27 empty] | 0 | 0 | 0 | Not Started
| SS-ZAM-MAK-2-1200 | [27 empty] | 0 | 0 | 0 | Not Started
Total | [28 empty] | 0 | 0 | 0 | 0
Note on M4: 4/2/2025